## year-data
ID | Name | Year | Milestone | Project length | Expected cost | Expected 5309 contribution | Expected other federal funds | Expected opening
301 | Canal Streetcar Spine | 1995 | Preliminary Engineering | 4.4 | 92.6 | 74.1
301 | Canal Streetcar Spine | 1997 | Final Design | 4.7 | 156.6 | 125.3 |  | 2002
301 | Canal Streetcar Spine | 2003 | FFGA Awarded | 4.7 | 161.3 | 129.05 |  | 2004
301 | Canal Streetcar Spine | 2004 | Project Opening | 4.7
302 | CBD to university LRT | 1998 | Preliminary Engineering | 2.5 | 105.75 | 84.6
302 | CBD to university LRT | 2000 | Final Design | 2.5
302 | CBD to university LRT | 2002 | Project Opening | 2.5 | 118.5 | 84.6 | 11.9 | 2002
302 | CBD to university LRT | 2000 | FFGA Awarded | 2.5 | 118.5 | 84.6 | 11.9 | 2002
303 | Central Avenue Bus Rapid Transit Project | 2016 | Project Development | 10.3 | 43.93 | 21.83 |  | 2021
304 | Central Broward Transit Study, Phase I | 2015 | Project Development | 5 |  |  |  | 2022
304 | Central Broward Transit Study, Phase I | 2018 | Project Cancelled
305 | Central Florida Commuter Rail Transit – Initial Operating Segment | 2007 | Preliminary Engineering | 32 | 361.5 | 178.61
305 | Central Florida Commuter Rail Transit – Initial Operating Segment | 2008 | Final Design | 32 | 357.23 | 178.61 |  | 2014
305 | Central Florida Commuter Rail Transit – Initial Operating Segment | 2011 | FFGA Awarded | 32 | 357.23 | 178.61
305 | Central Florida Commuter Rail Transit – Initial Operating Segment | 2014 | Project Opening | 32 | 357.2 |  |  | 2014
306 | Desire Streetcar Line | 2000 | Preliminary Engineering | 2.9 | 93.5 | 65.5 | 28
307 | Draper Transit Corridor | 2009 | Preliminary Engineering | 3.8 | 212.2 | 169.8
307 | Draper Transit Corridor | 2011 | FFGA Awarded | 3.8 | 193.64 | 116.18 | 74.46 | 2013
307 | Draper Transit Corridor | 2013 | Project Opening | 3.8 |  |  |  | 2013
308 | JTA BRT East Corridor | 2015 | Project Development | 18.5 | 33.9 | 16.9 |  | 2017
308 | JTA BRT East Corridor | 2019 | CGA | 18.5 | 33.9 | 16.9
309 | East-West Corridor/Miami Intermodal Center | 1995 | Project Development | 25.8 | 2000
309 | East-West Corridor/Miami Intermodal Center | 1998 | Final Design | 11.9 | 2152.5 | 808
310 | Flagler to duPont Place | 1991 | FFGA Awarded | 2.5 | 108.5 | 43.86 |  | 1994
311 | FrontRunner North Rail Project | 2003 | Preliminary Engineering | 44 | 408
311 | FrontRunner North Rail Project | 2005 | Final Design | 44 | 581
311 | FrontRunner North Rail Project | 2006 | FFGA Awarded | 44 | 611.7
311 | FrontRunner North Rail Project | 2008 | Project Opening | 44 |  |  |  | 2008
312 | Hudson Tunnel | 2016 | Project Development | 6.5 | 13702.43 | 6769 | 153.34 | 2030
313 | Hudson-Bergen Waterfront Light Rail Transit System | 1993 | Preliminary Engineering | 20.5 | 1300 | 623.9
314 | I-35 Commuter Rail | 1999 | Preliminary Engineering | 23 | 30.9 | 24.8
315 | JTA BRT North Corridor | 2010 | Project Development | 9.3 | 33.48 | 26.79 |  | 2014
315 | JTA BRT North Corridor | 2016 | CGA | 9.3 | NAV | NAV |  | 2021
316 | JTA BRT Southeast Corridor | 2011 | Project Development | 11.1 | 23.88 | 19.1 |  | 2014
317 | Largo Metrorail Extension | 1996 | Preliminary Engineering | 2.9 | 350 | 276.5
317 | Largo Metrorail Extension | 2000 | FFGA Awarded | 3.1 | 433.9 | 260.3 |  | 2004
318 | Martin Luther King, Jr. East Busway Extension | 1994 | Preliminary Engineering | 2.3 | 62.8 | 8.58 | 22.82
318 | Martin Luther King, Jr. East Busway Extension | 1996 | Final Design | 2.3 | 62.8 | 8.58 |  | 2001
318 | Martin Luther King, Jr. East Busway Extension | 2003 | Project Opening | 2.3 | 68.8 | 8.58 |  | 2003
319 | Miami (North 27th Avenue Corridor) | 1995 | Project Development | 9.5 | 453 | 317.1
319 | North 27th Avenue Corridor | 2001 | Preliminary Engineering | 9.5 | 87.9 | 61.5
319 | North Corridor Metro Rail Extension | 2003 | Preliminary Engineering | 9.5 | 872.9 | 434.5 | 3.9
319 | North Corridor Metro Rail Extension | 2010 | Project Cancelled | 9.2 | 1340.9 | 700
320 | Minillas Extension | 1999 | Final Design | 1 | 468 | 374.4
324 | North Shore LRT Connector | 2001 | Preliminary Engineering | 1.6 | 326.7 | 194.9
324 | North Shore LRT Connector | 2003 | Final Design | 1.5 | 326.8 | 217.7 | 72.6 | 2008
324 | North Shore LRT Connector | 2006 | FFGA Awarded | 1.2 | 435 | 235.7 | 112.3
324 | North Shore LRT Connector | 2009 | Recovery Plan | 1.2 | 538.7
324 | North Shore LRT Connector | 2012 | Project Opening | 1.2 | 510.4 |  |  | 2012
325 | Ogden/Weber State University BRT | 2019 | Project Development | 5.3 | 99.68 | 64.5 | 7.5 | 2022
326 | Oklahoma city (Map Links) | 1996 | Preliminary Engineering | 3 | 21.7 | 13 | 0.8
327 | Oklahoma city (Map Links) Park Avenue Rail Loop | 1995 | Project Development | 1.74 | 12.5 | 9.2 | 0.08
328 | Orlando (I-4 Central Florida Light Rail System) (MOS) | 1995 | Preliminary Engineering | 25 | 880 | 440 |  | 1998
328 | Orlando (I-4 Central Florida Light Rail System) (MOS) | 1999 | Final Design | 14.6 | 600.1 | 330
329 | Phase I Airport Busway/Wabash HOV Facility | 1994 | FFGA Awarded | 7 | 326.8 | 121 | 135.8 | 1999
330 | Portal North Bridge Replacement | 2016 | Project Development | 2.3 | 1642.2 | 811.2
331 | Prospect MAX Bus Rapid Transit | 2015 | Project Development | 10 | 53.8 | 29.9 | 8 | 2019
332 | Provo-Orem Bus Rapid Transit | 2013 | Project Development | 10.52 | 159.37 | 74.99 |  | 2016
332 | Provo-Orem Bus Rapid Transit | 2016 | CGA | 10.5 | 158.95 | 75
333 | Secaucus Transfer Station | 1994 | FFGA Awarded | NA | 444.26 | 444.26 |  | 2002
334 | South Corridor Rapid Transit Project | 2019 | Project Development | 20 | 299.81 | 100 |  | 2022
335 | South Extension of the Automated Skyway Express (ASE) | 1991 | FFGA Awarded | 1.2 | 133.7 | 15 |  | 1997
336 | South Miami-Dade Busway Extension | 1998 | Preliminary Engineering | 11.5 | 88.8 | 23.4 | 38.6
336 | South Miami-Dade Busway Extension | 2000 | Final Design | 11.5 | 88.8 | 23.4 | 38.6
337 | Southtown BRT | 1995 | Preliminary Engineering | 10 | 25.9 | 12.3
337 | Southtown BRT | 2005 | Final Design | 10 | 25.9 | 12.3
338 | Southtown Corridor | 1995 | Preliminary Engineering | 15.2 | 450 | 360
339 | Southwest Corridor | 2015 | Project Development | 12.9 | 19 | 9.5
340 | St. Clair County, Illinois Corridor | 1996 | Preliminary Engineering | 27 | 431.5
341 | St. Claude and Elysian Fields Streetcar Extensions | 2018 | Project Development | 1.1 |  |  |  | 2023
342 | Stage II Light Rail Transit Reconstruction Project | 1996 | Preliminary Engineering | 12 | 414 | 232 | 99.2
342 | Stage II Light Rail Transit Reconstruction Project | 1996 | Final Design | 12 | 512.5 | 162.6 | 237.4
342 | Stage II Light Rail Transit Reconstruction Project | 2001 | FFGA Awarded | 12 | 386.46 | 100.2 | 133.77 | 2004
343 | Streetcar Expansion | 2017 | Project Development | 3.5 | 351.63 | 174.06 |  | 2025
344 | SunRail Connector to Orlando Airport | 2015 | Project Development | 5.5 | 225 | 74.99
345 | SunRail Phase II North | 2013 | Project Development | 12.2 | 68.68 | 34.34 |  | 2017
346 | SunRail Phase II South | 2010 | Preliminary Engineering | 17.2 | 185 | 92.5 |  | 2017
346 | SunRail Phase II South | 2015 | FFGA Awarded | 17.2 | 186 | 93 |  | 2017
347 | Tampa Bay Regional Rail | 1999 | Preliminary Engineering | 20.1 | 1455.5 | 727.7
348 | Tampa Streetcar Extension Project | 2018 | Project Development | 2.6 | 102.6 | 51.27 |  | 2024
349 | TramLinkBR | 2016 | Project Development | 3 | 170 | 84 |  | 2021
350 | TRAX Light Rail System- Medical Center Extension | 2002 | FFGA Awarded | 1.53 | 89.39 | 53.63 |  | 2004
350 | TRAX Light Rail System- Medical Center Extension | 2001 | Final Design | 1.5 | 89.4 | 53.6
350 | TRAX Light Rail System- Medical Center Extension | 1998 | Preliminary Engineering | 10.85 | 521.9
350 | TRAX Light Rail System- Medical Center Extension | 2003 | Project Opening | 1.53
351 | Tren Urbano | 1996 | FFGA Awarded | 10.4 | 1250 | 312.4 | 300 | 2001
351 | Tren Urbano | 1999 | FFGA Awarded-2 | 10.7 | 1676 | 307.41 | 400.9 | 2005
351 | Tren Urbano | 2005 | Project Opening | 10.7 | 2250 | 307.41 | 400.9 | 2005
352 | Tri-County Commuter Rail | 1995 | Final Design | 67 | 428.29 | 189.5 | 56.39 | 1997
354 | Wave Streetcar | 2013 | Project Development | 2.7 | 142.59 | 49.65 | 21.5 | 2016
354 | Wave Streetcar | 2017 | CGA | 2.8 | 195.3 | 60.8
354 | Wave Streetcar | 2018 | Project Cancelled
309b | East-West Corridor/Miami Intermodal Center (MOS) | 1996 | Preliminary Engineering | 11.8 | 1574 | 550.9
309b | East-West Corridor/Miami Intermodal Center (MOS) | 1995 | Project Development | 11.8 | 1212 | 424.2
309b | East-West Corridor/Miami Intermodal Center (MOS) | 1998 | Final Design | 11.2 | 1480
310b | Flagler to duPont Place - ASE Extension | 1994 | FFGA Awarded | 0.3 | 31.4 | 25 |  | 1996
313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | 1993 | Preliminary Engineering | 10
313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | 1996 | FFGA Awarded | 9.6 | 992.14 | 604.09 | 281.65 | 2000
313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | 2002 | Project Opening | 9.3 | 992.14 | 604.09 | 281.65 | 2002
313b | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) | 2000 | FFGA Awarded | 5.1 | 1215.4 | 500 | 153.7 | 2005
313b | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) | 1998 | Final Design | 6.1 | 1112.8 | 721.6 | 273.8
313b | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) | 2003 | Project Opening | NAV | 1200
321a | Newark-Elizabeth Rail Link | 1995 | Preliminary Engineering | 8.8 | 694
321b | Newark-Elizabeth Rail Link (MOS I) | 1998 | Preliminary Engineering | 1 | 150 | 112.5 | 35.7
321b | Newark-Elizabeth Rail Link (MOS I) | 2000 | FFGA Awarded | 1 | 207.75 | 141.95 | 25.3 | 2005
338b | Southtown Corridor (Segment) | 1995 | Preliminary Engineering | 5.6 | 220 | 176
340b | St. Clair County, Illinois Corridor (IOS-1) | 1996 | Preliminary Engineering | 17.4 | 295 | 236
340b | St. Clair County, Illinois Corridor (IOS-1) | 1996 | Final Design | 17.4 | 339.2 | 243.93 |  | 2001
340b | St. Clair County, Illinois Corridor (IOS-1) | 1996 | FFGA Awarded | 17.4 | 339.2 | 243.93
340b | St. Clair County, Illinois Corridor (IOS-1) | 2001 | Project Opening | 17.4 | 339.2 | 243.93 |  | 2001
352b | Tri-County Commuter Rail / Segment 5 | 1997 | Preliminary Engineering | 72 | 327 | 110.5 | 91.4 | 2005
352b | Tri-County Commuter Rail / Segment 5 | 1999 | Final Design | 71.7 | 327 | 110.5 | 74.2 | 2005
352b | Tri-County Commuter Rail / Segment 5 | 2000 | FFGA Awarded | 71.7 | 327 | 110.5 | 91.4 | 2005
352b | Tri-County Commuter Rail / Segment 5 | 2004 | FFGA Awarded-2 | 72 | 333.9 | 110.5 |  | 2006
352b | Tri-County Commuter Rail / Segment 5 | 2006 | Project Opening | 72 | 345.6 | 110.5 |  | 2006