## year-data
temp_id | Project_ID | Name | Year | Milestone | Project length | Expected cost | Expected 5309 contribution | Expected other federal funds | Expected opening | Source
354 | 350 | TRAX Light Rail System- Medical Center Extension | 2002 | FFGA Awarded | 1.53 | 89.39 | 53.63 |  | 2004 | AR-2005
355 | 350 | TRAX Light Rail System- Medical Center Extension | 2001 | Final Design | 1.5 | 89.4 | 53.6 |  |  | AR-2003
356 | 350 | TRAX Light Rail System- Medical Center Extension | 1998 | Preliminary Engineering | 1.53 |  |  |  |  | AR-2005
357 | 350 | TRAX Light Rail System- Medical Center Extension | 2003 | Project Opening | 1.53 |  |  |  |  | BA
361 | #N/A | TRAX Light Rail System | 1999 | Final Design | [5 empty] | BA
362 | #N/A | TRAX Light Rail System | 1998 | Preliminary Engineering | [5 empty] | BA
363 | 307 | Draper Transit Corridor | 2009 | Preliminary Engineering |  | 193.64 | 116.18 |  |  | AR-2013
364 | 307 | Draper Transit Corridor | 2011 | FFGA Awarded |  | 193.64 | 116.18 |  |  | AR-2013
365 | 311 | FrontRunner North Rail Project | 2003 | Preliminary Engineering | 44 | 408 |  |  |  | BA
366 | 311 | FrontRunner North Rail Project | 2005 | Final Design | 44 | 581 |  |  |  | BA
367 | 311 | FrontRunner North Rail Project | 2006 | FFGA Awarded | 44 | 611.7 |  |  |  | BA
368 | 311 | FrontRunner North Rail Project | 2008 | Project Opening | 44 |  |  |  |  | BA
369 | 302 | CBD to university LRT | 1998 | Preliminary Engineering | 2.5 |  |  |  |  | AR-2005
370 | 302 | CBD to university LRT | 2000 | Final Design | 2.5 |  |  |  |  | AR-2005
372 | 302 | CBD to university LRT | 2001 | Project Opening | 2.5 | 118.5 | 84.6 | 11.9 | 2002 | AR-2005
373 | 302 | CBD to university LRT | 2000 | FFGA Awarded | 2.5 | 118.5 | 84.6 | 11.9 | 2002 | AR-2002
374 | 332 | Provo-Orem Bus Rapid Transit | 2013 | Project Development | 10.52 | 159.37 | 74.99 |  | 2016 | AR-2014
377 | 332 | Provo-Orem Bus Rapid Transit | 2016 | CGA | [5 empty] | AR-2018
382 | 351 | Tren Urbano | 1996 | FFGA Awarded | 10.4 | 1121.9 | 312.4 | 300 | 2004 | AR-1997
388 | 351 | Tren Urbano | 2005 | Project Opening | 10.7 | 1653.61 | 307.41 | 400.9 |  | AR-2007
394 | 340 | St. Clair County, Illinois Corridor (IOS-1) | 1996 | FFGA Awarded | 17.4 | 339.2 | 243.93 |  |  | AR-1999
395 | #N/A | St. Clair County, Illinois Corridor | 1996 | Preliminary Engineering | 17.4 | 339.2 | 243.93 |  |  | AR-2005
396 | #N/A | St. Clair County, Illinois Corridor | 1996 | Final Design | 17.4 | 339.2 | 243.93 |  | 2001 | AR-2005
391 | #N/A | St. Clair County, Illinois Corridor | 1996 | FFGA Awarded | 17.4 | 339.2 | 243.93 |  | 2001 | AR-1997
398 | #N/A | St. Clair County, Illinois Corridor | 2001 | Project Opening | 17.4 | 339.2 | 243.93 |  |  | AR-2005
399 | 338 | Southtown Corridor | 1995 | Preliminary Engineering | 15.2 | 450 | 360 |  |  | AR-1997
400 | #N/A | Southtown Corridor (Segment) | 1995 | Preliminary Engineering | 5.6 | 220 | 176 |  |  | AR-2000
402 | 343 | Streetcar Expansion | 2017 | Project Development | 3.5 | 351.63 | 174.06 |  | 2025 | PP
403 | 337 | Southtown BRT | 1995 | Preliminary Engineering | 10 | 25.9 | 12.3 |  |  | AR-2005
405 | 331 | Prospect MAX Bus Rapid Transit | 2015 | Project Development | [5 empty] | AR-2017
407 | 314 | I-35 Commuter Rail | 1999 | Preliminary Engineering | 23 | 30.9 | 24.8 |  |  | AR-2002
415 | 353 | Tri-Rail Double-track Corridor Improvement | 1997 | Preliminary Engineering | 72 | 327 | 110.5 | 91.4 | 2005 | BA
416 | 353 | Tri-Rail Double-track Corridor Improvement | 1999 | FFGA Awarded | 72 | 327 |  |  | 2005 | BA
418 | 353 | Tri-Rail Double-track Corridor Improvement | 2006 | Project Opening | 72 |  |  |  |  | BA
420 | 309 | East-West Corridor/Miami Intermodal Center | 1996 | Preliminary Engineering | [5 empty] | AR-1998
424 | 322 | North 27th Avenue Corridor | 2001 | Preliminary Engineering | 9.5 | 87.9 | 61.5 |  |  | AR-2002
426 | 334 | South Corridor Rapid Transit Project | 2019 | Project Development | 20 | 299.81 | 100 |  | 2022 | PP
427 | 336 | South Miami-Dade Bustway Extension | 1998 | Preliminary Engineering | 11.5 | 88.8 | 23.4 | 38.6 |  | AR-2002
428 | 336 | South Miami-Dade Bustway Extension | 2000 | Final Design | 11.5 | 88.8 | 23.4 | 38.6 |  | AR-2002
429 | 304 | Central Broward Transit Study, Phase I | 2015 | Project Development | [5 empty] | AR-2017
430 | #N/A | Central Florida Light Rail System- Initial Operating Segment | 2011 | FFGA Awarded | 32 | 357.23 | 178.61 |  | 2014 | AR-2013
431 | #N/A | Central Florida Light Rail System- Initial Operating Segment | 2008 | Final Design | 32 | 357.23 | 178.61 |  | 2014 | AR-2013
432 | #N/A | Central Florida Light Rail System- Initial Operating Segment | 2007 | Preliminary Engineering | 32 | 357.23 | 178.61 |  | 2014 | AR-2013
435 | 345 | SunRail Phase II North | 2014 (Anticipated) | FFGA Awarded | 12 | 79.2 | 39.6 |  | 2017 | AR-2015
436 | 345 | SunRail Phase II North | 2013 | Project Development | 12.2 | 68.68 | 34.34 |  | 2017 | AR-2016
438 | 346 | SunRail Phase II South | 2010 | Engineering | 17.2 | 185 | 92.5 |  | 2017 | AR-2014
441 | 346 | SunRail Phase II South | 2015 | CGA |  | 186 | 93 |  |  | AR-2017
443 | 344 | SunRail Connector to Orlando Airport | 2015 | Project Development | 5.5 |  |  |  |  | AR-2017
445 | 305 | Central Florida Commuter Rail Transit – Initial Operating Segment | 2007 | Preliminary Engineering | 32 | 357.23 | 178.61 |  |  | AR-2013
447 | 305 | Central Florida Commuter Rail Transit – Initial Operating Segment | 2008 | Final Design | 32 | 357.23 | 178.61 |  | 2014 | AR-2013
448 | 305 | Central Florida Commuter Rail Transit – Initial Operating Segment | 2011 | FFGA Awarded | 32 | 357.23 | 178.61 |  |  | AR-2013
449 | 305 | Central Florida Commuter Rail Transit – Initial Operating Segment | 2014 | Project Opening | 32 |  |  |  |  | BA
450 | 310 | Flagler to duPont Place | 1994 | FFGA Awarded | 0.3 | 31.4 | 25 |  |  | AR-1997
451 | 310 | Flagler to duPont Place | 1991 | FFGA Awarded |  | 108.5 | 43.86 |  |  | AR-1998
452 | 335 | South Extension of the Automated Skyway Express (ASE) | 1991 | FFGA Awarded | 1.2 | 133.7 | 15 |  |  | AR-1995
453 | #N/A | JTA Bus Rapid Transit North Corridor | 2010 | Project Development | 9.3 | 33.48 | 26.79 |  |  | AR-2013
454 | #N/A | BRT North Corridor | 2015 | CGA | [5 empty] | AR-2017
455 | 308 | East Corridor | 2015 | Project Development |  | 33.9 | 16.9 |  |  | AR-2017
456 | #N/A | JTA Bus Rapid Transit Southeast Corridor | 2011 | Project Development | 11.1 | 23.88 | 19.1 |  |  | AR-
457 | 339 | Southwest Corridor | 2015 | Project Development |  | 19 | 9.5 |  |  | AR-2017
458 | 354 | Wave Streetcar | 2013 | Project Development | 2.7 | 142.59 | 49.65 | 21.5 | 2016 | AR-2014
461 | 354 | Wave Streetcar | 2017 | CGA | 2.8 |  |  |  |  | AR-2019
462 | 316 | JTA BRT Southeast Corridor | 2011 | Project Development | 11.1 | 23.88 | 19.1 |  | 2014 | AR-2014
465 | 315 | JTA BRT North Corridor | 2010 | Project Development | 9.3 | 33.48 | 26.79 |  | 2014 | AR-2014
468 | 303 | Central Avenue Bus Rapid Transit Project | 2016 | Project Development | 10.3 | 43.93 | 21.83 |  | 2021 | OTHER
469 | 347 | Tampa Bay Regional Rail | 1999 | Preliminary Engineering | 20.1 | 1455.5 | 727.7 |  |  | AR-2005
475 | 317 | Largo Metrorail Extension | 2000 | Final Design | 3.1 | 433.9 | 260.3 |  | 2004 | AR-2005
476 | 317 | Largo Metrorail Extension | 2000 | FFGA Awarded | 3.1 | 433.9 | 260.3 |  | 2004 | AR-2005
477 | 301 | Canal Streetcar Spine | 1995 | Preliminary Engineering | 4.4 | 92.6 | 74.1 |  |  | AR-1997
479 | 301 | Canal Streetcar Spine | 1997 | Final Design | 4.7 | 156.6 | 125.3 |  | 2002 | AR-2000
482 | 301 | Canal Streetcar Spine | 2003 | FFGA Awarded | 4.7 | 161.3 | 129.05 |  | 2004 | AR-2005
483 | 306 | Desire Streetcar Line | 2000 | Preliminary Engineering | 2.9 | 93.5 | 65.5 |  |  | AR-2002
487 | #N/A | TramLinkBR Streetcar | 2016 | Project Development | [5 empty] | AR-2018
489 | #N/A | Hudson-Bergen Waterfront Light Rail Transit System | 1993 | Preliminary Engineering | 20.5 | 1300 | 623.9 |  |  | AR-1997
356 | 350 | TRAX Light Rail System- Medical Center Extension |  | Preliminary Engineering | 1.58 | 521.9 |  |  |  | BA
378 | 325 | Ogden/Weber State University BRT |  | Project Development | 5.3 |  |  |  | 2022 | PP
404 | 337 | Southtown BRT |  | Final Design | 10 | 25.9 | 12.3 |  |  | OTHER
411 | 352b | Tri-County Commuter Rail / Segment 5 |  | Final Design | 71.7 | 327 | 110.5 | 74.2 | 2005 | AR-2001
425 | 323 | North Corrido Metro Rail Extension |  | Preliminary Engineering | 9.5 | 872.9 | 434.5 | 3.9 |  | AR-2005
470 | 348 | Tampa Streetcar Extension Project |  | Project Development | 2.6 |  | 51.27 |  | 2024 | OTHER
486 | 341 | St. Claude and Elysian Fields Streetcar Extensions |  | Project Development | 1.1 |  |  |  | 2023 | PP
379 | 320 | Minillas Extension |  |  |  | 477.5 | 382.6 |  |  | AR-2002
379 | 320 | Minillas Extension |  |  | 1 | 468 | 374.4 |  |  | AR-2002
381 | 351 | Tren Urbano |  |  | 1 | 561.5 | 449.2 |  |  | AR-2004
391 | #N/A | St. Clair County, Illinois Corridor | 1996 | FFGA Awarded | 26 | 295 | 236 |  |  | AR-1997
391 | #N/A | St. Clair County, Illinois Corridor | 1996 | FFGA Awarded | 26 | 339.2 | 243.93 |  |  | AR-1997
391 | #N/A | St. Clair County, Illinois Corridor | 1996 | FFGA Awarded | 26 | 339.2 | 243.93 |  |  | AR-1997
408 | 352a | Tri-County Commuter Rail |  |  | 67 | 428.29 | 189.5 | 56.39 | 1997 | AR-1997
408 | 352a | Tri-County Commuter Rail |  |  | 70 | 428.3 | 206.4 | 39.5 | 1997 | AR-1997
408 | 352a | Tri-County Commuter Rail |  |  | 71.7 | 422 | 130.8 | 93.3 | 2007 | AR-1997
412 | 352b | Tri-County Commuter Rail / Segment 5 |  |  |  | 327 | 110.5 | 91.4 | 2005 | AR-2002
419 | 309 | East-West Corridor/Miami Intermodal Center |  |  | 24.3 to 25.8 | 1212 | 424.2 |  |  | AR-1997
421 | #N/A | East-West Corridor/Miami Intermodal Center (MOS) | 1996 | Preliminary Engineering | 11.8 | 1574 | 550.9 |  |  | AR-1998
421 | #N/A | East-West Corridor/Miami Intermodal Center (MOS) | 1996 | Preliminary Engineering | 11.9 | 2152.5 | 808 |  |  | AR-1998
423 | 319 | Miami (North 27th Avenue Corridor) |  |  | 9.5 | 453 | 317.1 |  |  | AR-1997
433 | 328 | Orlando (I-4 Central Florida Light Rail System) (MOS) |  |  | 25 | 880 | 440 |  | 1998 | AR-1998
433 | 328 | Orlando (I-4 Central Florida Light Rail System) (MOS) |  |  | 14.6 | 600.1 | 330 |  |  | AR-1998
471 | #N/A | Largo Corridor | 1996 | Preliminary Engineering | 2.9 | 350 | 276.5 |  |  | AR-1997
471 | #N/A | Largo Corridor | 1996 | Preliminary Engineering | 3.1 | 350 | 276.5 |  |  | AR-1997
473 | #N/A | Largo Corridor |  |  | 3.1 | 397.1 | 316.1 |  | 2005 | AR-2000
474 | #N/A | Largo Corridor | 2000 | FFGA Awarded | 3.1 | 433.9 | 260.3 |  | 2004 | AR-2002
488 | 349 | TramLinkBR | 2016 | Project Development | 3 | 170 | 84 |  | 2021 | PP
490 | #N/A | Hudson-Bergen Waterfront Light Rail Transit System |  |  | 20.2 | 1600 |  |  |  | AR-1999
490 | #N/A | Hudson-Bergen Waterfront Light Rail Transit System |  |  | 20.2 | 2000 |  |  |  | AR-1999
492 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | 1993 | Preliminary Engineering | 10 |  |  |  |  | AR-1997
493 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | 1996 | FFGA Awarded | 9.6 | 992.14 | 604.09 | 281.65 | 2000 | AR-1998
493 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | 1996 | FFGA Awarded | 9.6 | 992.14 | 604.09 | 281.65 | 2000 | AR-1998
493 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | 1996 | FFGA Awarded | 9.3 | 992.14 | 604.09 | 281.65 | 2002 | AR-1998
493 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | 1996 | FFGA Awarded | 9.3 | 992.14 | 604.09 | 281.65 | 2002 | AR-1998
497 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | 2002 | Project Opening | 9.3 | 992.14 | 604.09 | 281.65 | 2002 | AR-2005
498 | 313b | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) | 2000 | FFGA Awarded | 6.1 | 1215.4 | 500 | 153.7 |  | AR-2010
498 | 313b | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) | 2000 | FFGA Awarded | 5.1 | 1215.4 | 500 | 153.7 | 2005 | AR-2010
500 | 313b | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) |  |  | 6.1 | 1112.8 | 721.6 | 273.8 |  | AR-2001
501 | 321a | Newark-Elizabeth Rail Link |  |  | 8.8 | 694 |  |  |  | AR-1997
502 | 321b | Newark-Elizabeth Rail Link (MOS I) |  |  | 1 | 150 | 112.5 | 35.7 |  | AR-2000
502 | 321b | Newark-Elizabeth Rail Link (MOS I) |  |  | 1 | 207.7 | 141.9 | 65.2 |  | AR-2000
504 | 321b | Newark-Elizabeth Rail Link (MOS I) | 2000 | FFGA Awarded | 1 | 207.75 | 141.95 | 25.3 | 2005 | AR-2005
505 | 333 | Secaucus Transfer Station | 1994 | FFGA Awarded | _ | 444.26 | 444.26 |  | 2002 | AR-1997
506 | 312 | Hudson Tunnel | 2016 | Project Development | [5 empty] | AR-2018
507 | 330 | Portal North Bridge Replacement | 2016 | Project Development | [5 empty] | AR-2018
507 | 330 | Portal North Bridge Replacement | 2016 | Project Development | 2.44 | 1716.18 | 811.12 | 122.45 | 2026 | AR-2018
509 | 327 | Oklahoma city (Map Links) Park Avenue Rail Loop |  |  | 1.74 | 12.5 | 9.2 | 0.08 |  | AR-1997
510 | 326 | Oklahoma city (Map Links) |  |  | 3 | 21.7 | 13 | 0.8 |  | AR-1998
511 | 329 | Phase I Airport Busway/Wabash HOV Facility | 1994 | FFGA Awarded | 7 | 326.8 | 121 | 135.8 |  | AR-1996
511 | 329 | Phase I Airport Busway/Wabash HOV Facility | 1994 | FFGA Awarded | 7 | 326.8 | 121 | 135.8 |  | AR-1996
511 | 329 | Phase I Airport Busway/Wabash HOV Facility | 1994 | FFGA Awarded | 7 | 321.7 | 149.83 | 101.87 | 1999 | AR-1996
511 | 329 | Phase I Airport Busway/Wabash HOV Facility | 1997 | FFGA Awarded | 5 | 326.71 | 135.91 | 101.87 |  | AR-1996
515 | 318 | Martin Luther King, Jr. East Busway Extension |  |  | 2.3 | 62.8 | 8.58 | 22.82 |  | AR-2000
516 | 342 | Stage II Light Rail Transit Reconstruction Project | 1996 | Preliminary Engineering | 12 | 414 | 232 | 99.2 |  | AR-1997
517 | 342 | Stage II Light Rail Transit Reconstruction Project | 1996 | Final Design | 12 | 512.5 | 162.6 | 237.4 |  | AR-2000
516 | 342 | Stage II Light Rail Transit Reconstruction Project |  | Preliminary Engineering | 10.7 | 383.7 | 100.2 | 3.9 |  | AR-1997
519 | 342 | Stage II Light Rail Transit Reconstruction Project | 2001 | FFGA Awarded | 12 | 386.46 | 100.2 | 133.77 | 2004 | AR-2005
520 | 324 | North Shore LRT Connector | 2001 | Preliminary Engineering | 1.6 | 389.9 | 194.9 |  |  | AR-2002
520 | 324 | North Shore LRT Connector | 2001 | Preliminary Engineering | 1.6 | 389.9 | 272.9 | 39 |  | AR-2002
520 | 324 | North Shore LRT Connector | 2001 | Preliminary Engineering | 1.6 | 389.9 | 233.9 | 77.9 | 2007 | AR-2002
523 | 324 | North Shore LRT Connector | 2003 | Final Design | 1.5 | 362.8 | 217.7 | 72.6 | 2008 | AR-2005
524 | 324 | North Shore LRT Connector | 2006 | FFGA Awarded | 1.2 | 435 | 235.7 | 112.3 |  | AR-2010
520 | 324 | North Shore LRT Connector | 2001 | Preliminary Engineering | 1.2 | 326.7 |  |  |  | AR-2002
523 | 324 | North Shore LRT Connector | 2003 | Final Design | 1.2 | 326.8 |  |  |  | AR-2005
524 | 324 | North Shore LRT Connector | 2006 | FFGA Awarded | 1.2 | 435 |  |  |  | AR-2010
528 | 324 | North Shore LRT Connector | 2009 | Recovery Plan | 1.2 | 538.7 |  |  |  | BA
529 | 324 | North Shore LRT Connector | 2012 | Project opening | 1.2 |  |  |  |  | BA