## New Starts Projects
Project ID | Project Name | City | Additional cities | State | Additional states | Project mode | Project type | Project length | Grant program | Project milestone | Year of milestone | Planned opening year | Total Project cost ($ Million) | Section 5309 funding | Other Federal funding | Source document | Year of source document | Notes/ comments | Possible grant programs
111 | North line extension | Atlanta | _ | Georgia | _ | Heavy Rail | Expansition of existing system | 1.9 | New Starts | FFGA Awarded | 1994 |  | 381.31 | 305.01 |  | Annual report on funding recommendations | 1997
111 | North line extension | Atlanta | _ | Georgia | _ | Heavy Rail | Expansition of existing system | 1.9 | New Starts | Final Design | 1993 |  |  |  |  | Annual report on funding recommendations | 1997
111 | North line extension | Atlanta | _ | Georgia | _ | Heavy Rail | Expansition of existing system | 1.9 | New Starts | Final Design | 1991-2 |  |  |  |  | Annual report on funding recommendations | 1998
111 | North line extension | Atlanta | _ | Georgia | _ | Heavy Rail | Expansition of existing system | 1.9 | New Starts | FFGA Awarded | 1994 |  | 463.18 | 305.01 |  | Annual report on funding recommendations | 2000
| North line extension | Atlanta | _ | Georgia | _ | Heavy Rail | Expansition of existing system | 1.9 | New Starts | FFGA Awarded | 1994 |  | 463.18 | 370.54 |  | Annual report on funding recommendations | 2001
s | North line extension | Atlanta | _ | Georgia | _ | Heavy Rail | Expansition of existing system | 2.3 | New Starts | FFGA Awarded | 1994 | 2000 | 463.18 | 370.54 |  | Annual report on funding recommendations | 2005 | Amended FFGA because of the change in the project's scope
211 | LRT Extensions | Baltimore | _ | Maryland | _ | Light Rail | Expansition of existing system | 7.25 | New Starts | FFGA Awarded | 1994 | 1997 | 106.34 | 84.90 |  | Annual report on funding recommendations | 1997
212 | Baltimore Central Light Rail Double Tracking | Baltimore | _ | Maryland | _ | Light Rail | Improvement of existing service | 9.4 | New Starts | Preliminary Engineering | 1999 |  | 150 | 120.00 |  | Annual report on funding recommendations | 2000
212 | Baltimore Central Light Rail Double Tracking | Baltimore | _ | Maryland | _ | Light Rail | Improvement of existing service | 9.4 | New Starts | Preliminary Engineering | 1999 |  | 153.7 | 120 | 3 | Annual report on funding recommendations | 2001
212 | Baltimore Central Light Rail Double Tracking | Baltimore | _ | Maryland | _ | Light Rail | Improvement of existing service | 9.4 | New Starts | FFGA Awarded | 2000 |  | 153.7 | 120 | 3 | Annual report on funding recommendations | 2002
212 | Baltimore Central Light Rail Double Tracking | Baltimore | _ | Maryland | _ | Light Rail | Improvement of existing service | 9.4 | New Starts | Final Design | 2001 |  |  |  |  | Annual report on funding recommendations | 2007
212 | Baltimore Central Light Rail Double Tracking | Baltimore | _ | Maryland |  | Light Rail | Improvement of existing service | 9.4 | New Starts | FFGA Awarded | 2001 | 2006 | 153.7 | 120 | 3 | Annual report on funding recommendations | 2007
| MARC Commuter Rail Improvement | Maryland City | Baltimore, Washingotn DC | Maryland |  | Commuter Rail | Improvement of existing service |  | New Starts | Preliminary Engineering |  |  | 90.7 | 37.8 | 24.5 | Annual report on funding recommendations | 2003 | 2002 document states that the project has been broken down to three projects including the Penn-Cameden connection
| MARC Penn-Camden connection | Baltimore | _ | Maryland |  | Commuter Rail | Improvement of existing service |  | New Starts | Preliminary Engineering |  |  | 85.1 | 40.9 | 13.5 | Annual report on funding recommendations | 2002
| MARC Penn-Camden connection | Baltimore | _ | Maryland |  | Commuter Rail | Improvement of existing service | 30.8 | New Starts | Final Design |  |  | 30.8 | 12.4 |  | Annual report on funding recommendations | 2004
| MARC Frederick Extension & Rolling Stock Procurement | Maryland City | _ | Maryland |  | Commuter Rail | Expansition of existing system |  | New Starts |  |  | 1998 | 131.56 | 105.25 |  | Annual report on funding recommendations | 1997 | Ridership forecast for the year 2010 is 1,600 daily passengers on this extension.
| MARC Frederick Extension & Rolling Stock Procurement | Maryland City | _ | Maryland |  | Commuter Rail | Expansition of existing system |  | New Starts | FFGA Awarded | 1995 | 1999 | 131.56 | 105.25 |  | Annual report on funding recommendations | 1998
| MARC Frederick Extension & Rolling Stock Procurement | Maryland City | _ | Maryland |  | Commuter Rail | Expansition of existing system |  | New Starts | FFGA Awarded | 1995 | 2001 | 131.56 | 105.25 |  | Annual report on funding recommendations | 1999
| MARC Frederick Extension & Rolling Stock Procurement | Maryland City | _ | Maryland |  | Commuter Rail | Expansition of existing system |  | New Starts | FFGA Awarded | 1995 | 2001 | 131.56 | 105.25 |  | Annual report on funding recommendations | 2000
| Baltimore Red Line | Baltimore |  | Maryland |  | Light Rail | Introduction of new mode | 14.1 | New Starts | Preliminary Engineering | 2011 | 2021 | 2574.8 | 1250 |  | Annual report on funding recommendations | 2014 | The project’s capital cost estimate has increased from $2,219.25 million to $2,574.80 million due to increased tunneling, higher costs for train control, power supply, and communication systems than were previously estimated.
| Baltimore Red Line | Baltimore |  | Maryland |  | Light Rail | Introduction of new mode | 14.1 | New Starts | Project Development | 2013 | 2022 | 2644.52 | 900 |  | Annual report on funding recommendations | 2015 | Project capital costs increased from $2,574.80 million to $2,644.52 million primarily due to increased construction costs for underground stations and for the heavy maintenance facility. The number of vehicles to be purchased was reduced from 28 to 26 LRVs by eliminating a two-car gap train from the operating plan. The requested amount of New Starts funding for the Red Line was reduced
| Baltimore Red Line | Baltimore |  | Maryland |  | Light Rail | Introduction of new mode | 14.1 | New Starts | Project Development | 2013 | 2023 | 2997.75 | 900 | Section 5307 Urbanized Area Formula Funds: 55.2 mn | Annual report on funding recommendations | 2016 | Project capital costs increased from $2,644.52 million to $2,997.75 million due to further development of the project design and resulting adjustments to the cost estimate, inclusion of finance charges, and schedule modifications.
| Maryland National Capital Purple Line | Bethesda | New Carrollton | Maryland |  | Light Rail | Introduction of new mode | 16.2 | New Starts | Preliminary Engineering | 2011 | 2020 | 1,925.46 | 962.60 |  | Annual report on funding recommendations | 2013
| Maryland National Capital Purple Line | Bethesda | New Carrollton | Maryland |  | Light Rail | Introduction of new mode | 16.2 | New Starts | Project Development | 2012 | 2020 | 2151.66 | 1053 |  | Annual report on funding recommendations | 2014
| Maryland National Capital Purple Line | Bethesda | New Carrollton | Maryland |  | Light Rail | Introduction of new mode | 16.2 | New Starts | Project Development | 2012 | 2020 | 2371.15 | 900 |  | Annual report on funding recommendations | 2015
| Maryland National Capital Purple Line | Bethesda | New Carrollton | Maryland |  | Light Rail | Introduction of new mode | 16.2 | New Starts | Engineering | 2014 | 2020 | 2448.22 | 900 |  | Annual report on funding recommendations | 2016
| Maryland National Capital Purple Line | Bethesda | New Carrollton | Maryland |  | Light Rail | Introduction of new mode | 16.2 | New Starts | CGA | 2017 |  |  |  |  | Annual report on funding recommendations | 2019
| Maryland National Capital Purple Line | Bethesda | New Carrollton | Maryland |  | Light Rail | Expansition of existing system | 16.2 | New Starts | Preliminary Engineering | 2011 | 2022 | 2,407.03 | 900 | 36 | Project Profile | 2020
| Maryland National Capital Purple Line | Bethesda | New Carrollton | Maryland |  | Light Rail | Expansition of existing system | 16.2 | New Starts | Engineering | 2014 | 2022 | 2,407.03 | 900 | 36 | Project Profile | 2020
| Maryland National Capital Purple Line | Bethesda | New Carrollton | Maryland |  | Light Rail | Expansition of existing system | 16.2 | New Starts | FFGA Awarded | 2017 | 2022 | 2,407.03 | 900 | 36 | Project Profile | 2020
311-a | South Boston Piers Phase I (MOS-2) | Boston |  | Massachussettes |  | Transitway | Expansition of existing system | 1 | New Starts | Preliminary Engineering | 1993 | 2000 | 413.41 | 330.73 |  | Annual report on funding recommendations | 1996
311-a | South Boston Piers Phase I (MOS-2) | Boston |  | Massachussettes |  | Transitway | Expansition of existing system | 1 | New Starts | FFGA Awarded | 1994 | 2000 | 413.41 | 330.73 |  | Annual report on funding recommendations | 1997
311-a | South Boston Piers Phase I (MOS-2) | Boston |  | Massachussettes |  | Transitway | Expansition of existing system | 1 | New Starts | FFGA Awarded | 1994 | 2002 | 413.41 | 330.73 |  | Annual report on funding recommendations | 1999
311-a | South Boston Piers Phase I (MOS-2) | Boston |  | Massachussettes |  | Transitway | Expansition of existing system | 1 | New Starts | FFGA Awarded | 1994 | 2002 | 513.41 | 330.73 | 82.68 | Annual report on funding recommendations | 2000
311-a | South Boston Piers Phase I (MOS-2) | Boston |  | Massachussettes |  | Transitway | Expansition of existing system | 1 | New Starts | Final Design | 1993 | 2004 |  |  |  | Annual report on funding recommendations
311-a | South Boston Piers Phase I (MOS-2) | Boston |  | Massachussettes |  | Transitway | Expansition of existing system | 1 | New Starts | FFGA Awarded | 1994 | 2003 | 601 | 330.73 | 150.07 | Annual report on funding recommendations | 2002 | cost growth and project scheduled delays
311-a | South Boston Piers Phase I (MOS-2) | Boston |  | Massachussettes |  | Transitway | Expansition of existing system | 1 | New Starts | FFGA Awarded | 1994 | 2004 | 601 | 330.73 | 150.07 | Annual report on funding recommendations | 2004 | Revised FFGA in 1999 due to the change to address cost esclation and project scope
311-b | South Boston Piers Phase II | Boston |  | Massachussettes |  | Transitway | Expansition of existing system | 1.5 | New Starts | FFGA Awarded | 1994 | 2008 | 300 | 240 |  | Annual report on funding recommendations | 1997
311-b | South Boston Piers Phase II | Boston |  | Massachussettes |  | Transitway | Expansition of existing system | 1.5 | New Starts | FFGA Awarded | 1994 | 2008 | 258 | 206.40 |  | Annual report on funding recommendations | 1998
311-b | South Boston Piers Phase II | Boston |  | Massachussettes |  | Transitway | Expansition of existing system | 1.5 | New Starts | FFGA Awarded | 1994 | 2008 | 363.70 | 291.00 |  | Annual report on funding recommendations | 2000
| Silver Line Phase III | Boston |  | Massachussettes |  | Bus Rapid Transit | Expansition of existing system | 1.5 | New Starts | Preliminary Engineering | 2002 | 2003 | 951.9 | 571.1 |  | Annual report on funding recommendations | 2004
| Silver Line Phase III | Boston |  | Massachussettes |  | Bus Rapid Transit | Expansition of existing system | 1 | New Starts | Preliminary Engineering | 2002 |  | 756 | 378 |  | Annual report on funding recommendations | 2005
| Green Line Extension | Boston |  | Massachussettes |  | Light Rail | [6 empty] | 2,297 | 996 |  |  | 2019
| Green Line Extension | Cambridge | Medford | Massachusetts |  | Light Rail | Expansition of existing system | 4.3 | New Starts | Preliminary Engineering | 2012 | 2019 | 1334.62 | 557.07 |  | Annual report on funding recommendations | 2014
| Green Line Extension | Cambridge | Medford | Massachusetts |  | Light Rail | Expansition of existing system | 4.7 | New Starts | Engineering | 2012 onwards | 2019 | 1656.56 | 714.41 |  | Annual report on funding recommendations | 2015 | Milestone: FFGA expected in early 2015; Project capital costs increased as a result of advanced design development, primarily in areas of station construction, traction power supply and distribution. In addition, project financing costs were increased and vehicle costs have been increased to reflect current prices. The amount of New Starts funding requested for the GLX was increased
| Green Line Extension | Cambridge | Medford | Massachusetts |  | Light Rail | Expansition of existing system | 4.7 | New Starts | FFGA Awarded | 2015 | 2021 | 2297.62 | 996.12 |  | Annual report on funding recommendations | 2016
| Green Line Extension | Cambridge | Medford | Massachusetts |  | Light Rail | Expansition of existing system | 4.7 | New Starts | Preliminary Engineering | 2012 | 2021 | 2297.62 | 996.12 |  | Project Profile | 2020
| Green Line Extension | Cambridge | Medford | Massachusetts |  | Light Rail | Expansition of existing system | 4.7 | New Starts | FFGA Awarded | 2015 | 2021 | 2297.62 | 996.12 |  | Project Profile | 2020
| Lowel-Nashua Commuter Rail Extension | Lowell | Nashua | Massachusetts | New Hampshire | Commuter Rail | Expansition of existing system | 10 | New Starts | Preliminary Engineering | 2000 |  | 40.7 | 18 | 14.5 | Annual report on funding recommendations | 2005
| Lowel-Nashua Commuter Rail Extension | Lowell | Nashua | Massachusetts | New Hampshire | Commuter Rail | Expansition of existing system | 12 | New Starts | Preliminary Engineering | 2000 |  | 41 | 18 | 14.5 | Annual report on funding recommendations | 2002
411 | Burlington to Charlotte Corridor | Burlington | _ | Vermont |  |  | Improvement of existing service |  | New Starts |  |  |  | 7.68 | 5.58 | 0.7 | Annual report on funding recommendations | 1997
| Burlington-Essex Commuter Rail Porject | Burlington | Winooski, Essex, Colchester | Vermont |  | Commuter Rail | Expansition of existing system | 8 | New Starts | Preliminary Engineering | 2002 |  | 25.1 | 19.4 | 0.72 | Annual report on funding recommendations | 2004
511 | Queens Connection | New York | _ | New York |  |  | Expansition of existing system | 1/3 | New Starts | Preliminary Engineering | 1992 | 2001 | 645.00 | 306.10 |  | Annual report on funding recommendations | 1995
511 | Queens Connection | New York | _ | New York |  |  | Expansition of existing system | 1/3 | New Starts | FFGA Awarded | 1992 | 2001 | 645.00 | 306.10 | 22.68 | Annual report on funding recommendations | 1997
511 | Queens Connection | New York | _ | New York |  |  | Expansition of existing system | 1/3 | New Starts | FFGA Awarded | 1994 | 2001 | 645.00 | 306.10 | 22.68 | Annual report on funding recommendations | 1998
512 | Long Island Rail Road Access to Manhattan's East Side | New York | _ | New York |  | Commuter Rail | Expansition of existing system | 4 | New Starts | Preliminary Engineering | 1998 |  | 4,289.40 |  |  | Annual report on funding recommendations | 2000
512 | Long Island Rail Road Access to Manhattan's East Side | New York | _ | New York |  | Commuter Rail | Expansition of existing system | 4 | New Starts | Preliminary Engineering | 1998 |  | 4343 | 2172 |  | Annual report on funding recommendations | 2002
| Long Island Rail Road East Side Access | New York |  | New York |  | Commuter Rail | Expansition of existing system | 4 | New Starts | Preliminary Engineering | 1998 |  | 4.35 | 2.175 |  | Annual report on funding recommendations | 2003
| Long Island Rail Road East Side Access | New York |  | New York |  | Commuter Rail | Expansition of existing system | 3.5 | New Starts |  |  |  | 7,779.3 | 2,632.1 | 39.4 | Annual report on funding recommendations | 2007 | pending FFGA
| Long Island Rail Road East Side Access | New York |  | New York |  | Commuter Rail | Expansition of existing system | 3.5 | New Starts | FFGA Awarded | 2006 | 2013 (Dec) | 7386 | 2632.11 | 50.44 | Annual report on funding recommendations | 2014 | In 2010, FTA estimated that the project will likely cost $1.769 billion more than initially anticipated and will be delivered some 52 months later than scheduled.
| Long Island Rail Road East Side Access | New York |  | New York |  | Commuter Rail | Expansition of existing system | 3.5 | New Starts | FFGA Awarded | 2006 | 2013 (Dec) | 7386 | 2632.11 | 50.44 | Annual report on funding recommendations | 2015 | In 2012-2013, MTA experienced significant cost increases and schedule delays from the cancelled Manhattan station finish construction contract. MTA has repackaged the contract into three smaller contract packages and awarded two of the three in 2013. The third contract is forecasted to be awarded in 2015.
| Long Island Rail Road East Side Access | New York |  | New York |  | Commuter Rail | Expansition of existing system | 3.5 | New Starts | FFGA Awarded | 2002 |  | 7,386.00 | 2,632.11 | 50.44 | Annual report on funding recommendations | 2010
| Long Island Rail Road East Side Access | New York |  | New York |  | Commuter Rail | Expansition of existing system | 3.5 | New Starts | FFGA Awarded | 2006 |  | 7,386.00 | 2,632.11 | 50.44 | Annual report on funding recommendations | 2010 | Due to the redesign of a vent facility the FFGA needed to be revisited
| Long Island Rail Road East Side Access | New York |  | New York |  | Commuter Rail | Expansition of existing system | 3.5 | New Starts | Final Design | 2002 |  | 5.260.0 | 2,632.0 |  | Annual report on funding recommendations | 2005
| Long Island Rail Road East Side Access | New York |  | New York |  | Commuter Rail | Expansition of existing system | 3.5 | New Starts | Preliminary Engineering | 1998 |  | 7,386.00 | 2,632.11 | 50.44 | Annual report on funding recommendations | 2011
| Second Avenue Subway | New York |  | New York |  | Heavy Rail | Expansition of existing system | 8 | New Starts | Preliminary Engineering | 2001 |  | 16809 | 8385 |  | Annual report on funding recommendations | 2003
| Second Avenue Subway | New York |  | New York |  | Heavy Rail | Expansition of existing system | 8.5 | New Starts | Preliminary Engineering | 2001 |  | 16808.5 | 8404.3 |  | Annual report on funding recommendations | 2005
| Second Avenue Subway Phase I | New York | _ | New York | _ | Heavy Rail | Expansition of existing system | 2.3 | New Starts | FFGA Awarded | 2007 |  | 4,866.61 | 1,300.00 | 50.69 | Annual report on funding recommendations | 2010
| Second Avenue Subway Phase I | New York |  | New York |  | Heavy Rail | Expansition of existing system | 2.3 | New Starts | FFGA Awarded | 2007 | 2018 | 5574 | 1300 | 50.69 | Annual report on funding recommendations | 2014 | Subway
| Second Avenue Subway Phase I | New York |  | New York |  | Heavy Rail | Expansition of existing system | 2.3 | New Starts | FFGA Awarded | 2007 | 2014 | 4,866.61 | 1,300.00 | 50.69 | Annual report on funding recommendations | 2011 | Subway
| Second Avenue Subway Phase I | New York |  | New York |  | Heavy Rail | Expansition of existing system | 2.3 | New Starts | Final Design | 2006 | 2014 | 4,866.61 | 1,300.00 | 50.69 | Annual report on funding recommendations | 2011
| Second Avenue Subway Phase I | New York |  | New York |  | Heavy Rail | Expansition of existing system | 2.3 | New Starts | Preliminary Engineering | 2001 | 2014 | 4,947.8 | 1,300.00 | 45.3 | Annual report on funding recommendations | 2007
| Second Avenue Subway Phase II | New York |  | New York |  | Heavy Rail |  |  | New Starts | Project Development | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Second Avenue Subway Phase II | New York |  | New York |  | Heavy Rail | Expansition of existing system | 1.8 | New Starts | Project Development | 2016 | 2027 | 6,390.31 | 2,000.00 |  | Project Profile | 2019
| Canarsie Line Power Improvements | New York |  | New York |  | Light Rail | Improvement of existing service | 10.1 | Core Capacity | Project Development | 2014 |  | 300 |  |  | Annual report on funding recommendations | 2016
| Canarsie Line Power Improvements | New York |  | New York |  |  |  |  | Core Capacity | Engineering | 2017 |  | 372.9 | 100 |  | Annual report on funding recommendations | 2019
| Canarsie Line Power Improvements | New York |  | New York |  | Heavy Rail | Improvement of existing service | 6 | Core Capacity | Project Development | 2014 | 2020 | 372.91 | 100 |  | Project Profile | 2016
| Canarsie Line Power Improvements | New York |  | New York |  | Heavy Rail | Improvement of existing service | 6 | Core Capacity | Engineering | 2017 | 2020 | 372.91 | 100 |  | Project Profile | 2016
| Woodhaven Select Bus Service | New York |  | New York |  |  |  |  | New Starts | Project Development | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| Woodhaven Boulevard Select Bus Service | New York |  | New York |  | Bus Rapid Transit | Introduction of new mode | 6.1 | Small Starts | Project Development | 2015 | 2029 | 258.84 | 97.17 |  | Project Profile | 2019
| Washington/Western Bus Rapid Transit Line | Albany |  | New York |  | Bus Rapid Transit | Expansition of existing system | 8 | Small Starts | Project Development | 2014 |  | 64 |  |  | Annual report on funding recommendations | 2016
| Washington/Western Bus Rapid Transit Line | Albany |  | New York |  | Bus Rapid Transit | Expansition of existing system | 8.5 | Small Starts | Project Development | 2014 | 2022 | 81.18 | 60.89 |  | Project Profile | 2019
| River Corridor/Blue Line Bus Rapid Transit | Albany |  | New York |  | Bus Rapid Transit |  |  | Small Starts | Project Development | 2015 |  | 34.7 |  |  | Annual report on funding recommendations | 2017
| Hudson Tunnel | Secaucus | New York | New York | New Jeresy | Commuter Rail | Introduction of new mode | 6.5 | New Starts | Project Development | 2016 | 2029 | 5,338.68 | 12,127.22 | 153.34 | Project Profile | 2019
611 | North central corridor LRT | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 11.4 | New Starts | Preliminary Engineering | 1994 |  | 354.40 | 177.20 |  | Annual report on funding recommendations | 1997
611 | North central corridor LRT | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 11.4 | New Starts | Final Design | 1997 |  | 347.10 | 173.60 |  | Annual report on funding recommendations | 1998
611 | North central corridor LRT | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 12.5 | New Starts | FFGA Awarded | 1999 | 2002 | 517.20 | 333.00 |  | Annual report on funding recommendations | 2000
611 | North central corridor LRT | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 12.5 | New Starts | Project opening | 1999 | 2002 | 517.20 | 333.00 |  | Annual report on funding recommendations | 2004 | some part of the project were opened
612-b | Railtran Phase 2 | Dallas | Fort Worth | Texas | _ | Commuter Rail | Expansition of existing system | 25 | New Starts | Final Design | 1995 | 1999 | 129 | 58.80 | 18.80 | Annual report on funding recommendations | 1997
612-b | Railtran Phase 2 | Dallas | Fort Worth | Texas | _ | Commuter Rail | Expansition of existing system | 25 | New Starts | Final Design | 1996 | 1999 | 129.01 | 58.85 | 18.80 | Annual report on funding recommendations | 1998
612-b | Railtran Phase 2 | Dallas | Fort Worth | Texas | _ | Commuter Rail | Expansition of existing system | 25 | New Starts |  |  | 2000 | 141.40 | 64.30 | 41.40 | Annual report on funding recommendations | 2000 | total costs have two different numbers
612-b | Railtran Phase 2 | Dallas | Fort Worth | Texas | _ | Commuter Rail | Expansition of existing system | 25 | New Starts | FFga Awarded |  | 2000 | 160.60 | 62.40 | 57.60 | Annual report on funding recommendations | 2001 | the project is in the FFGA projects but no date is mentioned
| Trinity Railtran Phase 2 | Dallas | Fort Worth | Texas | _ | Commuter Rail | Expansition of existing system | 25 | New Starts | Final Design |  |  | 184.1 | 46.4 | 73.8 | Annual report on funding recommendations | 2002 | a part of the project was opened in 2000
613 | South oak cliff corridor | Dallas | _ | Texas | _ | Light Rail | Introduction of new mode | 20 | New Starts | FFGA Awarded | 1992 |  | 280.00 | 160.00 |  | Annual report on funding recommendations | 1996
| Northwest / Southeast LRT MOS | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 22 | New Starts | Preliminary Engineering | 2001 |  | 1237.5 | 500 | 31 | Annual report on funding recommendations | 2003
| Northwest / Southeast LRT MOS | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 20.9 | New Starts | Preliminary Engineering | 2001 |  | 1,536.8 | 700 | 5.4 | Annual report on funding recommendations | 2005
| Northwest / Southeast LRT MOS | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 21 | New Starts | Preliminary Engineering | 2001 | 2010 | 1,406.22 | 700.00 |  | Annual report on funding recommendations | 2013 | project opened in 2010
| Northwest / Southeast LRT MOS | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 21 | New Starts | Preliminary Engineering | 2001 | 2010 | 1,151.4 |  |  | before and After Study | 2014
| Northwest / Southeast LRT MOS | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 21 | New Starts | Final Design | 2005 |  | 1,406.2 | 700 |  | Annual report on funding recommendations | 2007
| Northwest / Southeast LRT MOS | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 21 | New Starts | Final Design | 2005 |  | 1,490.1 |  |  | before and After Study | 2014
| Northwest / Southeast LRT MOS | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 21 | New Starts | FFGA Awarded | 2006 |  | 1,406.22 | 700.00 |  | Annual report on funding recommendations | 2010
| Northwest / Southeast LRT MOS | Dallas | _ | Texas | _ | Light Rail | Expansition of existing system | 21 | New Starts | Project opening | 2010 |  |  |  |  | before and After Study | 2014
| Red and Blue Line Platform Extensions | Dallas |  | Texas |  | Light Rail | Improvement of existing service | 28 of 38 stations | Core Capacity | Project Development | 2014 | 2017 (Dec) | 188.4 |  |  | Annual report on funding recommendations | 2016
| Red and Blue Line Platform Extensions | Dallas |  | Texas |  |  |  |  | Core Capacity | Engineering | 2017 |  | 149.2 | 74.4 |  | Annual report on funding recommendations | 2019
| Northwest / Southeast LRT MOS | Dallas |  | Texas |  | Light Rail | Expansition of existing system | 21 | New Starts | Project opening | 2010 (Dec) | 2011 (Jun) | 1406.22 | 700 |  | Annual report on funding recommendations | 2014 | The project opened for revenue service six months early
| DART Second LRT Alignment, Phase I | Dallas |  | Texas |  | Bus Rapid Transit |  |  | Core Capacity | Project Development | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
621 | Regional Bus plan | Houston | _ | Texas | _ | Bus Rapid Transit | Improvement of existing service |  | New Starts | FFGA Awarded | 1994 |  | 625 | 500 |  | Annual report on funding recommendations | 1996
621 | Regional Bus plan | Houston | _ | Texas | _ | Bus Rapid Transit | Improvement of existing service |  | New Starts | FFGA Awarded | 1994 |  | 625 | 500 |  | Annual report on funding recommendations | 1997 | Houston Metro's Regional Bus Plan (RBP) is a package of improvements to the bus system.
621 | Regional Bus plan | Houston | _ | Texas | _ | Bus Rapid Transit | Improvement of existing service |  | New Starts | FFGA Awarded | 1994 | 2002 | 625 | 500 |  | Annual report on funding recommendations | 1999
621 | Regional Bus plan | Houston | _ | Texas | _ | Bus Rapid Transit | Improvement of existing service |  | New Starts | FFGA Awarded | 1994 | 2004 | 625 | 500 |  | Annual report on funding recommendations | 2000
| North Corridor LRT(MOS) | Houston |  | Texas |  | Light Rail | Expansition of existing system | 5.4 | New Starts | Preliminary Engineering | 2005 | 2030 | 359.7 | 177.2 |  | Annual report on funding recommendations | 2007
| North Corridor LRT | Houston |  | Texas |  | Light Rail | Expansition of existing system | 5.28 | New Starts | Preliminary Engineering | 2008 | 2015 | 756.00 | 450.00 |  | Annual report on funding recommendations | 2013
| North Corridor LRT | Houston |  | Texas |  | Light Rail | Expansition of existing system | 5.28 | New Starts | Final Design | 2009 | 2015 | 756.00 | 450.00 |  | Annual report on funding recommendations | 2013
| North Corridor LRT | Houston |  | Texas |  | Light Rail | Expansition of existing system | 5.28 | New Starts | FFGA Awarded | 2011 | 2015 | 756 | 450 |  | Annual report on funding recommendations | 2014
| Southeast Corridor LRT | Houston |  | Texas |  | Light Rail | Introduction of new mode | 6.56 | New Starts | FFGA Awarded | 2011 | 2015 | 822.91 | 450 |  | Annual report on funding recommendations | 2014
| Southeast Corridor LRT | Houston |  | Texas |  | Light Rail | Introduction of new mode | 6.5 | New Starts | Final Design | 2009 |  | 822.91 | 450 |  | Annual report on funding recommendations | 2011
| Southeast Corridor LRT | Houston |  | Texas |  | Light Rail | Introduction of new mode | 6.5 | New Starts | Preliminary Engineering | 2006 |  | 822.91 | 450 |  | Annual report on funding recommendations | 2011
| University Corridor LRT | Houston |  | Texas |  | Light Rail | Expansition of existing system | 11.3 | New Starts | Preliminary Engineering | 2009 | 2020 | 1,563.07 | 781.53 |  | Annual report on funding recommendations | 2013
| University Corridor LRT | Houston |  | Texas |  | Light Rail | Expansition of existing system | 11.3 | New Starts | Engineering | 2010 | 2020 | 1563.07 | 781.53 |  | Annual report on funding recommendations | 2014 | In November 2012, local voters passed a referendum that requires METRO to continue to dedicate 25 percent of its existing one percent sales tax to local jurisdictions to support pedestrian and street improvements. The referendum limits METRO’s financial capacity to build additional rail expansion projects. As a result, METRO is evaluating its financial capacity to implement the project.
| University Corridor LRT | Houston |  | Texas |  | Light Rail | Expansition of existing system | 11.3 | New Starts | Engineering | 2010 | 2020 | 1563.07 | 781.53 |  | Annual report on funding recommendations | 2015 | The project’s capital cost estimate and corresponding requested New Starts amount increased from the last evaluation to reflect additional contingency for LRV procurement and a revised planned revenue service date.
| University Corridor LRT | Houston |  | Texas |  | Light Rail | Expansition of existing system | 11.3 | New Starts | Engineering | 2010 | 2020 | 1563.07 | 781.53 |  | Annual report on funding recommendations | 2016 | The project’s capital cost estimate and corresponding requested New Starts amount increased from the last evaluation to reflect additional contingency for LRV procurement and a revised planned revenue service date.
| Downtown to Astrodome Light Rail | Houston |  | Texas |  | Light Rail | Introduction of new mode | 7.5 | New Starts | Preliminary Engineering | 1999 |  | 300 | 0 |  | Annual report on funding recommendations | 2002
731 | Northwest/North Central Corridor | Austin | _ | Texas | _ | Light Rail | Introduction of new mode | 54 | [7 empty] | Annual report on funding recommendations | 2000
| Rapid Transit Project MOS | Austin | _ | Texas | _ | Bus Rapid Transit | Introduction of new mode | 14.6 | New Starts | Preliminary Engineering | 1997 |  | 749.2 | 374.6 |  | Annual report on funding recommendations | 2003
| Rapid Transit Project MOS | Austin | _ | Texas | _ | Bus Rapid Transit | Introduction of new mode | 14.6 | New Starts | Preliminary Engineering | 1997 |  |  | 3.96 |  | before and After Study | 2018 | The actual cost of the project was $38.9 million in year-of-expenditure dollars.
| MetroRapid Bus Rapid Transit Project | Austin | _ | Texas | _ | Bus Rapid Transit | Introduction of new mode | 37,5 | New Starts | Project Development | 2009 |  | 47.0 |  |  | before and After Study | 2018 | The actual cost of the project was $38.9 million in year-of-expenditure dollars.
| MetroRapid Bus Rapid Transit Project | Austin | _ | Texas | _ | Bus Rapid Transit | Introduction of new mode | 37,5 | New Starts | PCGA | 2012 |  | 47.6 |  |  | before and After Study | 2018
| MetroRapid Bus Rapid Transit Project | Austin | _ | Texas | _ | Bus Rapid Transit | Introduction of new mode | 37,5 | New Starts | Project opening | 2014 |  |  |  |  | before and After Study | 2018
| Light Rail Corridor | Austin | _ | Texas | _ | Light Rail | Introduction of new mode | 14.6 | New Starts |  |  |  | 739 | 369.5 |  | Annual report on funding recommendations | 2001
| Light Rail Corridor | Austin | _ | Texas | _ | Light Rail | Introduction of new mode | 14.6 | New Starts | Preliminary Engineering | 1997 |  | 739 | 369.5 |  | Annual report on funding recommendations | 2002
| Dyer Avenue Bus Rapid Transit System | El Paso |  | Texas |  | Bus Rapid Transit | Introduction of new mode | 12 | Very Small Starts | Project Development | 2011 | 2015 | 35.25 | 20.40 |  | Annual report on funding recommendations | 2013
| Dyer Avenue Bus Rapid Transit System | El Paso |  | Texas |  | Bus Rapid Transit | Introduction of new mode | 12 | Small Starts | Project Development | 2011 | 2015 | 35.9 | 20.4 | 8.28 | Annual report on funding recommendations | 2014
| Dyer Avenue Bus Rapid Transit System | El Paso |  | Texas |  | Bus Rapid Transit | Improvement of existing service | 12 | Small Starts | Project Development | 2011 | 2017 | 35.89 | 20.4 | 7.22 | Annual report on funding recommendations | 2015 | Total estimated capital costs increased slightly from $35.25 million to $35.89 million, while the Small Starts amount was unchanged. The cost increases are due to refined cost estimates for vehicles and construction materials.
| Dyer Avenue Bus Rapid Transit System | El Paso |  | Texas |  | Bus Rapid Transit | Improvement of existing service | 12 | Small Starts | Project Development | 2011 | 2017 | 34.23 | 19.35 | 6.63 | Annual report on funding recommendations | 2016
| Dyer Corridor BRT | El Paso |  | Texas |  | Bus Rapid Transit |  |  | Small Starts | CGA | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| Montana Avenue Rapid Transit System | El Paso |  | Texas |  | Bus Rapid Transit | Improvement of existing service | 16.8 | Small Starts | Project Development | 2013 | 2016 | 43.36 | 25.74 | 8.85 | Annual report on funding recommendations | 2014
| Montana Avenue Rapid Transit System | El Paso |  | Texas |  | Bus Rapid Transit | Improvement of existing service | 16.8 | Small Starts | Project Development | 2013 | 2016 | 43.36 | 25.74 | 8.85 | Annual report on funding recommendations | 2015
| Montana Avenue Rapid Transit System | El Paso |  | Texas |  | Bus Rapid Transit | Improvement of existing service | 16.8 | Small Starts | Project Development | 2013 | 2019 | 45.52 | 26.97 | 7.76 | Annual report on funding recommendations | 2016
| Sun Metro Areas Rapid Trasnit (SMART) Satrter Line | El Paso |  | Texas |  | Light Rail | Introduction of new mode | 1.9 | New Starts | Preliminary Engineering | 2003 |  | 10 | 8 |  | Annual report on funding recommendations | 2005
| TEX Rail | Fort Worth |  | Texas |  | Commuter Rail | Introduction of new mode | 37.6 | New Starts | Preliminary Engineering | 2012 | 2016 | 959.13 | 479.56 | 76.3 | Annual report on funding recommendations | 2014 | Total estimated capital costs increased from $758.0 million to $959.1 million.
| TEX Rail | Fort Worth |  | Texas |  | Commuter Rail | Introduction of new mode | 27.2 | New Starts | Preliminary Engineering | 2012 | 2017 | 809.77 | 404.88 | 62.65 | Annual report on funding recommendations | 2015 | Reduced TEX Rail length from 37.6 miles to 27.2 miles and reduces the number of stations from 14 to 10.
| TEX Rail | Fort Worth |  | Texas |  | Commuter Rail | Introduction of new mode | 27.2 | New Starts | Project Development | 2014 | 2018 | 891.9 | 445.95 | 40.95 | Annual report on funding recommendations | 2016 | The project cost estimate changed from $809.77 million to $891.90 million due to refinements in design and changes in unit costs and real estate cost assumptions.
| TEX Rail | Fort Worth |  | Texas |  | Commuter Rail |  |  | New Starts | CGA | 2016 |  | 1.034 | 499 |  | Annual report on funding recommendations | 2018
| TEX Rail | Fort Worth |  | Texas |  |  |  |  | New Starts | Engineering | 2015 |  | 996 | 498 |  | Annual report on funding recommendations | 2017
| TEX Rail | Fort Worth |  | Texas |  | Commuter Rail | Introduction of new mode | 26.8 | New Starts | Preliminary Engineering | 2012 | 2020 | 1,034.41 | 499.39 | 37.50 | Project Profile | 2020
| TEX Rail | Fort Worth |  | Texas |  | Commuter Rail | Introduction of new mode | 26.8 | New Starts | Engineering | 2015 | 2020 | 1,034.41 | 499.39 | 37.50 | Project Profile | 2020
| TEX Rail | Fort Worth |  | Texas |  | Commuter Rail | Introduction of new mode | 26.8 | New Starts | FFGA Awarded | 2016 | 2020 | 1,034.41 | 499.39 | 37.50 | Project Profile | 2020
| TEX Rail | Fort Worth |  | Texas |  | Commuter Rail | Introduction of new mode | 26.8 | New Starts | Project opening | 2019 | 2020 | 1,034.41 | 499.39 | 37.50 | Project Profile | 2020
| San Antonio Modern Streetcar Project | San Antonio |  | Texas |  | Streetcar | Introduction of new mode | 5.9 | Small Starts | Project Development | 2013 | On hold |  |  |  | Annual report on funding recommendations | 2016 | In July 2014, due to changing local support for the project, VIA elected to put the project on hold. VIA does not currently have anticipated dates for resuming activity on the project, including completion of environmental assessment activities.
| Rail Trolley Extension | Galveston |  | Texas |  |  | Expansition of existing system | 1.5 | New Starts | Final Design | 2001 |  | 9.4 | 8.3 | 0.53 | Annual report on funding recommendations | 2005 | Fixed Rail Troelly Extension
| Waco Rapid Transit Corridor | Waco |  | Texas |  | Bus Rapid Transit | Introduction of new mode | 13.3 | Small Starts | Project Development |  | 2020 |  |  |  | Project Profile | 2019
711 | SW Corridor LRT | Denver | _ | Colorado | _ | Light Rail | Expansition of existing system | 8.7 | New Starts | FFGA Awarded | 1996 | 2000 | 177.40 | 120.00 |  | Annual report on funding recommendations | 1997
711 | SW Corridor LRT | Denver | _ | Colorado | _ | Light Rail | Expansition of existing system | 8.7 | New Starts | FFGA Awarded | 1996 |  | 176.32 | 120.00 |  | Annual report on funding recommendations | 1998
711 | SW Corridor LRT | Denver | _ | Colorado | _ | Light Rail | Expansition of existing system | 8.7 | New Starts | FFGA Awarded | 1996 | 2000 | 176.32 | 120.00 | 18.88 | Annual report on funding recommendations | 1999
711 | SW Corridor LRT | Denver | _ | Colorado | _ | Light Rail | Expansition of existing system | 8.7 | New Starts | FFGA Awarded | 1996 | 2000 | 176.32 | 120.00 | 18.88 | Annual report on funding recommendations | 2000 | Not opened
711 | SW Corridor LRT | Denver | _ | Colorado | _ | Light Rail | Expansition of existing system | 8.7 | New Starts | FFGA Awarded | 1996 | 2000 | 176.32 | 120.00 | 18.88 | Annual report on funding recommendations | 2002
| SW Corridor LRT | Denver | _ | Colorado | _ | Light Rail | Expansition of existing system | 19.1 | New Starts | Final Design | 2000 | 2008 | 879.27 | 525 |  | Annual report on funding recommendations | 2007
| SW Corridor LRT | Denver | _ | Colorado | _ | Light Rail | Expansition of existing system | 19.1 | New Starts | FFGA Awarded | 2000 | 2008 | 879.27 | 525 |  | Annual report on funding recommendations | 2007
| West Corridor LRT | Denver | _ | Colorado | _ | Light Rail | Expansition of existing system | 11 | New Starts | Preliminary Engineering | 2001 |  | 624.3 | 366.3 | 2 | Annual report on funding recommendations | 2003
| West Corridor LRT | Denver | _ | Colorado | _ | Light Rail | Expansition of existing system | 12 | New Starts | Preliminary Engineering | 2001 |  | 749.7 | 412 | 2 | Annual report on funding recommendations | 2005
| Eagle Commuter Rail | Denver |  | Colorado |  | Commuter Rail | Introduction of new mode | 30.2 | New Starts | Preliminary Engineering | 2009 |  | 2,043.14 | 1,030.45 |  | Annual report on funding recommendations | 2013
| Eagle Commuter Rail | Denver |  | Colorado |  | Commuter Rail | Introduction of new mode | 30.2 | New Starts | Final Design | 2010 |  | 2,043.14 | 1,030.45 |  | Annual report on funding recommendations | 2013
| Eagle Commuter Rail | Denver |  | Colorado |  | Commuter Rail | Introduction of new mode | 30.2 | New Starts | FFGA Awarded | 2011 | 2016 (Dec) | 2043.14 | 1030.45 | 62.1 | Annual report on funding recommendations | 2014
| Eagle Commuter Rail | Denver |  | Colorado |  | Commuter Rail | Introduction of new mode | 30.2 | New Starts | FFGA Awarded | 2011 | 2016 (Dec) | 2043.14 | 1030.45 | 62.1 | Annual report on funding recommendations | 2015 | Section 20008 of the Moving Ahead for Progress in the 21st Century Act authorized FTA to award Federal major capital investment funds for final design and construction of the Denver Eagle Commuter Rail project. Through FY 2014, Congress has appropriated a total of $517.19 million for the project.
| Eagle Commuter Rail | Denver |  | Colorado |  | Commuter Rail | Introduction of new mode | 30.2 | New Starts | FFGA Awarded | 2011 | 2016 (Dec) | 2043.14 | 1030.45 | 62.1 | Annual report on funding recommendations | 2016 | Section 20008 of the Moving Ahead for Progress in the 21st Century Act authorized FTA to award Federal major capital investment funds for final design and construction of the Denver Eagle Commuter Rail project. Through FY 2014, Congress has appropriated a total of $517.19 million for the project.
| Southeast Corridor LRT | Denver |  | Colorado |  | Light Rail | Expansition of existing system | 19.1 | New Starts | FFGA Awarded | 2000 | 2019 | 879.27 | 525.00 |  | Annual report on funding recommendations | 2010
| Southeast Corridor LRT | Denver |  | Colorado |  | Light Rail | Expansition of existing system | 19.12 | New Starts | FFGA Awarded | 2000 | 2006 | 879.27 | 525.00 |  | Annual report on funding recommendations | 2003
| Southeast Corridor LRT | Denver |  | Colorado |  | Light Rail | Expansition of existing system | 19 | New Starts | Preliminary Engineering | 1998 | 2007 | 882.50 | 525.00 |  | Annual report on funding recommendations | 2001
| Southeast Extension | Denver |  | Colorado |  | Light Rail | Expansition of existing system | 2.3 | New Starts | Project Development | 2013 | 2019 | 210.74 | 92 | 7.5 mn | Annual report on funding recommendations | 2015
| Southeast Extension | Denver |  | Colorado |  | Light Rail | Expansition of existing system | 2.3 | New Starts | Project Development | 2013 | 2019 | 210.74 | 92 | 7.5 mn | Annual report on funding recommendations | 2015
| Southeast Extension | Denver |  | Colorado |  | Light Rail | Expansition of existing system | 2.3 | New Starts | Project Development | 2013 | 2019 | 224.29 | 92 | 7.5 mn | Annual report on funding recommendations | 2016
| Southeast Rail Extension | Denver |  | Colorado |  |  | Expansition of existing system |  | New Starts | CGA | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Southeast Rail Extension | Denver |  | Colorado |  |  | Expansition of existing system |  | New Starts | Engineering | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| Southeast Corridor LRT | Denver |  | Colorado |  | Light Rail | Expansition of existing system | 19.2 | New Starts | Preliminary Engineering | 1998 |  |  |  |  | Annual report on funding recommendations | 2005
| Southeast Corridor LRT | Denver |  | Colorado |  | Light Rail | Expansition of existing system | 19.2 | New Starts | Final Design | 2000 | 2008 |  |  |  | Annual report on funding recommendations | 2005
| Southeast Corridor LRT | Denver |  | Colorado |  | Light Rail | Expansition of existing system | 19.2 | New Starts | FFGA Awarded | 2000 | 2008 | 879.27 | 525.00 |  | Annual report on funding recommendations | 2005
| West Corridor LRT | Denver |  | Colorado |  | Light Rail | Expansition of existing system | 12.1 | New Starts | FFGA Awarded | 2009 |  | 709.83 | 308.68 | 9.50 | Annual report on funding recommendations | 2010
| West Corridor LRT | Denver |  | Colorado |  | Light Rail | Expansition of existing system | 12.1 | New Starts | Final Design | 2005 |  | 593 | 290.6 | 2 | Annual report on funding recommendations | 2007
| Mason Transportation Corridor | Fort Collins |  | Colorado |  | Bus Rapid Transit | Expansition of existing system | 5.3 | New Starts | Preliminary Engineering |  |  | 66 | 52.3 | 0.5 | Annual report on funding recommendations | 2003
| Mason Transportation Corridor | Fort Collins |  | Colorado |  | Bus Rapid Transit | Expansition of existing system | 5.3 | New Starts | Preliminary Engineering | 2001 |  | 66 | 33 | 0.5 | Annual report on funding recommendations | 2005
|  | Los Angeles | _ | California |  | Bus Rapid Transit | Introduction of new mode | 14.4 | New Starts | Preliminary Engineering | 2000 |  | 313.7 | 0 |  | Annual report on funding recommendations | 2003
| Mid-city/ Exposition | Los Angeles | _ | California | _ | Light Rail | Introduction of new mode | 9.6 | New Starts | Preliminary Engineering | 2001 |  | 505.5 | 252.7 |  | Annual report on funding recommendations | 2005
| Mid City/Exposition LRT | Los Angeles | _ | California |  | Light Rail | Expansition of existing system | 9.6 | New Starts | Preliminary Engineering | 2001 |  | 343 | 160.3 | 74 | Annual report on funding recommendations | 2003
| East Cetral corridor | Los Angeles | _ | California | _ |  | Expansition of existing system | 6.5 | New Starts | FFGA Awarded | 1993 |  | 1640.00 | 650.00 |  | Annual report on funding recommendations | 1995
| Eastside Corridor LRT | Los Angeles | _ | California |  | Light Rail | Introduction of new mode | 5.9 | New Starts | Preliminary Engineering | 2000 |  | 795.5 | 402.3 | 116 | Annual report on funding recommendations | 2002 | the document has a good explanation of this LRT and the Heavy rail project
811-b | MOS-2 | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 6.7 | New Starts | FFGA Awarded | 1990 | 1996 |  |  |  | Annual report on funding recommendations | 1998
811-b | MOS-2 | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 6.7 | New Starts | FFGA Awarded | 1990 | 1998 |  |  |  | Annual report on funding recommendations | 1999
811-c1 | MOS-3- EastSide Corridor | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 3.7 | New Starts | Preliminary Engineering | 1993 |  | 980 |  |  | Annual report on funding recommendations | 1997 | PE begins / Metro rail
811-c1 | EastSide Corridor | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 3.7 | New Starts | Preliminary Engineering | 1993 |  | 1271 | 635.50 | 90.00 | Annual report on funding recommendations | 1997
811-c1 | MOS-3- EastSide Corridor | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 5.9 | New Starts | FFGA Awarded | 1993 |  |  |  |  | Annual report on funding recommendations | 2004
811-c1 | MOS-3- EastSide Corridor | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 5.9 | New Starts | Preliminary Engineering | 2000 |  | 817.9 | 491 | 41.7 | Annual report on funding recommendations | 2003
811-c1 | MOS-3- EastSide Corridor | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 5.9 | New Starts | Final Design | 2002 |  | 880 | 490.7 | 43.13 | Annual report on funding recommendations | 2004
811-c2 | MOS-3-North Hollywood Extension | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 6.3 | New Starts | FFGA Awarded | 1997 |  | 1310.82 | 681.04 |  | Annual report on funding recommendations | 2005
811-c2 | MOS-3-North Hollywood Extension | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 6.3 | New Starts | Project opening | 2000 |  | 1310.82 | 681.04 |  | Annual report on funding recommendations | 2005
811-c2 | MOS-3-North Hollywood Extension | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 6.3 | New Starts | Project opening | 2000 |  | 1310.82 | 681.04 | 245.6 | Annual report on funding recommendations | 2002
811-c3 | MOS-3- The Mid-City Extension | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 2.3 | New Starts | FFGA Awarded | 1993 |  | 491 |  |  | Annual report on funding recommendations | 1995
811-c3 | MOS-3- The Mid-City Extension | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system | 2.3 | New Starts |  |  |  | 683 |  |  | Annual report on funding recommendations | 1999
811-c | MOS-3 | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system |  | New Starts | FFGA Awarded | 1993 |  | 2460.00 | 1230.00 | 377.15 | Annual report on funding recommendations | 1995
811-c | MOS-3 | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system |  | New Starts | FFGA Awarded | 1993 |  | 2781.09 | 1416.49 | 377.15 | Annual report on funding recommendations | 1997
811-c | MOS-3 | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system |  | New Starts | FFGA Awarded | 1993 |  | 2781.09 | 1416.49 | 240.5 | Annual report on funding recommendations | 1998
811-c | MOS-3 | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system |  | New Starts | FFGA Awarded | 1997 |  | 3,135.90 | 681.04 | 1254.45 | Annual report on funding recommendations | 2000 | A restated FFGA for the North Hollywood extension (Phase I-A) of MOS-3 was signed on June 9, 1997.
811-c | MOS-3 | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system |  | New Starts | FFGA Awarded | 1997 |  | 1310.82 | 681.04 |  | Annual report on funding recommendations | 2001 | A restated FFGA for the North Hollywood extension (Phase I-A) of MOS-3 was signed on June 9, 1997.
811-c | MOS-3 | Los Angeles | _ | California | _ | Heavy Rail | Expansition of existing system |  | New Starts | FFGA Awarded | 1997 |  | 1310.82 | 681.04 |  | Annual report on funding recommendations | 2003 | A restated FFGA for the North Hollywood extension (Phase I-A) of MOS-3 was signed on June 9, 1997.
851 | LOSSAN Rail Corridor Improvement Project | Los Angeles | Commerce, Fullerton and Solana Beach | California | _ | Commuter Rail | Improvement of existing service |  | New Starts |  |  |  | 29.68 | 18.40 |  | Annual report on funding recommendations | 1997
851 | LOSSAN Rail Corridor Improvement Project | Los Angeles | Commerce, Fullerton and Solana Beach | California | _ | Commuter Rail | Improvement of existing service |  | New Starts |  |  |  | 31.18 | 19.90 |  | Annual report on funding recommendations | 1998
851 | LOSSAN Rail Corridor Improvement Project | Los Angeles | Commerce, Fullerton and Solana Beach | California | _ | Commuter Rail | Improvement of existing service | 126 | New Starts |  |  |  | 60.6 | 44.2 |  | Annual report on funding recommendations | 2000
851 | LOSSAN Rail Corridor Improvement Project | Los Angeles | Commerce, Fullerton and Solana Beach | California | _ | Commuter Rail | Improvement of existing service | 129 | New Starts | Preliminary Engineering |  |  | 35.7 | 24.1 |  | Annual report on funding recommendations | 2001
851 | LOSSAN Rail Corridor Improvement Project | Los Angeles | Commerce, Fullerton and Solana Beach | California | _ | Commuter Rail | Improvement of existing service | 129 | New Starts | Final Design |  |  | 35.7 | 24.1 |  | Annual report on funding recommendations | 2003
| Metro Gold Line Eastside Extension | Los Angeles | _ | California | _ | Light Rail | Expansition of existing system | 5.9 | New Starts | FFGA Awarded | 2004 | 2009 | 898.81 | 490.70 | 212.98 | Annual report on funding recommendations | 2010
| Metro Gold Line Eastside Extension | Los Angeles | _ | California | _ | Light Rail | Expansition of existing system | 6 | New Starts | Preliminary Engineering | 2000 |  | 759.5 |  |  | Before and After Study | 2013
| Metro Gold Line Eastside Extension | Los Angeles | _ | California | _ | Light Rail | Expansition of existing system | 6 | New Starts | Final Design | 2002 |  | 817.9 |  |  | Before and After Study | 2013
| Metro Gold Line Eastside Extension | Los Angeles | _ | California | _ | Light Rail | Expansition of existing system | 6 | New Starts | FFGA Awarded | 2004 |  | 898.8 |  |  | Before and After Study | 2013
| Metro Gold Line Eastside Extension | Los Angeles | _ | California | _ | Light Rail | Expansition of existing system | 6 | New Starts | Project Opening | 2009 |  |  |  |  | Before and After Study | 2013
I | Regional Connector | Los Angeles |  | California |  | Light Rail | Introduction of new mode | 1.9 | New Starts | Preliminary Engineering | 2011 | 2021 | 1,402.93 | 669.9 |  | Project Profile | 2018
I | Regional Connector | Los Angeles |  | California |  | Light Rail | Introduction of new mode | 1.9 | New Starts | FFGA Awarded | 2014 | 2021 | 1,402.93 | 669.9 | 64 | Project Profile | 2018
| Westside Subway Section 1 | Los Angeles |  | California |  | Heavy Rail | [6 empty] | 2,821 | 1,250
| Westside Subway Section 2 | Los Angeles |  | California |  | Heavy Rail | [6 empty] | 2,499 | 1,187
| Regional Connector Transit Corridor | Los Angeles |  | California |  | Light Rail | Expansition of existing system | 1.9 | New Starts | Preliminary Engineering | 2011 | 2019 | 1,342.54 | 671.27 |  | Annual report on funding recommendations | 2013
| Regional Connector Transit Corridor | Los Angeles |  | California |  | Light Rail | Expansition of existing system | 1.9 | New Starts | Engineering | 2012 | 2019 | 1366.29 | 669.9 | Congestion Mitigation and Air Quality Funds: 63.95 mn | Annual report on funding recommendations | 2014
| Regional Connector Transit Corridor | Los Angeles |  | California |  | Light Rail | Expansition of existing system | 1.9 | New Starts | FFGA Awarded | 2014 | 2021 | 1402.93 | 669.9 | Congestion Mitigation and Air Quality Funds: 64 million | Annual report on funding recommendations | 2015
| Regional Connector Transit Corridor | Los Angeles |  | California |  | Light Rail | Expansition of existing system | 1.9 | New Starts | FFGA Awarded | 2014 | 2021 | 1402.93 | 669.9 | Congestion Mitigation and Air Quality Funds: 64 mn | Annual report on funding recommendations | 2016
| Westside Subway Extension Section 1 | Los Angeles |  | California |  | Heavy Rail | Expansition of existing system | 3.9 | New Starts | Preliminary Engineering | 2011 |  | 5,662.35 | 2,399.52 |  | Annual report on funding recommendations | 2013
| Westside Subway Extension Section 1 | Los Angeles |  | California |  | Heavy Rail | Expansition of existing system | 3.9 | New Starts | Engineering | 2012 | 2023 | 2839.71 | 1250 | 22.55 mn | Annual report on funding recommendations | 2014 | Capital cost estimate decreased from $ 5,662.35 million to $2,839.72 million due to financial constraints and LACMTA’s decision to construct the project in three sections.
| Westside Purple Line Extension Section 1 | Los Angeles |  | California |  | Heavy Rail | Expansition of existing system | 3.9 | New Starts | Engineering | 2012 | 2024 | 2821.96 | 1250 | $18.46 mn | Annual report on funding recommendations | 2015
| Westside Purple Line Extension Section 1 | Los Angeles |  | California |  | Heavy Rail | Expansition of existing system | 3.92 | New Starts | FFGA Awarded | 2014 | 2024 | 2821.96 | 1250 | $12.17 mn | Annual report on funding recommendations | 2016
| Westside Purple Line Extension Section 1 | Los Angeles | Beverly Hills | California |  | Heavy Rail | Expansition of existing system | 3.92 | New Starts | FFGA Awarded | 2014 | 2024 | 2821.96 | 1250 | 12.17 | project Profile | 2020
| Westside Purple Line Extension Section 1 | Los Angeles | Beverly Hills | California |  | Heavy Rail | Expansition of existing system | 3.92 | New Starts | Preliminary Engineering | 2011 | 2024 | 2821.96 | 1250 | 12.17 | project Profile | 2020
| Westside Purple Line Extension Section 2 | Los Angeles |  | California |  | Heavy Rail | Expansition of existing system | 2.6 | New Starts | Engineering | 2014 | 2025 | 2374.44 | 1187 | 169 | Annual report on funding recommendations | 2016
| Westside Purple Line Extension Section 2 | Los Angeles |  | California |  |  |  |  | New Starts | CGA | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Westside Purple Line Extension Section 2 | Los Angeles |  | California |  |  |  |  | New Starts | FFGA Awarded | 2016 | 2026 | $2,499.24 | 1,187.00 | 169.00 | Project Profile | 2020
| Westside Purple Line Extension Section 2 | Los Angeles | Beverly Hills | California |  | Heavy Rail | Expansition of existing system | 2.59 | New Starts | Engineering | 2014 | 2026 | $2,499.24 | 1,187.00 | 169.00 | Project Profile | 2020
| Westside Purple Line Extension Section 3 | Los Angeles | Beverly Hills | California |  | Heavy Rail | Expansition of existing system | 2.6 | New Starts | Engineering | 2018 | 2028 | 3,599.27 | 1,300.00 | 138 | Project Profile | 2019
| Downtown Los Angeles Streetcar | Los Angeles |  | California |  | Streetcar | Introduction of new mode | 3.8 | Small Starts | Project Development | 2013 |  |  | 74.99 |  | Annual report on funding recommendations | 2016
| Downtown Los Angeles Streetcar | Los Angeles |  | California |  | Streetcar | Introduction of new mode | 3.4 | Small Starts | Project Development | 2022 |  | 296.38 | 100.00 |  | Project Profile | 2018
|  | Los Angeles |  | California |  | Bus Rapid Transit | Introduction of new mode | 14.2 | New Starts | Preliminary Engineering | 2000 |  | 300.3 | 0 |  | Annual report on funding recommendations | 2002
821 | BART Airport Extension | San Francisco Area | _ | California | _ | Heavy Rail | Expansition of existing system | 7.5 | New Starts |  |  |  | 1110.00 | 750.00 | 200 | Annual report on funding recommendations | 1997
821 | BART Airport Extension | San Francisco Area | _ | California | _ | Heavy Rail | Expansition of existing system | 8.2 | New Starts | FFGA Awarded | 1997 |  | 1,167.00 | 750.00 | 200 | Annual report on funding recommendations | 1999
821 | BART Airport Extension | San Francisco Area | _ | California | _ | Heavy Rail | Expansition of existing system | 8.2 | New Starts | FFGA Awarded | 1997 | 2001 | 1,233.00 | 750.00 | 113.00 | Annual report on funding recommendations | 2000
821 | BART Airport Extension | San Francisco Area | _ | California | _ | Heavy Rail | Expansition of existing system | 8.2 | New Starts | FFGA Awarded | 2000 |  | 1,552.23 | 750.00 |  | Annual report on funding recommendations | 2007 | Amended FFGA
| BART Airport Extension | San Francisco Area | _ | California | _ | Heavy Rail | Expansition of existing system | 8.7 | New Starts | FFGA Awarded | 1997 | 2002 | 1510.2 | 750.00 |  | Annual report on funding recommendations | 2003
821 | BART Airport Extension | San Francisco Area | _ | California | _ | Heavy Rail | Expansition of existing system | 8.2 | New Starts | Final Design | 1996 |  |  |  |  | Annual report on funding recommendations | 2007
821 | BART Airport Extension | San Francisco Area | _ | California | _ | Heavy Rail | Expansition of existing system | 8.2 | New Starts | Project Opening | 2003 |  | 1,552.23 | 750.00 |  | Annual report on funding recommendations | 2005
822 | San Francisco (Bayshore) | San Francisco Area | _ | California | _ | Light Rail | Introduction of new mode | 5-7 | New Starts | Preliminary Engineering | 1996 |  |  |  |  | Annual report on funding recommendations | 1998
822 | Central Subway LRT | San Francisco Area | _ | California | _ | Light Rail | Expansition of existing system | 1.5 | New Starts | Preliminary Engineering | 2002 |  | 1,412.5 | 762.2 | 92.2 | Annual report on funding recommendations | 2007
822 | Central Subway LRT | San Francisco Area | _ | California | _ | Light Rail | Expansition of existing system | 1.7 | New Starts | Final Design | 2009 |  | 1,578.30 | 942.19 |  | Annual report on funding recommendations | 2011
822 | Central Subway LRT | San Francisco Area | _ | California | _ | Light Rail | Expansition of existing system | 1.7 | New Starts | Preliminary Engineering | 2002 |  | 1,347.7 | 531.7 | 51.1 | Annual report on funding recommendations | 2005 |  | project had an initial PE dating 1996
822 | Central Subway LRT | San Francisco Area | _ | California | _ | Light Rail | Expansition of existing system | 1.7 | New Starts | Preliminary Engineering | 2002 |  | 763.8 | 531.6 |  | Annual report on funding recommendations | 2004 |  | project had an initial PE dating 1996
| Third Street Light Rail Phase 1 | San Francisco |  | California |  | Light Rail | Expansition of existing system | 5.4 | New Starts | Preliminary Engineering | 1996 |  |  |  |  | Annual report on funding recommendations | 2003
| Third Street Light Rail Phase 1 | San Francisco |  | California |  | Light Rail | Expansition of existing system | 5.4 | New Starts | Final Design | 2000 |  | 557.9 | 46.1 | 46.5 | Annual report on funding recommendations | 2003
| Third Street Light Rail Phase 1 | San Francisco |  | California |  | Light Rail | Expansition of existing system | 5.4 | New Starts | Final Design | 2000 |  | 530.8 | 46.1 | 5 | Annual report on funding recommendations | 2002
| Third Street Light Rail Phase 2 – Central Subway | San Francisco |  | California |  | Light Rail | Expansition of existing system | 1.7 | New Starts | Preliminary Engineering | 2002 |  | 1.578 | 942.20 |  | Annual report on funding recommendations | 2013
| Third Street Light Rail Phase 2 – Central Subway | San Francisco |  | California |  | Light Rail | Expansition of existing system | 1.7 | New Starts | Final Design | 2010 |  | 1.578 | 942.20 |  | Annual report on funding recommendations | 2013
| Third Street Light Rail Phase 2 – Central Subway | San Francisco |  | California |  | Light Rail | Expansition of existing system | 1.7 | New Starts | FFGA Awarded | 2012 | 2018 (Dec) | 1578.3 | 942.2 | FHWA Flexible Funds (CMAQ) : 41.02 mn | Annual report on funding recommendations | 2015
| Third Street Light Rail Phase 2 – Central Subway | San Francisco |  | California |  | Light Rail | Expansition of existing system | 1.7 | New Starts | FFGA Awarded | 2012 | 2018 (Dec) | 1578.3 | 942.2 | FHWA Flexible Funds (CMAQ) : 41.02 mn | Annual report on funding recommendations | 2016
| Van Ness Avenue BRT | San Francisco |  | California |  | Bus Rapid Transit | Introduction of new mode | 2 | Small Starts | Project Development | 2007 | 2018 | 125.63 | 74.99 | FHWA Flexible Funds (Surface Transportation Program and Congestion Mitigation and Air Quality Funds): 13.04 mn | Annual report on funding recommendations | 2014
| Van Ness Avenue BRT | San Francisco |  | California |  | Bus Rapid Transit | Introduction of new mode | 2 | Small Starts | Project Development | 2007 | 2018 | 125.63 | 74.99 | FHWA Flexible Funds (Surface Transportation Program and Congestion Mitigation and Air Quality Funds): 13.04 mn | Annual report on funding recommendations | 2015 | Final EIS in July 2013. FTA issued a Record of Decision in December 2013
| Van Ness Avenue BRT | San Francisco |  | California |  | Bus Rapid Transit | Introduction of new mode | 2 | Small Starts | Project Development | 2007 | 2018 | 162.07 | 74.99 |  | Annual report on funding recommendations | 2016
| Van Ness Bus Rapid Transit Project | San Francisco |  | California |  | Bus Rapid Transit |  |  | Small Starts | CGA | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Transbay Corridor | San Francisco |  | California |  |  |  |  | Core Capacity | Project Development | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| Transbay Corridor | San Francisco |  | California |  | Heavy Rail | Introduction of new mode | 112 | Core Capacity | Project Development | 2015 | 2026 | 2,705.72 | 1,169.00 |  | Project Profile | 2019
| Transbay Corridor | San Francisco |  | California |  | Heavy Rail | Introduction of new mode | 112 | Core Capacity | Engineering | 2019 | 2026 | 2,705.72 | 1,169.00 |  | Project Profile | 2019
831 | South corridor (IOS-1) | Sacramento | _ | California | _ | Light Rail | Introduction of new mode | 6.3 | New Starts |  |  |  | 220 | 104 |  | Annual report on funding recommendations | 1997
831 | South corridor (IOS-1) | Sacramento | _ | California | _ | Light Rail | Introduction of new mode | 6.3 | New Starts |  |  | 2003 | 220 | 113.20 |  | Annual report on funding recommendations | 1998
831 | South corridor (IOS-1) | Sacramento | _ | California | _ | Light Rail | Introduction of new mode | 6.3 | New Starts | FFGA Awarded | 1997 | 2003 | 222 | 111.20 |  | Annual report on funding recommendations | 1999
831 | South corridor (IOS-1) | Sacramento | _ | California | _ | Light Rail | Introduction of new mode | 6.3 | New Starts | Final Design | 1997 | 2003 | 222 | 111.20 |  | Annual report on funding recommendations | 1999
831 | South corridor (IOS-1) | Sacramento | _ | California | _ | Light Rail | Introduction of new mode | 6.3 | New Starts | FFGA Awarded | 1997 | 2003 | 222 | 111.20 |  | Annual report on funding recommendations | 2002
| South Corridor Phase Light Rail Transit Extension | Sacramento |  | California |  | Light Rail | Expansition of existing system | 4.2 | New Starts | Preliminary Engineering | 2005 |  | 197.1 | 98.6 | 11.4 | Annual report on funding recommendations | 2007
| South Sacramento Corridor Phase 2 Light Rail Transit | Sacramento |  | California |  | Light Rail | Expansition of existing system | 4.3 | New Starts | FFGA Awarded | 2012 | 2015 | 270 | 135 | 7.1 | Annual report on funding recommendations | 2014
| Downtown Riverfront Streetcar | Sacramento |  | California |  | Streetcar | Introduction of new mode | 3.3 | Small Starts | Project Development | 2014 | 2018 | 165.93 | 74.99 | 5 | Annual report on funding recommendations | 2016
| Downtown Riverfront Streetcar | Sacramento |  | California |  | Streetcar | Introduction of new mode | 4.4 | Small Starts | Project Development | 2014 | 2022 | 209.78 | 99.99 | 5 | Project Profile | 2018
841 | Tasman LRT (West Extension) | San Jose | _ | California | _ | Light Rail | Expansition of existing system | 12.4 | New Starts | Preliminary Engineering | 1992 |  | 480.00 | 240.00 |  | Annual report on funding recommendations | 1995
841 | Tasman LRT (West Extension) | San Jose | _ | California | _ | Light Rail | Expansition of existing system | 7.6 | New Starts | Preliminary Engineering | 1992 |  | 325.40 | 182.50 | 15.00 | Annual report on funding recommendations | 1997 | PE was completed in 1992. West Extension is a part of a 12.4 mile project
841 | Tasman LRT (West Extension) | San Jose | _ | California | _ | Light Rail | Expansition of existing system | 7.6 | New Starts | FFGA Awarded | 1996 |  | 325 | 182.75 | 57.3 | Annual report on funding recommendations | 1998
841 | Tasman LRT (West Extension) | San Jose | _ | California | _ | Light Rail | Expansition of existing system | 7.6 | New Starts | FFGA Awarded | 1996 |  | 342.5 | 182.75 | 79.45 | Annual report on funding recommendations | 1999
841 | Tasman LRT (West Extension) | San Jose | _ | California | _ | Light Rail | Expansition of existing system | 7.6 | New Starts | FFGA Awarded | 1996 |  | 325 | 182.75 | 61.96 | Annual report on funding recommendations | 2000
| El Camino Real Corridor BRT Project | San Jose | Palo Alto | California |  | Bus Rapid Transit | Introduction of new mode | 17.4 | Small Starts | Project Development | 2014 | 2018 | 188 | 74.99 |  | Annual report on funding recommendations | 2015
| El Camino Real Corridor BRT Project | San Jose | Palo Alto | California |  | Bus Rapid Transit | Introduction of new mode | 17.4 | Small Starts | Project Development | 2013 | 2018 | 188 | 74.99 |  | Annual report on funding recommendations | 2016
| Silicon Valley Berryessa Extension Project | San Jose |  | California |  | Heavy Rail | Expansition of existing system | 10.2 | New Starts | Final Design | 2011 |  | 2,330.02 | 900 |  | Annual report on funding recommendations | 2013
| Silicon Valley Berryessa Extension Project | San Jose |  | California |  | Heavy Rail | Expansition of existing system | 10.2 | New Starts | Preliminary Engineering | 2009 |  | 2,330.02 | 900 |  | Annual report on funding recommendations | 2013
| Silicon Valley Berryessa Extension Project | San Jose |  | California |  | Heavy Rail | Expansition of existing system | 16.3 | New Starts | Preliminary Engineering | 2002 |  | 4997.8 | 973 |  | Annual report on funding recommendations | 2005
| Silicon Valley Berryessa Extension Project | San Jose |  | California |  | Heavy Rail | Expansition of existing system | 16.3 | New Starts | Preliminary Engineering | 2002 |  | 4771.8 | 973 |  | Annual report on funding recommendations | 2004
| Silicon Valley Berryessa Extension Project | San Jose | Santa Clara, Alameda | California |  | Bus Rapid Transit | Expansition of existing system | 10.15 | New Starts | FFGA Awarded | 2012 | 2018 | 2330.02 | 900 |  | Annual report on funding recommendations | 2014 | VTA and FTA entered into an FFGA in March 2012. More than eighty percent of the contracts have been awarded and the majority of the utility relocation work has been completed. Construction activities on the project are progressing well. Section 20008 of the Moving Ahead for Progress in the 21st Century Act authorized FTA to award Federal major capital investment funds for final design and construction of the project. Through FY 2014, Congress has appropriated a total of $402.59 million for the project.
| Silicon Valley Berryessa Extension Project | San Jose | Santa Clara, Alameda | California |  | Bus Rapid Transit | Expansition of existing system | 10.15 | New Starts | FFGA Awarded | 2012 | 2018 | 2330 | 900 |  | Annual report on funding recommendations | 2015 | VTA and FTA entered into an FFGA in March 2012. More than eighty percent of the contracts have been awarded and the majority of the utility relocation work has been completed. Construction activities on the project are progressing well. Section 20008 of the Moving Ahead for Progress in the 21st Century Act authorized FTA to award Federal major capital investment funds for final design and construction of the project. Through FY 2014, Congress has appropriated a total of $402.59 million for the project.
| Silicon Valley Berryessa Extension Project | San Jose | Santa Clara, Alameda | California |  | Bus Rapid Transit | Expansition of existing system | 10.15 | New Starts | FFGA Awarded | 2012 | 2018 | 2330 | 900 |  | Annual report on funding recommendations | 2016
| Silicon Valley Phase II | San Jose |  | California |  | Bus Rapid Transit |  |  | New Starts | Project Development |  |  | 4.693 |  |  | Annual report on funding recommendations | 2018
| BART Silicon Valley Phase II Extension to San Jose | San Jose | Santa Clara | California |  | Heavy Rail | Expansition of existing system | 6.5 | New Starts | Project Development | 2016 | 2026 |  |  |  | project Profile | 2018
861-a | Mid Coast Corridor (LR) | San Diego County | _ | California | _ | Light Rail | Expansition of existing system | 10.3 | New Starts |  |  |  | $353.3 |  |  | Annual report on funding recommendations | 1997 | commuter rail improvements, a light rail line, and high occupancy vehicle lanes in the Mid-Coast Corridor.
861-a1 | Mid Coast Corridor (LR-Initial rail improvement) | San Diego County | _ | California | _ |  | Expansition of existing system |  | New Starts |  |  |  | 77.00 | 61.60 |  | Annual report on funding recommendations | 1997
861-b | Mid Coast Corridor (Commuter rail improvements) | San Diego County | _ | California | _ | Commuter Rail | Improvement of existing service |  | New Starts |  |  |  | 5.7 |  |  | Annual report on funding recommendations | 1997
861-c | Mid Coast Corridor (HOV lanes) | San Diego County | _ | California | _ |  |  |  | New Starts |  |  |  | 148.7 |  |  | Annual report on funding recommendations | 1997
861-a | Mid Coast Corridor (LR) | San Diego County | _ | California | _ | Light Rail | Expansition of existing system | 10.4 | New Starts |  |  |  | $353.3 |  |  | Annual report on funding recommendations | 1998
861-a | Mid Coast Corridor (LR) | San Diego County | _ | California | _ | Light Rail | Expansition of existing system | 10.7 | New Starts | [6 empty] | Annual report on funding recommendations | 2000
861-a | Mid Coast Corridor (LR) | San Diego County | _ | California | _ | Light Rail | Expansition of existing system | 3.4 | New Starts | Preliminary Engineering |  |  | 116.7 | 42.2 | 0.5 | Annual report on funding recommendations | 2002
861-a1 | Mid Coast Corridor (LR-Initial rail improvement) | San Diego County | _ | California | _ | Light Rail | Expansition of existing system | 3.4 | New Starts | Preliminary Engineering | 1996 |  | 77 | 61.60 |  | Annual report on funding recommendations | 1998
861-a1 | Mid Coast Corridor (LR-Initial rail improvement) | San Diego County | _ | California | _ | Light Rail | Expansition of existing system | 3.4 | New Starts |  |  |  | 104.6 | 54.7 | 0.6 | Annual report on funding recommendations | 2000
861-a1 | Mid Coast Corridor (LR-Initial rail improvement) | San Diego County | _ | California | _ | Light Rail | Expansition of existing system | 3.4 | New Starts | Preliminary Engineering | 1996 |  | 131.6 | 65.8 |  | Annual report on funding recommendations | 2005
861-a1 | Mid Coast Corridor (LR-Initial rail improvement) | San Diego County | _ | California | _ | Light Rail | Expansition of existing system | 3.4 | New Starts | Preliminary Engineering | 1996 |  | 134.2 | 65.8 | 0.5 | Annual report on funding recommendations | 2004
| Ocenaside-Esconsiso Rail Corridor | San Diego County | Visat, San Marcos | California |  | Diesel Multiple Units | Conversion | 23.7 | New Starts | Final Design | 2000 |  | 332.3 | 152.1 |  | Annual report on funding recommendations | 2002
871 | I-405/SR-55 Transitway and Direct Access HOV Ramps | Orange County | _ | California | _ | Transitway | Improvement of existing service | 100 | New Starts |  |  | 2004 | 409.10 | 288.30 |  | Annual report on funding recommendations | 1997 | Construction of a joint HOV/Transitway facilities
871 | I-405/SR-55 Transitway and Direct Access HOV Ramps (MOS-1) | Orange County | _ | California | _ | Transitway | Improvement of existing service |  | New Starts |  |  | 2002 |  | 23.32 |  | Annual report on funding recommendations | 1998
| CentreLine LRT Project | Orange County | _ | California | _ | Light Rail | Introduction of new mode | 8.5 | New Starts | Preliminary Engineering | 1998 |  | 965.7 | 482.8 | 16.8 | Annual report on funding recommendations | 2005
| CentreLine LRT Project | Orange County | _ | California | _ | Light Rail | Introduction of new mode | 18.7 | New Starts | Preliminary Engineering | 1998 |  | 2110.7 | 1055.4 | 521.9 | Annual report on funding recommendations | 2004 | The project got shorten in 2001 and again in 2002
| CentreLine LRT Project | Orange County | _ | California | _ | Light Rail | Introduction of new mode | 18.7 | New Starts | Preliminary Engineering | 1998 |  | 1889 | 944.5 | 411 | Annual report on funding recommendations | 2003
| CentreLine LRT Project | Orange County | _ | California | _ | Light Rail | Introduction of new mode | 30.1 | New Starts | Preliminary Engineering | 1998 |  | 3741 | 1870.6 | 638.6 | Annual report on funding recommendations | 2002
| San Diego County, California/Mission Valley East | San Diego | _ | California | _ | Light Rail | Expansition of existing system | 5.9 | New Starts | Preliminary Engineering | 1998 |  | $361 | 275.2 | 12.1 | Annual report on funding recommendations | 2000
| San Diego County, California/Mission Valley East | San Diego | _ | California | _ | Light Rail | Expansition of existing system | 5.9 | New Starts | Final Design | 1998 |  | 431.0 | 330.0 | 13.7 | Annual report on funding recommendations | 2001
881 | San Diego County, California/Mission Valley East | San Diego | _ | California | _ | Light Rail | Expansition of existing system | 5.9 | New Starts | Final Design | 1998 |  |  |  |  | Annual report on funding recommendations | 2007 | Total cost of the project predicted in YOE $351.52/ Section 5309 share: 152.10
881 | San Diego County, California/Mission Valley East | San Diego | _ | California | _ | Light Rail | Expansition of existing system | 5.9 | New Starts | FFGA Awarded | 2000 | 2005 | 430.96 | 329.96 | 13.7 | Annual report on funding recommendations | 2004
881 | San Diego County, California/Mission Valley East | San Diego | _ | California | _ | Light Rail | Expansition of existing system | 5.9 | New Starts | Project Opening | 2005 |  | 430.96 | 329.96 |  | Annual report on funding recommendations | 2007
| Mid-Coast Corridor Transit Project | San Diego |  | California |  | Light Rail | Expansition of existing system | 10.9 | New Starts | Project Development | 2012 | 2019 | 1984.69 | 980.43 |  | Annual report on funding recommendations | 2014
| Mid-Coast Corridor Transit Project | San Diego |  | California |  | Light Rail | Expansition of existing system | 10.9 | New Starts | Preliminary Engineering | 2011 | 2019 | 2112.11 | 1043.38 |  | Annual report on funding recommendations | 2016
| Mid-Coast Corridor Transit Project | San Diego |  | California |  | Light Rail |  |  | New Starts | CGA | 2016 |  | 2.171 | 1.043 |  | Annual report on funding recommendations | 2018
| Mid-Coast Corridor Transit Project | San Diego |  | California |  |  |  |  | New Starts | Engineering | 2015 |  | 2,171 | 1,043 |  | Annual report on funding recommendations | 2017
| Mid-Coast Corridor Project | San Diego |  | California |  | Transitway | Expansition of existing system | 3.5 | New Starts | Preliminary Engineering | 2011 | 2022 | 2,171.2 | 1,043.38 |  | Project Profile | 2020
| Mid-Coast Corridor Project | San Diego |  | California |  | Transitway | Expansition of existing system | 3.5 | New Starts | Engineering | 2015 | 2022 | 2,171.2 | 1,043.38 |  | Project Profile | 2020
| Mid-Coast Corridor Project | San Diego |  | California |  | Transitway | Expansition of existing system | 3.5 | New Starts | FFGA Awarded | 2016 | 2022 | 2,171.2 | 1,043.38 |  | Project Profile | 2020
| Caltrain Peninsula Corridor Electrification Project | San Carlos | _ | California | _ | Transitway |  |  | Core Capacity | CGA | 2017 |  |  |  |  | Annual report on funding recommendations | 2019
| Caltrain Peninsula Corridor Electrification Project | San Carlos | _ | California | _ |  |  |  | Core Capacity | Project Development | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| Peninsula Corridor Electrification Project | San Carlos | _ | California |  | Commuter Rail | Improvement of existing service | 51 | Core Capacity | Project Development | 2015 | 2022 | 1,930.67 | 647.00 | 287.15 | Project Profile | 2020
| Peninsula Corridor Electrification Project | San Carlos | _ | California |  | Commuter Rail | Improvement of existing service | 51 | Core Capacity | Engineering | 2016 | 2022 | 1,930.67 | 647.00 | 287.15 | Project Profile | 2020
| Blackstone/Kings Canyon Bus Rapid Transit | Fresno |  | California |  | Bus Rapid Transit | Introduction of new mode | 15.7 | Small Starts | Project Development | 2010 | Late 2015 | 48.75 | 39 |  | Annual report on funding recommendations | 2015
| Blackstone/Kings Canyon Bus Rapid Transit | Fresno |  | California |  | Bus Rapid Transit |  |  | Small Starts | CGA | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| Fresno Area Express “Q” Blackstone/Kings Canyon | Fresno |  | California |  | Bus Rapid Transit | Improvement of existing service | 15.7 | Small Starts | Project Development | 2014 | Late 2016 | 48.53 | 38.82 |  | Annual report on funding recommendations | 2016
| Garden Grove Streetcar | Santa Ana |  | California |  | Streetcar |  |  | New Starts | Engineering | 2016 |  | 297.9 | 149.0 |  | Annual report on funding recommendations | 2018
| Garden Grove Streetcar | Santa Ana |  | California |  | Streetcar |  |  | New Starts | Project Development | 2015 |  | 288.7 | 144.4 |  | Annual report on funding recommendations | 2017
| East Bay BRT | Oakland | San Leandro | California |  | Bus Rapid Transit | Introduction of new mode | 14.4 | Small Starts | Project Development | 2008 |  | 205.48 | 74.99 |  | Annual report on funding recommendations | 2013
| East Bay BRT | Oakland | San Leandro | California |  | Bus Rapid Transit | Introduction of new mode | 9.5 | Small Starts | Project Development | 2012 | 2016 | 177.86 | 74.99 | STIP Funds: 41.55mn Section 5309 Bus Discretionary: 2.96 mn | Annual report on funding recommendations | 2014
| East Bay BRT | Oakland | San Leandro | California |  | Bus Rapid Transit | Introduction of new mode | 9.5 | Small Starts | Project Development | 2012 | Late 2017 | 177.99 | 74.99 | 44.41 | Annual report on funding recommendations | 2015
| San Rafael to Larkspur Regional Connection | San Rafael | Larkspur | California |  | Commuter Rail | Expansition of existing system | 2 | Small Starts | Project Development | 2013 | Not given | 30 | 16 |  | Annual report on funding recommendations | 2015
| SMART Regional Rail Commuter Rail | San Rafael | Larkspur | California |  | Commuter Rail | Expansition of existing system | 2.1 | Small Starts | Project Development | 2013 | 2016 | 42.53 | 22.53 |  | Annual report on funding recommendations | 2016
| Redlands Passenger Rail Project | San Bernardino |  | California |  |  |  |  | Small Starts | Project Development | 2016 |  | 262.0 |  |  | Annual report on funding recommendations | 2018
| West Valley Connector | San Bernardino |  | California |  | Bus Rapid Transit | Introduction of new mode | 19 | Small Starts | Project Development |  | 2022 | 219 | 65 |  | Project Profile | 2018
| SPRINTER Light Rail (Oceanside-Escondido) | Oceanside | Vista, San Marcos and Escondido | California |  | Light Rail | Introduction of new mode | 22 | New Starts | FFGA Awarded | 2003 | 2005 | 351.52 | 152.1 |  | Annual report on funding recommendations | 2005
| SPRINTER Light Rail (Oceanside-Escondido) | Oceanside | Vista, San Marcos and Escondido | California |  | Light Rail | Introduction of new mode | 22 | New Starts | Final Design | 2000 | 2005 | 351.52 | 152.1 |  | Annual report on funding recommendations | 2004
| SPRINTER Light Rail (Oceanside-Escondido) | Oceanside | Vista, San Marcos and Escondido | California |  | Light Rail | Introduction of new mode | 22 | New Starts | Final Design | 2000 |  | 332.3 | 152.1 |  | Annual report on funding recommendations | 2003
| SPRINTER Light Rail | Oceanside | Vista, San Marcos and Escondido | California |  | Light Rail | Introduction of new mode | 22 | New Starts | FFGA Awarded | 2002 | 2005 | 351.52 |  |  | Before-and-After Study | 2011
| SPRINTER Light Rail | Oceanside | Vista, San Marcos and Escondido | California |  | Light Rail | Introduction of new mode | 22 | New Starts | FFGA Awarded | 2006 | 2008 | 484.14 |  |  | Before-and-After Study | 2011 | Amended FFGA
| SPRINTER Light Rail | Oceanside | Vista, San Marcos and Escondido | California |  | Light Rail | Introduction of new mode | 22 | New Starts | Project Opening | 2008 |  | 477.63 |  |  | Before-and-After Study | 2011
| SURF | Monterey | Marina, Sand City, and Seaside, in Monterey County | California |  | Bus Rapid Transit | Introduction of new mode | 6 | Small Starts | Project Development |  | 2027 | 55 | 40 |  | Project Profile | 2020
911 | South LRT | Salt Lake City | _ | Utah | _ | Light Rail | Introduction of new mode | 15 | New Starts | FFGA Awarded | 1995 | 1997 | 312.50 | 237.40 | 4 | Annual report on funding recommendations | 1997
911 | South LRT | Salt Lake City | _ | Utah | _ | Light Rail | Introduction of new mode | 15 | New Starts | Final Design | 1995 | 2000 |  |  |  | Annual report on funding recommendations | 2004
911 | South LRT | Salt Lake City | _ | Utah | _ | Light Rail | Introduction of new mode | 15 | New Starts | FFGA Awarded | 1995 |  | 312.49 | 237.39 | 4 | Annual report on funding recommendations | 1999
911 | South LRT | Salt Lake City | _ | Utah | _ | Light Rail | Introduction of new mode | 15 | New Starts | FFGA Awarded | 1995 | 2003 | 312.49 | 237.39 | 4 | Annual report on funding recommendations | 2004
912 | Downtown connector | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 1 | New Starts | Preliminary Engineering | 1998 |  | 74.8 | 59.8 |  | Annual report on funding recommendations | 2000
| Mid-Jordan LRT | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 10.6 | New Starts | Preliminary Engineering | 2007 |  |  |  |  | Annual report on funding recommendations | 2011
| Mid-Jordan LRT | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 10.6 | New Starts | Preliminary Engineering | 2007 |  | 521.8 |  |  | before and After Study | 2016 | The actual cost of the Mid-Jordan project was $509.8 million in year-of-expenditure (YOE)
| Mid-Jordan LRT | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 10.6 | New Starts | Final Design | 2008 |  | 535.37 | 428.29 |  | Annual report on funding recommendations | 2011
| Mid-Jordan LRT | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 10.6 | New Starts | FFGA Awarded | 2009 | 2011 | 535.37 | 428.29 |  | Annual report on funding recommendations | 2010
| Mid-Jordan LRT | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 10.6 | New Starts | Project Opening | 2011 |  | 509.00 |  |  | before and After Study | 2016
| Weber County to Salt Lake City Commuter Rail | Salt Lake City | _ | Utah | _ | Commuter Rail | Introduction of new mode | 44 | New Starts | FFGA Awarded | 2006 |  | $611.68 | 489.35 |  | Annual report on funding recommendations | 2010
| Weber County to Salt Lake City Commuter Rail | Salt Lake City | _ | Utah | _ | Commuter Rail | Introduction of new mode | 44 | New Starts | Final Design | 2005 |  | 611.7 | 489.3 |  | Annual report on funding recommendations | 2007
| Weber County to Salt Lake City Commuter Rail | Salt Lake City | _ | Utah | _ | Commuter Rail | Introduction of new mode | 44 | New Starts | Preliminary Engineering | 2003 |  | 408 | 204 |  | Annual report on funding recommendations | 2005
| Weber County to Salt Lake City Commuter Rail | Salt Lake City | _ | Utah | _ | Commuter Rail | Introduction of new mode | 44 | New Starts | Preliminary Engineering | 2003 |  |  |  |  | Annual report on funding recommendations | 2011
| TRAX Light Rail System- Medical Center Extension | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 1.53 |  | FFGA Awarded | 2002 | 2004 | 89.39 | 53.63 |  | Annual report on funding recommendations | 2005
| TRAX Light Rail System- Medical Center Extension | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 1.5 | New Starts | Final Design | 2001 |  | 89.4 | 53.6 |  | Annual report on funding recommendations | 2003
| TRAX Light Rail System- Medical Center Extension | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 1.53 |  | Preliminary Engineering | 1998 |  |  |  |  | Annual report on funding recommendations | 2005
| TRAX Light Rail System- Medical Center Extension | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 1.53 |  | Project Opening | 2003 |  |  |  |  | Before-and-After Study | 2007
| TRAX Light Rail System- Medical Center Extension | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 1.53 |  | Final Design | 2002 |  | 89.3 |  |  | Before-and-After Study | 2007
| TRAX Light Rail System- Medical Center Extension | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 1.58 |  | Preliminary Engineering |  |  | 521.9 |  |  | Before-and-After Study | 2007
| TRAX Light Rail System- Medical Center Extension | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system | 1.53 |  | FFGA Awarded | 2002 |  |  |  |  | Before-and-After Study | 2007
| TRAX Light Rail System | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system |  |  | Final Design | 1999 |  |  |  |  | Before-and-After Study | 2007
| TRAX Light Rail System | Salt Lake City | _ | Utah | _ | Light Rail | Expansition of existing system |  |  | Preliminary Engineering | 1998 |  |  |  |  | Before-and-After Study | 2007
| Draper Transit Corridor | Salt Lake City | _ | Utah |  | Light Rail | Expansition of existing system |  |  | Preliminary Engineering | 2009 |  | 193.64 | 116.18 |  | Annual report on funding recommendations | 2013
| Draper Transit Corridor | Salt Lake City | _ | Utah |  | Light Rail | Expansition of existing system |  |  | FFGA Awarded | 2011 |  | 193.64 | 116.18 |  | Annual report on funding recommendations | 2013
| FrontRunner North Rail Project | Salt Lake City | _ | Utah |  | Commuter Rail | Introduction of new mode | 44 |  | Preliminary Engineering | 2003 |  | 408 |  |  | Before-and-After Study | 2013
| FrontRunner North Rail Project | Salt Lake City | _ | Utah |  | Commuter Rail | Introduction of new mode | 44 |  | Final Design | 2005 |  | 581 |  |  | Before-and-After Study | 2013
| FrontRunner North Rail Project | Salt Lake City | _ | Utah |  | Commuter Rail | Introduction of new mode | 44 |  | FFGA Awarded | 2006 |  | 611.7 |  |  | Before-and-After Study | 2013
| FrontRunner North Rail Project | Salt Lake City | _ | Utah |  | Commuter Rail | Introduction of new mode | 44 |  | Project Opening | 2008 |  |  |  |  | Before-and-After Study | 2013
| CBD to university LRT | Salt Lake City | _ | Utah |  | Light Rail | Expansition of existing system | 2.5 |  | Preliminary Engineering | 1998 |  |  |  |  | Annual report on funding recommendations | 2005
| CBD to university LRT | Salt Lake City | _ | Utah |  | Light Rail | Expansition of existing system | 2.5 |  | Final Design | 2000 |  |  |  |  | Annual report on funding recommendations | 2005
| CBD to university LRT | Salt Lake City | _ | Utah |  | Light Rail | Expansition of existing system | 2.5 |  | FFGA Awarded | 2000 | 2002 | 118.50 | 84.6 | 11.90 | Annual report on funding recommendations | 2005
| CBD to university LRT | Salt Lake City | _ | Utah |  | Light Rail | Expansition of existing system | 2.5 |  | Project Opening | 2001 | 2002 | 118.50 | 84.6 | 11.90 | Annual report on funding recommendations | 2005
| CBD to university LRT | Salt Lake City | _ | Utah |  | Light Rail | Expansition of existing system | 2.5 |  | FFGA Awarded | 2000 | 2002 | 118.50 | 84.6 | 11.90 | Annual report on funding recommendations | 2002
| Provo-Orem Bus Rapid Transit | Utah County |  | Utah |  | Bus Rapid Transit | Introduction of new mode | 10.52 | Small Starts | Project Development | 2013 | 2016 | 159.37 | 74.99 |  | Annual report on funding recommendations | 2014
| Provo-Orem Bus Rapid Transit | Utah County |  | Utah |  | Bus Rapid Transit | Introduction of new mode | 10.5 | Small Starts | Project Development | 2013 | 2016 | 159.38 | 74.99 |  | Annual report on funding recommendations | 2015
| Provo-Orem Bus Rapid Transit | Utah County |  | Utah |  | Bus Rapid Transit | Introduction of new mode | 10.5 | Small Starts | Project Development | 2013 | 2017 | 149.92 | 74.99 |  | Annual report on funding recommendations | 2016
| Provo-Orem Bus Rapid Transit | Utah County |  | Utah |  | Bus Rapid Transit |  |  | Small Starts | CGA | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Ogden/Weber State University BRT | Ogden |  | Utah |  | Bus Rapid Transit | Introduction of new mode | 5.3 | Small Starts | Project Development |  | 2022 |  |  |  | Project Profile | 2019
1012 | Minillas Extension | San Juan | _ | Puerto Rico | _ | Heavy Rail | Expansition of existing system |  | New Starts |  |  |  | 477.5 | 382.6 |  | Annual report on funding recommendations | 2002 | Extension to Tren Urbano Phase I which is under construction
1012 | Minillas Extension | San Juan | _ | Puerto Rico | _ | Heavy Rail | Expansition of existing system | 1 | New Starts |  |  |  | 468.0 | 374.4 |  | Annual report on funding recommendations | 2000 | Extension to Tren Urbano Phase I which is under construction
1011 | Tren Urbano | San Juan | _ | Puerto Rico | _ | Light Rail | Expansition of existing system | 1 | New Starts |  |  |  | 561.5 | 449.2 |  | Annual report on funding recommendations | 2004
1011 | Tren Urbano | San Juan | _ | Puerto Rico | _ | Light Rail | Introduction of new mode | 10.4 | New Starts | FFGA Awarded | 1999 | 2004 | 1,653.61 | 307.41 | 400.9 | Annual report on funding recommendations | 2005
1011 | Tren Urbano | San Juan | _ | Puerto Rico | _ | Light Rail | Introduction of new mode | 10.4 | New Starts | FFGA Awarded | 1996 |  | 1121.90 | 312.40 | 300 | Annual report on funding recommendations | 1997 | Rapid transit
1011 | Tren Urbano | San Juan | _ | Puerto Rico | _ | Light Rail | Introduction of new mode | 10.4 | New Starts | FFGA Awarded | 1996 |  | 1,250.30 | 307.40 | 300 | Annual report on funding recommendations | 1998
1011 | Tren Urbano | San Juan | _ | Puerto Rico | _ | Light Rail | Introduction of new mode | 10.7 | New Starts | FFGA Awarded | 1999 | 2004 | 1,653.60 | 307.40 | 300 | Annual report on funding recommendations | 2004 | Amended FFGA
1011 | Tren Urbano | San Juan | _ | Puerto Rico | _ | Light Rail | Introduction of new mode | 10.7 | New Starts | FFGA Awarded | 1999 |  | 1,653.31 | 307.41 | 400 | Annual report on funding recommendations | 2001 | Amended FFGA
1011 | Tren Urbano | San Juan | _ | Puerto Rico | _ | Light Rail | Introduction of new mode | 10.7 | New Starts | FFGA Awarded | 1996 |  | 1,550.3 | 307.40 |  | Annual report on funding recommendations | 2000
1011 | Tren Urbano | San Juan | _ | Puerto Rico | _ | Light Rail | Introduction of new mode | 10.7 | New Starts | Project Opening | 2005 |  | 1,653.61 | 307.41 | 400.9 | Annual report on funding recommendations | 2007
1011 | Tren Urbano | San Juan | _ | Puerto Rico | _ | Light Rail | Introduction of new mode | 10.7 | New Starts | FFGA Awarded | 1996 | 2002 |  |  |  | Before and After Study | 2008 | Amended FFGA
1011 | Tren Urbano | San Juan | _ | Puerto Rico | _ | Light Rail | Introduction of new mode | 10.7 | New Starts | Project Opening | 2004 |  |  |  |  | Before and After Study | 2008 | From 1999 to 2004, total estimated project cost increased from $1.65 billion to $2.25 billion
1111 | St. Clair County, Illinois Corridor | St. Louis | St. Clair County | Missouri | Illinois | Light Rail | Expansition of existing system | 26 | New Starts | FFGA Awarded | 1996 |  | 295.00 | 236.00 |  | Annual report on funding recommendations | 1997 | the project is projected to carry 10,000 to 15,000 riders per day in the year 2010.
1111 | St. Clair County, Illinois Corridor | St. Louis | St. Clair County | Missouri | Illinois | Light Rail | Expansition of existing system | 26 | New Starts | FFGA Awarded | 1996 |  | 339.2 | 243.93 |  | Annual report on funding recommendations | 1998
1111 | St. Clair County, Illinois Corridor | St. Louis | St. Clair County | Missouri | Illinois | Light Rail | Expansition of existing system | 26 | New Starts | FFGA Awarded | 1996 |  | 339.2 | 243.93 |  | Annual report on funding recommendations | 2003
1111-a | St. Clair County, Illinois Corridor (IOS-1) | St. Louis | St. Clair County | Missouri | Illinois | Light Rail | Expansition of existing system | 17.4 | New Starts | FFGA Awarded | 1996 |  | 339.2 | 243.93 |  | Annual report on funding recommendations | 1999
1111-a | St. Clair County, Illinois Corridor | St. Louis | St. Clair County | Missouri | Illinois | Light Rail | Expansition of existing system | 17.4 | New Starts | Preliminary Engineering | 1996 |  | 339.2 | 243.93 |  | Annual report on funding recommendations | 2005
1111-a | St. Clair County, Illinois Corridor | St. Louis | St. Clair County | Missouri | Illinois | Light Rail | Expansition of existing system | 17.4 | New Starts | Final Design | 1996 | 2001 | 339.2 | 243.93 |  | Annual report on funding recommendations | 2005
1111-a | St. Clair County, Illinois Corridor | St. Louis | St. Clair County | Missouri | Illinois | Light Rail | Expansition of existing system | 17.4 | New Starts | FFGA Awarded | 1996 | 2001 | 339.2 | 243.93 |  | Annual report on funding recommendations | 2005
1111-a | St. Clair County, Illinois Corridor | St. Louis | St. Clair County | Missouri | Illinois | Light Rail | Expansition of existing system | 17.4 | New Starts | Project Opening | 2001 |  | 339.2 | 243.93 |  | Annual report on funding recommendations | 2005
1121 | Southtown Corridor | Kansas city | _ | Missouri | _ | Light Rail | Expansition of existing system | 15.2 | New Starts | Preliminary Engineering | 1995 |  | 450 | 360 |  | Annual report on funding recommendations | 1997 | PE begins
1121-a | Southtown Corridor (Segment) | Kansas city | _ | Missouri | _ | Light Rail | Expansition of existing system | 5.6 | New Starts | Preliminary Engineering | 1995 |  | 220 | 176 |  | Annual report on funding recommendations | 2000
| Streetcar Expansion | Kansas city | _ | Missouri | _ |  |  |  | Small Starts | Project Development | 2017 |  |  |  |  | Annual report on funding recommendations | 2019
| Streetcar Expansion | Kansas city | _ | Missouri | _ | Streetcar | Expansition of existing system | 3.5 | Small Starts | Project Development | 2017 | 2025 | 351.63 | 174.06 |  | Project Profile | 2019
| Southtown BRT | Kansas city |  | Missouri |  | Bus Rapid Transit | Improvement of existing service | 10 | New Starts | Preliminary Engineering | 1995 |  | 25.9 | 12.3 |  | Annual report on funding recommendations | 2005
| Southtown BRT | Kansas city |  | Missouri |  | Bus Rapid Transit | Improvement of existing service | 10 | New Starts | Final Design |  |  | 25.9 | 12.3
| Prospect MAX Bus Rapid Transit | Kansas city | _ | Missouri | _ | Bus Rapid Transit |  |  | Small Starts | Project Development | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| I-35 Commuter Rail | Kansas city | Johnson County | Missouri |  | Commuter Rail | Expansition of existing system | 23 | New Starts | Preliminary Engineering | 1999 |  | 30.9 | 24.8 |  | Annual report on funding recommendations | 2005
| I-35 Commuter Rail | Kansas city | Johnson County | Missouri |  | Commuter Rail | Expansition of existing system | 23 | New Starts | Preliminary Engineering | 1999 |  | 30.9 | 24.8 |  | Annual report on funding recommendations | 2002
1211 | Tri-County Commuter Rail | Ft. Lauderdale | West Palm Beach, Broward and Miami | Florida | _ | Commuter Rail | Improvement of existing service | 67 | New Starts |  |  | 1997 | 428.29 | 189.50 | 56.39 | Annual report on funding recommendations | 1997
1211 | Tri-County Commuter Rail | Ft. Lauderdale | West Palm Beach, Broward and Miami | Florida | _ | Commuter Rail | Expansition of existing system | 70 | New Starts |  |  | 1997 | 428.3 | 206.40 | 39.50 | Annual report on funding recommendations | 1998 | FFTA is anticipated to be submitted in 1997
1211 | Tri-County Commuter Rail | Ft. Lauderdale | West Palm Beach, Broward and Miami | Florida | _ | Commuter Rail | Improvement of existing service | 71.7 | New Starts |  |  | 2007 | 422.00 | 130.80 | 93.3 | Annual report on funding recommendations | 2000
1211 | Tri-County Commuter Rail / Segment 5 | Ft. Lauderdale | West Palm Beach, Broward and Miami | Florida | _ | Commuter Rail | Improvement of existing service | 71.7 | New Starts | Final Design |  | 2005 | 327 | 110.5 | 74.2 | Annual report on funding recommendations | 2001
1211 | Tri-County Commuter Rail / Segment 5 | Ft. Lauderdale | West Palm Beach, Broward and Miami | Florida | _ | Commuter Rail | Improvement of existing service |  | New Starts |  |  | 2005 | 327 | 110.5 | 91.4 | Annual report on funding recommendations | 2002
| Tri-Rail Double-track Corridor Improvement | Miami | West Palm Beach, Broward and Ft. Lauderdale | Florida |  | Commuter Rail | Improvement of existing service | 71.7 | New Starts | FFGA Awarded | 2000 | 2005 | 327 | 110.50 | 147.1 | Annual report on funding recommendations | 2005
| Tri-Rail Double-track Corridor Improvement | Miami | West Palm Beach, Broward and Ft. Lauderdale | Florida |  | Commuter Rail | Improvement of existing service | 71.7 | New Starts | FFGA Awarded | 2000 | 2005 | 327 | 110.50 | 91.4 | Annual report on funding recommendations | 2003
| Tri-Rail Double-track Corridor Improvement | Miami | West Palm Beach, Broward and Ft. Lauderdale | Florida |  | Commuter Rail | Improvement of existing service | 72 | New Starts | Preliminary Engineering | 1997 | 2005 | 327.0 |  |  | Before and After Study | 2011
| Tri-Rail Double-track Corridor Improvement | Miami | West Palm Beach, Broward and Ft. Lauderdale | Florida |  | Commuter Rail | Improvement of existing service | 72 | New Starts | FFGA Awarded | 1999 | 2005 | 327.0 |  |  | Before and After Study | 2011
| Tri-Rail Double-track Corridor Improvement | Miami | West Palm Beach, Broward and Ft. Lauderdale | Florida |  | Commuter Rail | Improvement of existing service | 72 | New Starts | FFGA Awarded | 2004 | 2006 | 333.9 |  |  | Before and After Study | 2011 | Amended FFGA
| Tri-Rail Double-track Corridor Improvement | Miami | West Palm Beach, Broward and Ft. Lauderdale | Florida |  | Commuter Rail | Improvement of existing service | 72 | New Starts | Project Opening | 2006 |  |  |  |  | Before and After Study | 2011
1241 | East-West Corridor/Miami Intermodal Center | Miami | _ | Florida | _ |  | Improvement of existing service | 24.3 to 25.8 | New Starts |  |  |  | 1212 | 424.20 |  | Annual report on funding recommendations | 1997
1241 | East-West Corridor/Miami Intermodal Center | Miami | _ | Florida | _ |  | Improvement of existing service |  | New Starts | Preliminary Engineering | 1996 |  |  |  |  | Annual report on funding recommendations | 1998 | (MOS) of an 11.8 mile/ multimodal improvements
1241-a | East-West Corridor/Miami Intermodal Center (MOS) | Miami | _ | Florida | _ |  | Improvement of existing service | 11.8 | New Starts | Preliminary Engineering | 1996 |  | 1574.00 | 550.90 |  | Annual report on funding recommendations | 1998
1241-a | East-West Corridor/Miami Intermodal Center (MOS) | Miami | _ | Florida | _ | Heavy Rail | Improvement of existing service | 11.9 | New Starts | Preliminary Engineering | 1996 |  | 2,152.50 | 808.00 |  | Annual report on funding recommendations | 2000
1242 | Miami (North 27th Avenue Corridor) | Miami | _ | Florida | _ |  | Expansition of existing system | 9.5 | New Starts |  |  |  | 453.00 | 317.10 |  | Annual report on funding recommendations | 1997 | metrorail
1242 | North 27th Avenue Corridor | Miami | _ | Florida | _ | Bus Rapid Transit | Expansition of existing system | 9.5 | New Starts | Preliminary Engineering | 2001 |  | 87.9 | 61.5 |  | Annual report on funding recommendations | 2002
| North Corrido Metro Rail Extension | Miami | _ | Florida |  |  | Expansition of existing system | 9.5 | New Starts | Preliminary Engineering |  |  | 872.9 | 434.5 | 3.9 | Annual report on funding recommendations | 2005 | metrorail
| South Corridor Rapid Transit Project | Miami | _ | Florida |  | Bus Rapid Transit | Introduction of new mode | 20 | Small Starts | Project Development | 2019 | 2022 | 299.81 | 100.00 |  | Project Profile | 2019
| South Miami-Dade Bustway Extension | Miami | _ | Florida |  | Busway | Expansition of existing system | 11.5 | New Starts | Preliminary Engineering | 1998 |  | 88.8 | 23.4 | 38.6 | Annual report on funding recommendations | 2002
| South Miami-Dade Bustway Extension | Miami | _ | Florida |  | Busway | Expansition of existing system | 11.5 | New Starts | Final Design | 2000 |  | 88.8 | 23.4 | 38.6 | Annual report on funding recommendations | 2002
| Central Broward Transit Study, Phase I | Ft. Lauderdale |  | Florida |  |  |  |  | New Starts | Project Development | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
1221 | Central Florida Light Rail System- Initial Operating Segment | Orlando | _ | Florida | _ | Commuter Rail | Improvement of existing service | 32 | New Starts | FFGA Awarded | 2011 | 2014 | 357.23 | 178.61 |  | Annual report on funding recommendations | 2013
1221 | Central Florida Light Rail System- Initial Operating Segment | Orlando | _ | Florida | _ | Commuter Rail | Improvement of existing service | 32 | New Starts | Final Design | 2008 | 2014 | 357.23 | 178.61 |  | Annual report on funding recommendations | 2013
1221 | Central Florida Light Rail System- Initial Operating Segment | Orlando | _ | Florida | _ | Commuter Rail | Improvement of existing service | 32 | New Starts | Preliminary Engineering | 2007 | 2014 | 357.23 | 178.61 |  | Annual report on funding recommendations | 2013
1221 | Orlando (I-4 Central Florida Light Rail System) (MOS) | Orlando | _ | Florida | _ | Light Rail | Improvement of existing service | 25 | New Starts |  |  | 1998 | 880.00 | 440.00 |  | Annual report on funding recommendations | 1998
1221 | Orlando (I-4 Central Florida Light Rail System) (MOS) | Orlando | _ | Florida | _ | Light Rail | Improvement of existing service | 14.6 | New Starts |  |  |  | 600.1 | 330.0 |  | Annual report on funding recommendations | 2000
| SunRail Phase II North | Orlando |  | Florida |  | Commuter Rail | Expansition of existing system | 12 | Small Starts | FFGA Awarded | 2014 (Anticipated) | 2017 | 79.2 | 39.6 |  | Annual report on funding recommendations | 2015
| SunRail Phase II North | Orlando |  | Florida |  | Commuter Rail | Expansition of existing system | 12.2 | Small Starts | Project Development | 2013 | 2017 | 68.68 | 34.34 |  | Annual report on funding recommendations | 2016
| SunRail Phase II North | Orlando |  | Florida |  | Commuter Rail | Expansition of existing system | 12.2 | Small Starts | Project Development | 2013 | 2017 | 68.68 | 34.34 |  | Project Profile | 2014
| SunRail Phase II South | Orlando |  | Florida |  | Commuter Rail | Expansition of existing system | 17.2 | New Starts | Engineering | 2010 | 2017 | 185 | 92.5 |  | Annual report on funding recommendations | 2014
| SunRail Phase II South | Orlando |  | Florida |  | Commuter Rail | Expansition of existing system | 17.2 | New Starts | Engineering | 2010 | 2017 | 173.6 | 86.8 |  | Annual report on funding recommendations | 2015 | Anticipated FFGA in 2014
| SunRail Phase II South | Orlando |  | Florida |  | Commuter Rail | Expansition of existing system | 17.2 | New Starts | Engineering | 2010 | 2017 | 184.88 | 92.44 |  | Annual report on funding recommendations | 2016
| SunRail Phase II South | Orlando |  | Florida |  |  |  |  | New Starts | CGA | 2015 |  | 186 | 93 |  | Annual report on funding recommendations | 2017
| SunRail Connector to Orlando Airport | Orlando |  | Florida |  |  |  |  | Small Starts | Project Development | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| SunRail Connector to Orlando Airport | Orlando |  | Florida |  | Commuter Rail | Introduction of new mode | 5.5 | Small Starts | Project Development | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| Central Florida Commuter Rail Transit – Initial Operating Segment | Orlando |  | Florida |  | Commuter Rail | Introduction of new mode | 32 | New Starts | Final Design | 2012 | 2014 | 357.23 | 178.61 |  | Annual report on funding recommendations | 2014
| Central Florida Commuter Rail Transit – Initial Operating Segment | Orlando |  | Florida |  | Commuter Rail | Introduction of new mode | 32 |  | Preliminary Engineering | 2007 |  | 357.23 | 178.61 |  | Annual report on funding recommendations | 2013
| Central Florida Commuter Rail Transit – Initial Operating Segment | Orlando |  | Florida |  | Commuter Rail | Introduction of new mode | 32 |  | Preliminary Engineering | 2007 |  | 361.5 |  |  | Before and After Study | 2019
| Central Florida Commuter Rail Transit – Initial Operating Segment | Orlando |  | Florida |  | Commuter Rail | Introduction of new mode | 32 |  | Final Design | 2008 |  | 357.23 | 178.61 |  | Annual report on funding recommendations | 2013
| Central Florida Commuter Rail Transit – Initial Operating Segment | Orlando |  | Florida |  | Commuter Rail | Introduction of new mode | 32 |  | FFGA Awarded | 2011 |  | 357.23 | 178.61 |  | Annual report on funding recommendations | 2013
| Central Florida Commuter Rail Transit – Initial Operating Segment | Orlando |  | Florida |  | Commuter Rail | Introduction of new mode | 32 |  | Project Opening | 2014 |  |  |  |  | Before and After Study | 2019
1231 | Flagler to duPont Place | Jacksonville | _ | Florida | _ |  | Expansition of existing system | 0.3 | New Starts | FFGA Awarded | 1994 |  | 31.4 | 25 |  | Annual report on funding recommendations | 1997 | extension of the Automated Skyway Express (ASE). The FFGA was amended in 1994 to include this extension
1231 | Flagler to duPont Place | Jacksonville | _ | Florida | _ |  | Expansition of existing system |  | New Starts | FFGA Awarded | 1991 |  | 108.5 | 43.86 |  | Annual report on funding recommendations | 1998
1232 | South Extension of the Automated Skyway Express (ASE) | Jacksonville | _ | Florida | _ |  | Expansition of existing system | 1.2 | New Starts | FFGA Awarded | 1991 |  | 133.7 | 15.00 |  | Annual report on funding recommendations | 1995 | Automated Skyway Express
| JTA Bus Rapid Transit North Corridor | Jacksonville | _ | Florida | _ | Bus Rapid Transit | Expansition of existing system | 9.3 |  | Project Development | 2010 |  | 33.48 | 26.79 |  | Annual report on funding recommendations | 2013
| BRT North Corridor | Jacksonville | _ | Florida |  |  |  |  | Small Starts | CGA | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| East Corridor | Jacksonville | _ | Florida | _ |  |  |  | Small Starts | Project Development | 2015 |  | 33.9 | 16.9 |  | Annual report on funding recommendations | 2017
| JTA Bus Rapid Transit Southeast Corridor | Jacksonville | _ | Florida | _ |  | Expansition of existing system | 11.1 |  | Project Development | 2011 |  | 23.88 | 19.10 |  | Annual report on funding recommendations
| Southwest Corridor | Jacksonville | _ | Florida | _ |  |  |  | Small Starts | Project Development | 2015 |  | 19 | 9.5 |  | Annual report on funding recommendations | 2017
| Wave Streetcar | Fort Lauderdale |  | Florida |  | Streetcar | Introduction of new mode | 2.7 | Small Starts | Project Development | 2013 | 2016 | 142.59 | 49.65 | 21.5 | Annual report on funding recommendations | 2014
| Wave Streetcar | Fort Lauderdale |  | Florida |  | Streetcar | Introduction of new mode | 2.7 | Small Starts | Project Development | 2013 | 2016 | 142.59 | 49.65 | 21.5 | Annual report on funding recommendations | 2015
| Wave Streetcar | Fort Lauderdale |  | Florida |  | Streetcar | Introduction of new mode | 2.8 | Small Starts | Project Development | 2013 | 2017 | 161.85 | 59.28 | 21.5 | Annual report on funding recommendations | 2016
| Wave Streetcar | Fort Lauderdale |  | Florida |  | Streetcar | Introduction of new mode | 2.8 | Small Starts | CGA | 2017 |  |  |  |  | Annual report on funding recommendations | 2019
| JTA BRT Southeast Corridor | Jacksonville |  | Florida |  | Bus Rapid Transit | Expansition of existing system | 11.1 | Small Starts | Project Development | 2011 | 2014 | 23.88 | 19.1 |  | Annual report on funding recommendations | 2014
| JTA BRT Southeast Corridor | Jacksonville |  | Florida |  | Bus Rapid Transit | Expansition of existing system | 11.1 | Small Starts | Project Development | 2011 | 2016 | 23.88 | 19.1 |  | Annual report on funding recommendations | 2015
| JTA BRT Southeast Corridor | Jacksonville |  | Florida |  | Bus Rapid Transit | Expansition of existing system | 11.1 | Small Starts | Project Development | 2011 | 2017 | 23.88 | 19.1 |  | Annual report on funding recommendations | 2016
| JTA BRT North Corridor | Jacksonville |  | Florida |  | Bus Rapid Transit | Expansition of existing system | 9.3 | Small Starts | Project Development | 2010 | 2014 | 33.48 | 26.79 |  | Annual report on funding recommendations | 2014
| JTA BRT North Corridor | Jacksonville |  | Florida |  | Bus Rapid Transit | Expansition of existing system | 9.3 | Small Starts | Project Development | 2012 | 2015 | 33.23 | 26.59 |  | Annual report on funding recommendations | 2015
| Central Avenue Bus Rapid Transit Project | St. Petersburg |  | Florida |  | Bus Rapid Transit |  |  |  | Project Development | 2016 |  | 16.5 | 8.3 |  | Annual report on funding recommendations | 2018
| Central Avenue Bus Rapid Transit Project | St. Petersburg |  | Florida |  | Bus Rapid Transit | Introduction of new mode | 10.3 | Small Starts | Project Development | 2016 | 2021 | 43.93 | 21.83 |  | Project Profile | 2019
| Tampa Bay Regional Rail | Tampa Bay |  | Florida |  | Light Rail | Introduction of new mode | 20.1 | New Starts | Preliminary Engineering | 1999 |  | 1455.5 | 727.7 |  | Annual report on funding recommendations | 2005
| Tampa Streetcar Extension Project | Tampa |  | Florida |  | Streetcar | Expansition of existing system | 2.6 | Small Starts | Project Development |  | 2024 |  | 51.27 |  | Project Profile | 2018
1311 | Largo Corridor | Washington DC | _ | Distrcit of Colombia | _ | Heavy Rail | Expansition of existing system | 2.9 | New Starts | Preliminary Engineering | 1996 |  | 350 | 276.50 |  | Annual report on funding recommendations | 1997 | Washington Metrorail Blue Line.
1311 | Largo Corridor | Washington DC | _ | Distrcit of Colombia | _ | Heavy Rail | Expansition of existing system | 3.1 | New Starts | Preliminary Engineering | 1996 |  | 350 | 276.50 |  | Annual report on funding recommendations | 1998
1311 | Largo Corridor | Washington DC | _ | Distrcit of Colombia | _ | Heavy Rail | Expansition of existing system | 3.1 | New Starts |  |  | 2005 | 397.1 | 316.1 |  | Annual report on funding recommendations | 2000 | Heavy rail
1311 | Largo Corridor | Washington DC | _ | Distrcit of Colombia | _ | Heavy Rail | Expansition of existing system | 3.1 | New Starts | FFGA Awarded | 2000 | 2004 | 433.9 | 260.3 |  | Annual report on funding recommendations | 2002
| Largo Metrorail Extension | Washington DC | _ | Distrcit of Colombia | _ | Heavy Rail | Expansition of existing system | 3.1 | New Starts | Final Design | 2000 | 2004 | 433.90 | 260.30 |  | Annual report on funding recommendations | 2005
| Largo Metrorail Extension | Washington DC | _ | Distrcit of Colombia | _ | Heavy Rail | Expansition of existing system | 3.1 | New Starts | FFGA Awarded | 2000 | 2004 | 433.90 | 260.30 |  | Annual report on funding recommendations | 2005
1411 | Canal Streetcar Spine | New Orleans | _ | Louisiana | _ | Streetcar | Introduction of new mode | 4.4 | New Starts | Preliminary Engineering | 1995 |  | 92.60 | 74.10 |  | Annual report on funding recommendations | 1997 | Preliminary engineering is scheduled to begin in late 1996.
1411 | Canal Streetcar Spine | New Orleans | _ | Louisiana | _ | Streetcar | Introduction of new mode | 4.9 | New Starts | Preliminary Engineering | 1995 |  | 146.40 | 117.12 |  | Annual report on funding recommendations | 1998
1411 | Canal Streetcar Spine | New Orleans | _ | Louisiana | _ | Streetcar | Introduction of new mode | 4.7 | New Starts | Final Design | 1997 |  | 156.60 | 125.30 |  | Annual report on funding recommendations | 2000
1411 | Canal Streetcar Spine | New Orleans | _ | Louisiana | _ | Streetcar | Introduction of new mode | 5.5 | New Starts | Final Design | 1997 | 2002 | 139.4 | 111.5 |  | Annual report on funding recommendations | 2001
1411 | Canal Streetcar Spine | New Orleans | _ | Louisiana | _ | Streetcar | Introduction of new mode | 5.4 | New Starts | Final Design | 1997 |  | 161.3 | 129.05 |  | Annual report on funding recommendations | 2004 | ?
1411 | Canal Streetcar Spine | New Orleans | _ | Louisiana | _ | Streetcar | Introduction of new mode | 4.7 | New Starts | FFGA Awarded | 2003 | 2004 | 161.30 | 129.05 |  | Annual report on funding recommendations | 2005
| Desire Streetcar Line | New Orleans | _ | Louisiana | _ | Streetcar | Expansition of existing system | 2.9 | New Starts | Preliminary Engineering | 2000 |  | 93.5 | 65.5 |  | Annual report on funding recommendations | 2002
| Desire Streetcar Line | New Orleans | _ | Louisiana | _ | Streetcar | Expansition of existing system | 2.9 | New Starts | Preliminary Engineering | 2000 |  | 93.5 | 56.1 |  | Annual report on funding recommendations | 2003
| Desire Streetcar Line | New Orleans | _ | Louisiana | _ | Streetcar | Expansition of existing system | 2.9 | New Starts | Preliminary Engineering | 2001 |  | 121.2 | 68.7 |  | Annual report on funding recommendations | 2005
| St. Claude and Elysian Fields Streetcar Extensions | New Orleans | _ | Louisiana | _ | Streetcar | Expansition of existing system | 1.1 | Small Starts | Project Development |  | 2023 |  |  |  | Project Profile | 2018
| TramLinkBR Streetcar | Baton Rouge |  | Louisiana |  | Streetcar |  |  |  | Project Development | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| TramLinkBR | Baton Rouge |  | Louisiana |  | Streetcar | Expansition of existing system | 3 | Small Starts | Project Development | 2016 | 2021 | 170 | 84 |  | Project Profile | 2018
1511 | Hudson-Bergen Waterfront Light Rail Transit System | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 20.5 | New Starts | Preliminary Engineering | 1993 |  | 1300.00 | 623.90 |  | Annual report on funding recommendations | 1997
1511 | Hudson-Bergen Waterfront Light Rail Transit System | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 20.2 | New Starts |  |  |  | 1600 |  |  | Annual report on funding recommendations | 1999
1511 | Hudson-Bergen Waterfront Light Rail Transit System | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 20.2 | New Starts |  |  |  | 2000 |  |  | Annual report on funding recommendations | 2000
1512 | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 10 | New Starts | Preliminary Engineering | 1993 |  |  |  |  | Annual report on funding recommendations | 1997
1512 | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 9.6 | New Starts | FFGA Awarded | 1996 | 2000 | 992.14 | 604.09 | 281.65 | Annual report on funding recommendations | 1998
1512 | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 9.6 | New Starts | FFGA Awarded | 1996 | 2000 | 992.14 | 604.09 | 281.65 | Annual report on funding recommendations | 2000
1512 | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 9.3 | New Starts | FFGA Awarded | 1996 | 2002 | 992.14 | 604.09 | 281.65 | Annual report on funding recommendations | 2005
1512 | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 9.3 | New Starts | FFGA Awarded | 1996 | 2002 | 992.14 | 604.09 | 281.65 | Annual report on funding recommendations | 2003
1512 | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 9.3 | New Starts | Project Opening | 2002 | 2002 | 992.14 | 604.09 | 281.65 | Annual report on funding recommendations | 2005
1512 | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 6.1 | New Starts | FFGA Awarded | 2000 |  | 1,215.40 | 500.00 | 153.70 | Annual report on funding recommendations | 2010
1512 | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 5.1 | New Starts | FFGA Awarded | 2000 | 2005 | 1,215.40 | 500.00 | 153.70 | Annual report on funding recommendations | 2007
1512 | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 6.1 | New Starts |  |  |  | 1,112.8 | 721.6 | 273.8 | Annual report on funding recommendations | 2001
1513 | Newark-Elizabeth Rail Link | Northern New Jersey | _ | New Jersey | _ | Light Rail | Introduction of new mode | 8.8 | New Starts |  |  |  | 694.00 |  |  | Annual report on funding recommendations | 1997
1513-a | Newark-Elizabeth Rail Link (MOS I) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Expansition of existing system | 1 | New Starts |  |  |  | 150 | 112.5 | 35.70 | Annual report on funding recommendations | 2000 | a one mile Minimum Operable Segment (MOS) of an 8.8-mile .
1513-a | Newark-Elizabeth Rail Link (MOS I) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Expansition of existing system | 1 | New Starts |  |  |  | 207.7 | 141.9 | 65.2 | Annual report on funding recommendations | 2001 | a one mile Minimum Operable Segment (MOS) of an 8.8-mile .
1513-a | Newark-Elizabeth Rail Link (MOS I) | Northern New Jersey | _ | New Jersey | _ | Light Rail | Expansition of existing system | 1 | New Starts | FFGA Awarded | 2000 | 2005 | 207.75 | 141.95 | 25.30 | Annual report on funding recommendations | 2005
1514 | Secaucus Transfer Station | Northern New Jersey | _ | New Jersey | _ | commuter Rail | Expansition of existing system | _ | New Starts | FFGA Awarded | 1994 | 2002 | 444.26 | 444.26 |  | Annual report on funding recommendations | 1997 | commuter rail transfer station
| Hudson Tunnel | Seacaucus |  | New Jersey | New York |  |  |  | New Starts | Project Development | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Portal North Bridge Replacement | Hudson County |  | New Jersey |  |  |  |  | Core Capacity | Project Development | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Portal North Bridge Replacement | Hudson County |  | New Jersey |  | Commuter Rail | Improvement of existing service | 2.44 | Core Capacity | Project Development | 2016 | 2026 | 1,716.18 | 811.12 | 122.45 | Project Profile | 2019
1611 | Oklahoma city (Map Links) Park Avenue Rail Loop | Oklahoma City, | _ | Oklahoma | _ |  | Introduction of new mode | 1.74 | New Starts |  |  |  | 12.50 | 9.20 | 0.08 | Annual report on funding recommendations | 1997 | vintage rail trolley circulator
1611 | Oklahoma city (Map Links) | Oklahoma City, | _ | Oklahoma | _ |  | Introduction of new mode | 3 | New Starts |  |  |  | 21.70 | 13.00 | 0.8 | Annual report on funding recommendations | 1998 | vintage rail trolley
1711 | Phase I Airport Busway/Wabash HOV Facility | Pittsburgh | _ | Pennsylvania | _ | Bus Rapid Transit | Expansition of existing system | 7 | New Starts | FFGA Awarded | 1994 |  | 326.80 | 121 | 135.8 | Annual report on funding recommendations | 1996 | a 7-mile busway and a 1-mile HOV facility
1711 | Phase I Airport Busway/Wabash HOV Facility | Pittsburgh | _ | Pennsylvania | _ | Bus Rapid Transit | Expansition of existing system | 7 | New Starts | FFGA Awarded | 1994 |  | 326.80 | 121 | 135.8 | Annual report on funding recommendations | 1997 | a 7-mile busway and a 1-mile HOV facility
1711 | Phase I Airport Busway/Wabash HOV Facility | Pittsburgh | _ | Pennsylvania | _ | Bus Rapid Transit | Expansition of existing system | 7 | New Starts | FFGA Awarded | 1994 | 1999 | 321.70 | 149.83 | 101.87 | Annual report on funding recommendations | 1998
1711 | Phase I Airport Busway/Wabash HOV Facility | Pittsburgh | _ | Pennsylvania | _ | Bus Rapid Transit | Expansition of existing system | 5 | New Starts | FFGA Awarded | 1997 |  | 326.71 | 135.91 | 101.87 | Annual report on funding recommendations | 1999 | Amended FFGA
1712 | Martin Luther King, Jr. East Busway Extension | Pittsburgh | _ | Pennsylvania | _ | Bus Rapid Transit | Expansition of existing system | 2.3 | New Starts |  |  |  | 62.8 | 8.58 | 22.82 | Annual report on funding recommendations | 2000
1713 | Stage II Light Rail Transit Reconstruction Project | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Improvement of existing service | 12 | New Starts | Preliminary Engineering | 1996 |  | 414.00 | 232 | 99.2 | Annual report on funding recommendations | 1997 | PE begins
1713 | Stage II Light Rail Transit Reconstruction Project | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Improvement of existing service | 12 | New Starts | Final Design | 1996 |  | 512.50 | 162.60 | 237.4 | Annual report on funding recommendations | 2000
1713 | Stage II Light Rail Transit Reconstruction Project | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Improvement of existing service | 10.7 | New Starts | Preliminary Engineering |  |  | 383.7 | 100.2 | 3.9 | Annual report on funding recommendations | 2001 | PE completed in 1998
1713 | Stage II Light Rail Transit Reconstruction Project | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Improvement of existing service | 12 | New Starts | FFGA Awarded | 2001 | 2004 | 386.46 | 100.20 | 133.77 | Annual report on funding recommendations | 2005
| North Shore LRT Connector | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Expansition of existing system | 1.6 | New Starts | Preliminary Engineering | 2001 |  | 389.9 | 194.9 |  | Annual report on funding recommendations | 2002
| North Shore LRT Connector | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Expansition of existing system | 1.6 | New Starts | Preliminary Engineering | 2001 |  | 389.9 | 272.9 | 39 | Annual report on funding recommendations | 2003
| North Shore LRT Connector | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Expansition of existing system | 1.6 | New Starts | Preliminary Engineering | 2001 | 2007 | 389.9 | 233.9 | 77.9 | Annual report on funding recommendations | 2004
| North Shore LRT Connector | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Expansition of existing system | 1.5 | New Starts | Final Design | 2003 | 2008 | 362.8 | 217.7 | 72.6 | Annual report on funding recommendations | 2005 | pending FFGA
| North Shore LRT Connector | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Expansition of existing system | 1.2 | New Starts | FFGA Awarded | 2006 |  | 435.00 | 235.70 | 112.3 | Annual report on funding recommendations | 2010
| North Shore LRT Connector | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Expansition of existing system | 1.2 | New Starts | Preliminary Engineering | 2001 |  | 326.7 |  |  | before and After Study | 2016 | The actual capital cost of the project was $510.4 million in year-of-expenditure
| North Shore LRT Connector | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Expansition of existing system | 1.2 | New Starts | Final Design | 2003 |  | 326.8 |  |  | before and After Study | 2016
| North Shore LRT Connector | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Expansition of existing system | 1.2 | New Starts | FFGA Awarded | 2006 |  | 435.0 |  |  | before and After Study | 2016
| North Shore LRT Connector | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Expansition of existing system | 1.2 | New Starts | Recovery Plan | 2009 |  | 538.7 |  |  | before and After Study | 2016
| North Shore LRT Connector | Pittsburgh | _ | Pennsylvania | _ | Light Rail | Expansition of existing system | 1.2 | New Starts | Project opening | 2012 |  |  |  |  | before and After Study | 2016
| Downtown-Uptown-Oakland-East End BRT Project | Pittsburgh | _ | Pennsylvania | _ |  |  |  | Small Starts | Project Development | 2017 |  | 195.5 | 97.8 |  | Annual report on funding recommendations | 2019
| Downtown-Uptown-Oakland-East End BRT Project | Pittsburgh | _ | Pennsylvania | _ | Bus Rapid Transit | Introduction of new mode | 15 | Small Starts | Project Development | 2017 | 2024 | 249.90 | 99.95 | 10.76 | Project Profile | 2019
| Corridor one Rail MOS | Harrisburg |  | Pennsylvania |  | Commuter Rail | Introduction of new mode | 40.5 | New Starts | Preliminary Engineering | 2002 |  | 75.8 | 24.9 | 13.4 | Annual report on funding recommendations | 2005
| Corridor one Rail MOS | Harrisburg |  | Pennsylvania |  | Commuter Rail | Introduction of new mode | 40.5 | New Starts | Preliminary Engineering | 2002 |  | 87 | 24.9 | 14 | Annual report on funding recommendations | 2007
| Schuylkill Valley Metro Rail | Philadelphia |  | Pennsylvania |  | Commuter Rail | Introduction of new mode | 74 | New Starts | Preliminary Engineering | 2002 |  | 2588.2 | 2,071.1 |  | Annual report on funding recommendations | 2007
| Schuylkill Valley Metro Rail | Philadelphia |  | Pennsylvania |  | Commuter Rail | Introduction of new mode | 74 | New Starts | Preliminary Engineering | 2002 | 2010 | 1831.7 | 1465.4 |  | Annual report on funding recommendations | 2004
1811 | South/North Corridor | Portland | Vancouver | Oregon | Washington | Light Rail | Introduction of new mode | 20 | New Starts | Preliminary Engineering | 1996 |  | 2400.00 | 1200.00 |  | Annual report on funding recommendations | 1997 | PE begins
1811-a | South/North Corridor (MOS-1) | Portland | Vancouver | Oregon | Washington | Light Rail | Introduction of new mode | 12 | New Starts | Preliminary Engineering | 1996 |  | 1200 | 600 |  | Annual report on funding recommendations | 1998
1811-a | South/North Corridor (MOS-1) | Portland | Vancouver | Oregon | Washington | Light Rail | Introduction of new mode | 12 | New Starts |  |  |  | 1,186.3 | 636.3 | 55.00 | Annual report on funding recommendations | 2000
1812 | Portland, Oregon/Westside-Hillsboro Corridor | Portland | _ | Oregon | _ | Light Rail | Expansition of existing system | 18 | New Starts | FFGA Awarded | 1992 |  | 688 | 516.00 |  | Annual report on funding recommendations | 1996
1812 | Portland, Oregon/Westside-Hillsboro Corridor | Portland | _ | Oregon | _ | Light Rail | Expansition of existing system | 17.7 | New Starts | FFGA Awarded | 1992 |  | 688 | 516.00 |  | Annual report on funding recommendations | 1997
1812 | Portland, Oregon/Westside-Hillsboro Corridor | Portland | _ | Oregon | _ | Light Rail | Expansition of existing system | 17.7 | New Starts | Final Design | 1994 |  | 688 | 516.00 |  | Annual report on funding recommendations | 1997
1812 | Portland, Oregon/Westside-Hillsboro Corridor | Portland | _ | Oregon | _ | Light Rail | Expansition of existing system | 17.7 | New Starts | FFGA Awarded | 1994 |  | 910.18 | 590.05 | 74 | Annual report on funding recommendations | 1997 | Project starts with one segement and in 1994, two segments get combined
1812 | Portland, Oregon/Westside-Hillsboro Corridor | Portland | _ | Oregon | _ | Light Rail | Expansition of existing system | 17.7 | New Starts | FFGA Awarded | 1994 | 1998 | 963.52 | 630.06 | 74 | Annual report on funding recommendations | 1998
1812 | Portland, Oregon/Westside-Hillsboro Corridor | Portland | _ | Oregon | _ | Light Rail | Expansition of existing system | 17.7 | New Starts | FFGA Awarded | 1996 | 1998 | 963.52 | 630.06 | 74 | Annual report on funding recommendations | 1999 | Amended FFGA
1812 | Portland, Oregon/Westside-Hillsboro Corridor | Portland | _ | Oregon | _ | Light Rail | Expansition of existing system | 17.7 | New Starts | Project opening | 1998 |  | 963.52 | 630.06 | 74 | Annual report on funding recommendations | 2000 | project opened within the budget
1813 | Westside Light Rail to 185th | Portland | _ | Oregon | _ | Light Rail | Introduction of new mode | 11.5 | New Starts | FFGA Awarded | 1992 |  | 688.00 | 515.00 | 13.5 | Annual report on funding recommendations | 1995 | The additional fundings come from redirection of other project's budget
| South Corridor I-205 / Portland Mall LRT | Portland | _ | Oregon | _ | Light Rail | Expansition of existing system | 8.3 | New Starts | Preliminary Engineering | 2004 |  |  |  |  | Annual report on funding recommendations | 2007
| South Corridor I-205 / Portland Mall LRT | Portland | _ | Oregon | _ | Light Rail | Expansition of existing system | 8.3 | New Starts | Final Design | 2005 |  | 557.4 | 334.4 | 80.1 | Annual report on funding recommendations | 2007
| South Corridor I-205 / Portland Mall LRT | Portland | _ | Oregon | _ | Light Rail | Expansition of existing system | 8.3 | New Starts | FFGA Awarded | 2007 | 2007 | 575.70 | 345.40 | 90.94 | Annual report on funding recommendations | 2010
| Portland-Milwaukie Light Rail Project | Portland |  | Oregon |  | Light Rail | Expansition of existing system |  | New Starts | Preliminary Engineering | 2009 | 2016 | 1,490.35 | 745.18 | 140.64 | Annual report on funding recommendations | 2013
| Portland-Milwaukie Light Rail Project | Portland |  | Oregon |  | Light Rail | Expansition of existing system |  | New Starts | Final Design | 2011 | 2016 | 1,490.35 | 745.18 | 140.64 | Annual report on funding recommendations | 2013
| Portland-Milwaukie Light Rail Project | Portland |  | Oregon |  | Light Rail | Expansition of existing system |  | New Starts | FFGA Awarded | 2012 | 2016 | 1490.35 | 745.18 | 140.65 | Annual report on funding recommendations | 2014
| Portland-Milwaukie Light Rail Project | Portland |  | Oregon |  | Light Rail | Expansition of existing system |  | New Starts | Final Design | 2014 | 2017 | 1490.35 | 745.18 | 140.65 | Annual report on funding recommendations | 2015
| Portland-Milwaukie Light Rail Project | Portland | Milwaukie | Oregon |  | Light Rail | Expansition of existing system |  | New Starts | Final Design | 2015 | 2016 | 1490.35 | 745.18 | 140.65 | Annual report on funding recommendations | 2016
| Portland-Milwaukie Light Rail Project | Portland | Milwaukie | Oregon |  | Light Rail | Expansition of existing system |  | New Starts | Project opening | 2015 |  | 1490.35 | 745.18 | 140.65 | Project Profile | 2018
| Portland-Milwaukie Light Rail Project | Portland | Milwaukie | Oregon |  | Light Rail | Expansition of existing system |  | New Starts | Final Design | 2011 | 2016 | 1490.35 | 745.18 | 140.65 | Project Profile | 2018
| Portland-Milwaukie Light Rail Project | Portland | Milwaukie | Oregon |  | Light Rail | Expansition of existing system |  | New Starts | Preliminary Engineering | 2009 | 2016 | 1490.35 | 745.18 | 140.65 | Project Profile | 2018
| Columbia River Crossing Project | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 2.9 | New Starts | Preliminary Engineering | 2009 | 2019 | 2796.91 | 850 | FHWA Interstate Maintenance, Corridors of the Future, National Highway System, and Surface Transportation Program Funds: 112.7 mn$ | Annual report on funding recommendations | 2014 | The project’s capital cost decreased from $3,507.87 million to $2,796.91 million per a local decision to implement the project in phases.
| Columbia River Crossing Project | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 2.9 | New Starts | Engineering | 2014 | 2019 | 2711.83 | 850 | FHWA Interstate Maintenance, Corridors of the Future, National Highway System, and Surface Transportation Program Funds: 84.23 mn$ | Annual report on funding recommendations | 2015 | The project scope was revised to eliminate the highway interchanges north of State Route 14 in Washington State. As a result, the project’s capital cost decreased from $2,796.91 million to $2,711.83 million.
| Powell-Division Transit and Development | Portland |  | Oregon |  |  |  |  | Small Starts | Project Development | [5 empty] | Annual report on funding recommendations | 2017
| TriMet Interstate MAX Light Rail | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 5.8 | New Starts | Final Design | 2000 |  |  |  |  | Annual report on funding recommendations
| TriMet Interstate MAX Light Rail | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 5.8 | New Starts | FFGA Awarded | 2000 | 2004 | 350 | 257.5 | 24 | Before and After Study | 2004
| TriMet Interstate MAX Light Rail | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 5.8 | New Starts | FFGA Awarded | 2004 |  |  |  |  | Before and After Study | 2008 | Amended FFGA
| TriMet Interstate MAX Light Rail | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 5.8 | New Starts | Preliminary Engineering | 1996 |  |  |  |  | Before and After Study | 2008
| TriMet Interstate MAX Light Rail | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 5.8 | New Starts | Project opening | 2004 |  |  |  |  | Before and After Study | 2008 | Opening was four months ahead of schedule
| TriMet Interstate MAX Light Rail | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 5.8 | New Starts | FFGA Awarded | 2000 | 2001 | 350 | 257.5 | 24 | Annual report on funding recommendations | 2002
| MAX Red Line Extension and Reliability Improvements | Portland |  | Oregon |  | Light Rail | Improvement of existing service | 7.8 | Small Starts | Project Development | 2019 | 2023 | 206.02 | 100.00 |  | Project Profile | 2019
| Westside Express Service Rail Project | Portland |  | Oregon |  | Commuter Rail | Introduction of new mode |  |  | Preliminary Engineering | 2001 |  | 84.8 |  |  | Before and After Study | 2013
| Westside Express Service Rail Project | Portland |  | Oregon |  | Commuter Rail | Introduction of new mode |  |  | Final Design | 2004 |  | 103.5 |  |  | Before and After Study | 2013
| Westside Express Service Rail Project | Portland |  | Oregon |  | Commuter Rail | Introduction of new mode |  |  | FFGA Awarded | 2006 |  | 117.3 |  |  | Before and After Study | 2013
| Westside Express Service Rail Project | Portland |  | Oregon |  | Commuter Rail | Introduction of new mode |  |  | FFGA Awarded | 2008 |  |  |  |  | Before and After Study | 2013 | Amended FFGA
| Green Line Light Rail Project | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 14.5 |  | Preliminary Engineering | 2004 |  | 495.36 |  |  | Before and After Study | 2014 | The actual capital cost was $576 million in year-of-expenditure (YOE) dollars. -14% at PE
| Green Line Light Rail Project | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 14.5 |  | Final Design | 2005 |  | 576 |  |  | Before and After Study | 2014
| Green Line Light Rail Project | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 14.5 |  | FFGA Awarded | 2007 |  | 576 |  |  | Before and After Study | 2014
| Green Line Light Rail Project | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 14.5 |  | Project opening | 2009 |  |  |  |  | Before and After Study | 2014
| Streetcar Loop Project | Portland |  | Oregon |  | Streetcar | Expansition of existing system | 3.3 |  | Project Development | 2007 |  | 151.9 |  |  | Before and After Study | 2016 | The actual cost of the project was $148.8 million in year-of-expenditure
| Streetcar Loop Project | Portland |  | Oregon |  | Streetcar | Expansition of existing system | 3.3 |  | SSGA | 2009 |  | 148.8 |  |  | Before and After Study | 2016
| Streetcar Loop Project | Portland |  | Oregon |  | Streetcar | Expansition of existing system | 3.3 |  | Project opening | 2012 |  |  |  |  | Before and After Study | 2016
| Westside Express Service Rail Project | Portland |  | Oregon |  | Commuter Rail | Introduction of new mode |  |  | Project opening | 2009 |  |  |  |  | Before and After Study | 2013
| Southwest Corridor Light Rail Transit Project | Portland |  | Oregon |  | Light Rail | Expansition of existing system | 12 | New Starts | Project Development |  | 2027 |  |  |  | Project Profile | 2019
| Pioneer Parkway EmX BRT | Springfield | _ | Oregon | _ | Bus Rapid Transit | Expansition of existing system | 7.8 | Small Starts | PCGA Awarded | 2008 |  | 41.29 | 32.54 | 0.49 | Annual report on funding recommendations | 2010
| West Eugene EmX Extension | Eugene |  | Oregon |  | Bus Rapid Transit | Expansition of existing system | 8.9 | Small Starts | Project Development | 2012 | 2017 | 95.57 | 74.99 |  | Annual report on funding recommendations | 2014
| West Eugene EmX Extension | Eugene |  | Oregon |  | Bus Rapid Transit | Expansition of existing system | 8.9 | Small Starts | Project Development | 2012 | 2017 | 95.57 | 74.99 |  | Annual report on funding recommendations | 2015
| West Eugene EmX Extension | Eugene |  | Oregon |  | Bus Rapid Transit | Expansition of existing system | 9.2 | Small Starts | Project Development | 2012 | 2017 | 96.73 | 74.99 | Section 5307 Formula Funds: 1.07 mn | Annual report on funding recommendations | 2016
| West Eugene EmX Extension | Eugene |  | Oregon |  |  | Expansition of existing system |  | Small Starts | CGA | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| Wilsonville to Beaverton commuter rail | Washington county |  | Oregon |  | Commuter Rail | Improvement of existing service | 15.3 | New Starts | Preliminary Engineering | 2000 |  | 82.8 | 24.9 |  | Annual report on funding recommendations | 2002
| Wilsonville to Beaverton commuter rail | Washington county |  | Oregon |  | Commuter Rail | Improvement of existing service | 15 | New Starts | Preliminary Engineering | 2000 |  | 82.8 | 24.9 |  | Annual report on funding recommendations | 2003
| Wilsonville to Beaverton commuter rail | Washington county |  | Oregon |  | Commuter Rail | Improvement of existing service | 14.7 | New Starts | Preliminary Engineering | 2000 |  | 120 | 72 |  | Annual report on funding recommendations | 2004
| Wilsonville to Beaverton commuter rail | Washington county |  | Oregon |  | Commuter Rail | Improvement of existing service | 14.7 | New Starts | Preliminary Engineering | 2000 |  | 123.5 | 61.8 |  | Annual report on funding recommendations | 2005
| Wilsonville to Beaverton commuter rail | Washington county |  | Oregon |  | Commuter Rail | Improvement of existing service | 14.7 | New Starts | final Design | 2002 |  | 117.3 | 58.7 | 10.3 | Annual report on funding recommendations | 2007
1911 | Cleveland (Euclid Corridor) | Cleveland | _ | Ohio | _ | Bus Rapid Transit | Improvement of existing service | 9.8 | New Starts | Preliminary Engineering |  |  | 228.6 | 135 |  | Annual report on funding recommendations | 2002
1911 | Cleveland (Euclid Corridor) | Cleveland | _ | Ohio | _ | Bus Rapid Transit | Improvement of existing service | 9.8 | New Starts | Preliminary Engineering |  |  | 228.6 | 135 |  | Annual report on funding recommendations | 2003
1911 | Cleveland (Euclid Corridor) | Cleveland | _ | Ohio | _ | Bus Rapid Transit | Improvement of existing service | 9.8 | New Starts | Final Design | 2002 |  | 245.7 | 122.8 |  | Annual report on funding recommendations | 2004
1911 | Cleveland (Euclid Corridor) | Cleveland | _ | Ohio | _ | Bus Rapid Transit | Improvement of existing service | 9 | New Starts | Final Design | 2002 |  | 168.4 | 82.2 |  | Annual report on funding recommendations | 2005
1911 | Cleveland (Euclid Corridor) | Cleveland | _ | Ohio | _ | Bus Rapid Transit | Improvement of existing service | 5.6 | New Starts |  |  |  | 210.00 | 168.00 |  | Annual report on funding recommendations | 1998
1911 | Cleveland (Euclid Corridor) | Cleveland | _ | Ohio | _ | Bus Rapid Transit | Improvement of existing service | 5.6 | New Starts |  |  |  | 327.00 | 262.00 |  | Annual report on funding recommendations | 2000
1911 | Cleveland (Euclid Corridor) | Cleveland | _ | Ohio | _ | Bus Rapid Transit | Improvement of existing service | 7.1 | New Starts | Preliminary Engineering | 1996 |  | 168.4 | 82.2 | 60 | Before and After Study | 2007
1911 | Cleveland (Euclid Corridor) | Cleveland | _ | Ohio | _ | Bus Rapid Transit | Improvement of existing service | 7.1 | New Starts | Preliminary Engineering | 1997 |  |  |  |  | Before and After Study | 2012
1911 | Cleveland (Euclid Corridor) | Cleveland | _ | Ohio | _ | Bus Rapid Transit | Improvement of existing service | 7.1 | New Starts | Final Design | 2002 |  |  |  |  | Before and After Study | 2012
1911 | Cleveland (Euclid Corridor) | Cleveland | _ | Ohio | _ | Bus Rapid Transit | Improvement of existing service | 7.1 | New Starts | FFGA Awarded | 2004 |  |  |  |  | Before and After Study | 2012
1911 | Cleveland (Euclid Corridor) | Cleveland | _ | Ohio | _ | Bus Rapid Transit | Improvement of existing service | 7.1 | New Starts | Project opening | 2008 |  |  |  |  | Before and After Study | 2012
1921 | Interstate 71 corridor (MOS-1) | Cincinatti | _ | Ohio | _ | Light Rail | Introduction of new mode | 19 | New Starts | Preliminary Engineering | 1998 | 2001 | 874.7 | 431.2 |  | Annual report on funding recommendations | 2002
1921 | Interstate 71 corridor (MOS-1) | Cincinatti | _ | Ohio | _ | Light Rail | Introduction of new mode | 19.5 | New Starts | Preliminary Engineering | 1998 |  | 899.9 | 449.9 |  | Annual report on funding recommendations | 2004
| Northeast Corridor BRT Project | Columbus |  | Ohio |  | Bus Rapid Transit | Improvement of existing service | 15.6 | Small Starts | Project Development | 2013 | 2016 | 39.43 | 31.54 |  | Annual report on funding recommendations | 2014
| Northeast Corridor BRT Project | Columbus |  | Ohio |  | Bus Rapid Transit | Improvement of existing service | 15.6 | Small Starts | Project Development | 2013 | 2017 | 39.43 | 31.54 |  | Annual report on funding recommendations | 2015
| Northeast Corridor LRT | Columbus |  | Ohio |  | Light Rail | Introduction of new mode | 13 |  | Preliminary Engineering | 2001 |  | 501.8 | 250.9 |  | Annual report on funding recommendations | 2003
| Northeast Corridor LRT | Columbus |  | Ohio |  | Light Rail | Introduction of new mode | 13 |  | Preliminary Engineering | 2001 |  | 528.7 | 264.4 |  | Annual report on funding recommendations | 2005
| Cleveland Avenue Bus Rapid Transit | Columbus |  | Ohio |  | Bus Rapid Transit | Improvement of existing service | 15.6 | Small Starts | Project Development | 2013 | 2017 | 47.67 | 38.13 |  | Annual report on funding recommendations | 2016 | capital cost increased from $39.43 million to $47.67 million as a result of further engineering and design and a one-year delay in completing the project relative to COTA’s anticipated schedule at that time.
| Cleveland Avenue Bus Rapid Transit | Columbus |  | Ohio |  | Bus Rapid Transit |  |  | Small Starts | CGA | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
2011 | Craig, Alaska (Alaska-Hollis Ketchikan Ferry) | Craig | _ | Alaska | _ |  | Introduction of new mode | _ | New Starts |  |  |  | 10.70 | 6.35 |  | Annual report on funding recommendations | 1998 | a new passenger terminal at Hollis and a new 196 foot shelter deck ferry vessel
| Alaska Rail Road- South Wasilla Track Realignment | Wasilla |  | Alaska |  |  | Improvement of existing service | [5 empty] | 25.3 | 23.1 |  | Annual report on funding recommendations | 2005
| South Anchorage Double Track | Girdwood |  | Alaska |  | commuter Rail | Improvement of existing service | 5 | New Starts | Preliminary Engineering | 2000 |  |  |  |  | Annual report on funding recommendations | 2004
| South Anchorage Double Track | Girdwood |  | Alaska |  | commuter Rail | Improvement of existing service | 5 | New Starts | Final Design | 2001 |  | 7 | 5.6 |  | Annual report on funding recommendations | 2004
| Eagle river to Knik river | Girdwood |  | Alaska |  | commuter Rail | Improvement of existing service | 12.5 | New Starts | Preliminary Engineering | 2000 |  |  |  |  | Annual report on funding recommendations | 2004
| Eagle river to Knik river | Girdwood |  | Alaska |  | commuter Rail | Improvement of existing service | 12.5 | New Starts | Final Design | 2001 |  | 12.5 | 10 |  | Annual report on funding recommendations | 2004
| Knik River to Wasilla | Girdwood |  | Alaska |  | commuter Rail | Improvement of existing service | 11.3 | New Starts | Preliminary Engineering | 2000 |  |  |  |  | Annual report on funding recommendations | 2004
| Knik River to Wasilla | Girdwood |  | Alaska |  | commuter Rail | Improvement of existing service | 11.3 | New Starts | Final Design | 2001 |  | 11.3 | 9 |  | Annual report on funding recommendations | 2003
| Alaska Railroad Commuter Rail | Girdwood |  | Alaska |  | commuter Rail | Improvement of existing service | 71 | New Starts | Preliminary Engineering | 2000 |  | 69.6 | 15 |  | Annual report on funding recommendations | 2002
| Alaska Marine Highway System | Prince William Sound |  | Alaska |  |  | Improvement of existing service |  |  | Preliminary Engineering | 2001 |  | 38.5 | 24.9 |  | Annual report on funding recommendations | 2004 | 4 fast Ferries
| Alaska Marine Highway System | Prince William Sound |  | Alaska |  |  | Improvement of existing service |  |  | Final Design | 2001 |  | 38.5 | 24.9 |  | Annual report on funding recommendations | 2004 | Ferry
| Alaska Marine Highway System | Prince William Sound |  | Alaska |  |  | Improvement of existing service |  |  | Final Design | 2001 |  | 38.5 | 24.9 | 5.8 | Annual report on funding recommendations | 2003 | Ferry
2111 | Norfolk -Virginia Beach Corridor (First phase) | Norfolk | _ | Virginia | _ | Light Rail | Introduction of new mode | 18.3 | New Starts | Preliminary Engineering | 1997 |  | 524.60 | 288.60 |  | Annual report on funding recommendations | 2000
| Norfolk LRT | Norfolk | _ | Virginia | _ | Light Rail | Expansition of existing system | 7.4 | New Starts | FFGA Awarded | 2007 |  | 232.10 | 127.98 | 39.2 | Annual report on funding recommendations | 2010
| Norfolk LRT | Norfolk | _ | Virginia | _ | Light Rail | Expansition of existing system | 7.4 | New Starts | Preliminary Engineering | 2002 |  | 203.7 | 99.8 | 36.5 | Annual report on funding recommendations | 2007 | Abridged project
| Norfolk LRT | Norfolk | _ | Virginia | _ | Light Rail | Expansition of existing system | 8 | New Starts | Preliminary Engineering | 2002 | 2007 | 222 | 111 |  | Annual report on funding recommendations | 2004 | Abridged project
| The Tide Light Rail Project | Norfolk | _ | Virginia | _ | Light Rail | Expansition of existing system | 7.4 | New Starts | Preliminary Engineering | 2002 |  | 194.6 |  |  | Before and After Study | 2015 | The actual cost of the project was $314.6 million in year-of-expenditure (YOE)
| The Tide Light Rail Project | Norfolk | _ | Virginia | _ | Light Rail | Expansition of existing system | 7.4 | New Starts | Final Design | 2006 |  | 235.6 |  |  | Before and After Study | 2015
| The Tide Light Rail Project | Norfolk | _ | Virginia | _ | Light Rail | Expansition of existing system | 7.4 | New Starts | FFGA Awarded | 2007 |  | 231.6 |  |  | Before and After Study | 2015
| The Tide Light Rail Project | Norfolk | _ | Virginia | _ | Light Rail | Expansition of existing system | 7.4 | New Starts | Project opening | 2011 |  |  |  |  | Before and After Study | 2015
| West End Transitway | Alexandria |  | Virginia |  | Bus Rapid Transit | Introduction of new mode |  | Small Starts | Project Development | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| West End Transitway | Alexandria |  | Virginia |  | Bus Rapid Transit | Introduction of new mode | 5.3 | Small Starts | Project Development | 2016 | 2021 |  |  |  | Project Profile | 2018
| Richmond Highway BRT Project | Fairfax County |  | Virginia |  | Bus Rapid Transit | Introduction of new mode | 7.4 | New Starts | Project Development |  | 2028 |  |  |  | Project Profile | 2020
2211 | Seattle-Tacoma Sounder Commuter Rail | Seattle | _ | Washington | _ | Commuter Rail | Introduction of new mode | 40 | New Starts | Preliminary Engineering | 1998 |  | 401.0 | 100.0 |  | Annual report on funding recommendations | 2000
| Central Link Initial Segment (Initial MOS-1) | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 7.2 | New Starts | FFGA Awarded | 2001 |  | 2228 | 500 |  | Annual report on funding recommendations | 2003
| Central Link Initial Segment (Initial MOS-1) | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 7.2 | New Starts | FFGA Awarded | 2001 |  | 2603 | 500 |  | Annual report on funding recommendations | 2002
| Central Link Initial Segment (Initial MOS-2 and 3) | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 16.3 | New Starts | final Design | 2000 | 2009 | 1503 | 931.4 |  | Annual report on funding recommendations | 2002
| Central Link Initial Segment (Initial) | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 13.9 | New Starts | Preliminary Engineering | 1997 |  |  |  |  | Annual report on funding recommendations | 2004
| Central Link Initial Segment (Initial) | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 13.9 | New Starts | Final Design | 2000 |  |  |  |  | Annual report on funding recommendations | 2004
| Central Link Initial Segment (Initial) | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 13.9 | New Starts | Final Design | 2002 |  | 2,491.6 | 500 |  | Annual report on funding recommendations | 2004
| Central Link Initial Segment (Initial) | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 13.9 | New Starts | FFGA Awarded | 2003 |  | 2,436.90 | 500.00 |  | Annual report on funding recommendations | 2005
| Central Link Initial Segment (Initial) | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 13.9 | New Starts | FFGA Awarded | 2001 |  | 2,436.90 | 500.00 |  | Annual report on funding recommendations | 2010
| Central Link Initial Segment (Initial) | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 13.9 | New Starts | FFGA Awarded | 2003 |  | 2,436.90 | 500.00 |  | Annual report on funding recommendations | 2010 | In April 2001, the Secretary of Transportation put the project on hold until significant concerns raised by the Office of the Inspector General were resolved.
| Central Link Initial Segment | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 15.6 | New Starts | Preliminary Engineering | 1999 | 2006 |  |  |  | before and After Study | 2013
| Central Link Initial Segment | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 15.6 | New Starts | Final Design | 2000 |  |  |  |  | before and After Study | 2013
| Central Link Initial Segment | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 15.6 | New Starts | FFGA Awarded | 2008 |  |  |  |  | before and After Study | 2013
| Central Link Initial Segment | Seattle | _ | Washington | _ | Light Rail | Introduction of new mode | 15.6 | New Starts | Project opening | 2009 |  |  |  |  | before and After Study | 2013
| Roosevelt RapidRide BRT | Seattle | _ | Washington | _ | Bus Rapid Transit |  |  | Small Starts | Project development | 2017 |  | 77.2 | 38.6 |  | Annual report on funding recommendations | 2019
| University Link LRT Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 3.1 | New Starts | FFGA Awarded | 2001 |  | 1,947.68 | 813.00 | 12 | Annual report on funding recommendations | 2010 | the FFGA of 2001 was suspended later that year due to cost increases.
| University Link LRT Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 3.1 | New Starts | FFGA Awarded | 2009 |  | 1,947.68 | 813.00 | 12 | Annual report on funding recommendations | 2011
| University Link LRT Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 3.1 | New Starts | Final Design | 2006 |  | 1,947.68 | 813.00 | 12 | Annual report on funding recommendations | 2011
| University Link LRT Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 3.1 | New Starts | Preliminary Engineering | 2005 |  | 1,720.0 | 700 |  | Annual report on funding recommendations | 2007
| University Link LRT Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 3.1 | New Starts | FFGA Awarded | 2009 | 2017 | 1947.68 | 813 | 12 | Annual report on funding recommendations | 2014
| University Link LRT Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 3.1 | New Starts | FFGA Awarded | 2009 | 2017 | 1947.68 | 813 | 12 | Annual report on funding recommendations | 2015
| Lynnwood Link Extension | Seattle | Lynwood, Mountlake Terrace | Washington |  | Light Rail | Expansition of existing system | 8.5 |  | Project Development | 2013 | 2023 | 1200 - 1700 mn (under consideration) | 50% share |  | Annual report on funding recommendations | 2015
| Lynnwood Link Extension | Seattle | Lynwood, Mountlake Terrace | Washington |  | Light Rail | Expansition of existing system | 8.5 | New Starts | Project Development | 2013 | 2023 | 1200 - 1700 mn (under consideration) | 50% share |  | Annual report on funding recommendations | 2016
| Center City Connector Streetcar | Seattle |  | Washington |  | Streetcar | Expansition of existing system | 1.3 | Small Starts | Project Development | 2014 | 2026 | 285.51 | 74.99 |  | Project Profile | 2019
| Center City Connector Streetcar | Seattle |  | Washington |  | Streetcar | Introduction of new mode | 1.2 | Small Starts | Project Development | 2015 | 2018 | 110 | 55 - 75 |  | Annual report on funding recommendations | 2016
| Sound Transit-Federal Way Link Extension | Seattle |  | Washington |  |  | Expansition of existing system |  | Small Starts | Project Development | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Madison Street Corridor BRT | Seattle |  | Washington |  | Bus Rapid Transit | Introduction of new mode | 2.3 | Small Starts | Project Development | 2016 | 2022 | 121.18 | 59.90 | 9.66 | Project Profile | 2019
| Madison Street Corridor BRT | Seattle |  | Washington |  | Bus Rapid Transit |  |  | Small Starts | Project Development | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Lynwood Link Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 8.5 | New Starts | FFGA Awarded | 2018 | 2024 | 3,260.35 | 1,172.73 |  | Project Profile | 2020
| Lynwood Link Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 8.5 | New Starts | Engineering | 2016 | 2024 | 3,260.35 | 1,172.73 |  | Project Profile | 2020
| Lynwood Link Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 8.5 | New Starts | Project Development | 2013 | 2024 | 3,260.35 | 1,172.73 |  | Project Profile | 2020
| Lynwood Link Extension | Seattle |  | Washington |  |  |  |  | New Starts | Engineering | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| Link extension and North Link | Seattle |  | Washington |  | Light Rail |  | 24 | New Starts | Preliminary Engineering | [5 empty] | Annual report on funding recommendations | 2003
| Airport Link | Seattle |  | Washington |  | Light Rail | Introduction of new mode | 24 | New Starts | Preliminary Engineering | 1997 |  |  |  |  | Annual report on funding recommendations | 2004
| North Link | Seattle |  | Washington |  | Light Rail | Introduction of new mode | 24 | New Starts | Preliminary Engineering | 1997 |  |  |  |  | Annual report on funding recommendations | 2004
| Everett to Seattle | Seattle |  | Washington |  | Commuter Rail | Introduction of new mode | 35 | New Starts | Preliminary Engineering |  |  | 104 | 24.9 |  | Annual report on funding recommendations | 2004
| Federal Way Link Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 7.8 | New Starts | FFGA Awarded | 2020 |  | 3.161 | 790 | 18 | Project Profile | 2020
| Federal Way Link Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 7.8 | New Starts | Engineering | 2019 |  | 3.161 | 790 | 18 | Project Profile | 2020
| Federal Way Link Extension | Seattle |  | Washington |  | Light Rail | Expansition of existing system | 7.8 | New Starts | Project Development | 2016 |  | 3.161 | 790 | 18 | Project Profile | 2020
| RapidRide I | Seattle |  | Washington |  | Bus Rapid Transit | Introduction of new mode | 17.9 | Small Starts |  |  | 2023 | 117-140 |  |  | Project Profile | 2019
| RapidRide K | Seattle |  | Washington |  | Bus Rapid Transit | Introduction of new mode | 15.7 | Small Starts |  |  | 2023 | 89.8 |  |  | Project Profile | 2019
| RapidRide Roosevelt Project | Seattle |  | Washington |  | Bus Rapid Transit | Introduction of new mode | 6.1 | Small Starts | Project Development | 2017 | 2024 | 90.21 | 45 | 5.43 | Project Profile | 2019
| Mill Plain Bus Rapid Transit | Vancouver |  | Washington |  | Bus Rapid Transit | Introduction of new mode | 10 | Small Starts | Project Development | 2019 | 2022 | 49.86 | 24.88 | 4.2 | Project Profile | 2019
| Fourth Plain Bus Rapid Transit | Vancouver |  | Washington |  | Bus Rapid Transit | Introduction of new mode | 6.6 | Small Starts | Project Development | 2013 | 2015 | 49.3 | 39.44 |  | Annual report on funding recommendations | 2014
| Fourth Plain Bus Rapid Transit | Vancouver |  | Washington |  | Bus Rapid Transit | Introduction of new mode | 6 | Small Starts | Project Development | 2013 | 2016 | 53.4 | 38.72 | FHWA Flexible Funds (Congestion Mitigation and Air Quality Funds): 4mn | Annual report on funding recommendations | 2015
| Fourth Plain Bus Rapid Transit | Vancouver |  | Washington |  | Bus Rapid Transit | Introduction of new mode | 5.9 | Small Starts | Project Development | 2013 | 2016 | 53.4 | 38.4 | FHWA Flexible Funds (Congestion Mitigation and Air Quality Funds): 4mn | Annual report on funding recommendations | 2016
| Fourth Plain BRT | Vancouver |  | Washington |  | Bus Rapid Transit |  |  | Small Starts | CGA | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| Columbia River Crossing Project | Vancouver |  | Washington |  | Light Rail | Expansition of existing system | 2.9 | New Starts | Preliminary Engineering | 2009 | 2019 | 3,507.87 | 850.00 |  | Annual report on funding recommendations | 2013
| Swift II | Everett |  | Washington |  | Bus Rapid Transit | Expansition of existing system | 12 | Small Starts | Project Development | 2015 | 2018 | 48 | 38 |  | Annual report on funding recommendations | 2016
| Swift II | Everett |  | Washington |  | Bus Rapid Transit | Expansition of existing system | 11.3 | Small Starts | Project Development | 2018 | 2024 | 41.65 | 17 | 84.16 | Project Profile | 2019
| Tacoma Link Light Rail Expansion | Tacoma |  | Washington |  | Light Rail | Expansition of existing system | 2.4 | Small Starts | Project Development | 2014 | 2021 | 166.01 | 74.99 | 11.6 | Annual report on funding recommendations | 2016
| Lakewood to Tacoma Commuter Rail | Tacoma |  | Washington |  | Commuter Rail | Introduction of new mode | 8 | Small Starts | Final Design | 2001 | 2004 | 86 | 24.9 |  | Annual report on funding recommendations | 2004
| Lakewood to Tacoma Commuter Rail | Tacoma |  | Washington |  | Commuter Rail | Introduction of new mode | 8 | Small Starts | Final Design | 2001 | 2001 | 86 | 24.9 |  | Annual report on funding recommendations | 2002
| Pacific Avenue/SR 7 Corridor | Tacoma |  | Washington |  | Bus Rapid Transit | Introduction of new mode | 14.3 | Small Starts |  |  | 2023 | 150 | 59.87 | 8.74 | Project Profile | 2019
| Central City Line | Spokane |  | Washington |  |  |  |  | Small Starts | Project Development | 2015 |  | 72 |  |  | Annual report on funding recommendations | 2017
2312 | North central corridor | Chicago | _ | Illinois | _ | Commuter Rail | Expansition of existing system | 16.3 | New Starts | FFGA Awarded | 2001 | 2006 | 225.52 | 135.32 | 23.8 | Annual report on funding recommendations | 2005
2312 | North central corridor | Chicago | _ | Illinois | _ | Commuter Rail | Expansition of existing system | 16.3 | New Starts | Preliminary Engineering | 1998 |  |  |  |  | Annual report on funding recommendations | 2005
2312 | North central corridor | Chicago | _ | Illinois | _ | Commuter Rail | Expansition of existing system | 16 | New Starts | Final Design | 2000 |  | 236.4 | 144.7 | 8.2 | Annual report on funding recommendations | 2002
2312 | North central corridor | Chicago | _ | Illinois | _ | Commuter Rail | Expansition of existing system | 12 | New Starts | Preliminary Engineering | 1998 |  | 177.90 | 110.90 |  | Annual report on funding recommendations | 2001
2313 | South west corridor | Chicago | _ | Illinois | _ | Commuter Rail | Expansition of existing system | 11 | New Starts | Preliminary Engineering | 1998 |  | 177.40 | 111.80 |  | Annual report on funding recommendations | 2000
2313 | South west corridor | Chicago | _ | Illinois | _ | Commuter Rail | Expansition of existing system | 11 | New Starts | Preliminary Engineering | 1998 |  | 165.50 | 103.90 |  | Annual report on funding recommendations | 2001
2313 | South west corridor | Chicago | _ | Illinois | _ | Commuter Rail | Expansition of existing system | 11 | New Starts | Preliminary Engineering | 1998 |  | 218.7 | 37 | 91.1 | Annual report on funding recommendations | 2002
2313 | South west corridor | Chicago | _ | Illinois | _ | Commuter Rail | Expansition of existing system | 12 | New Starts | Final Design | 2001 |  |  |  |  | Annual report on funding recommendations | 2005
2313 | South west corridor | Chicago | _ | Illinois | _ | Commuter Rail | Expansition of existing system | 12 | New Starts | FFGA Awarded | 2001 |  | 198.12 | 103.02 | 34.3 | Annual report on funding recommendations | 2005
2314 | Central area circulator | Chicago | _ | Illinois | _ | Light Rail | Introduction of new mode |  | New Starts | FFGA Awarded | 1994 |  | 775.00 | 258.30 | 258.30 | Annual report on funding recommendations | 1996
| Ravenswood Line Extension | Chicago | _ | Illinois | _ | Heavy Rail | Improvement of existing service | 9.3 | New Starts | Final Design |  |  | 327.00 | 245.5 | 14 | Annual report on funding recommendations | 2001
| Ravenswood Line Extension | Chicago | _ | Illinois | _ | Heavy Rail | Improvement of existing service | 9.3 | New Starts | Preliminary Engineering |  |  | 327 | 245.5 | 13.2 | Annual report on funding recommendations | 2002
| Ravenswood Line Extension | Chicago | _ | Illinois | _ | Heavy Rail | Improvement of existing service | 9.3 | New Starts | Preliminary Engineering |  |  | 476 | 245.5 | 134.8 | Annual report on funding recommendations | 2003
| Ravenswood Line Extension | Chicago | _ | Illinois | _ | Heavy Rail | Improvement of existing service | 9.3 | New Starts | Final Design | 2002 |  | 529.9 | 245.5 | 177.6 | Annual report on funding recommendations | 2004
| Ravenswood Line Extension | Chicago | _ | Illinois | _ | Heavy Rail | Improvement of existing service | 9.1 | New Starts | FFGA Awarded | 2004 |  | 529.91 | 245.52 | 177.56 | Annual report on funding recommendations | 2010
| Ashland Avenue BRT Phase I Project | Chicago |  | Illinois |  | Bus Rapid Transit | Introduction of new mode | 5.4 | Small Starts | Project Development | 2013 | Not given | 116.9 | 58.3 |  | Annual report on funding recommendations | 2015 | CTA anticipates completing the environmental review process with receipt of a Finding of No Significant Impact in early 2014, and receipt of a Small Starts Grant Agreement in late 2015.
| Ashland Avenue BRT Phase I Project | Chicago |  | Illinois |  | Bus Rapid Transit | Improvement of existing service | 5.4 | Small Starts | Project Development | 2014 | Not given | 116.9 | 58.3 |  | Annual report on funding recommendations | 2016
| Red and Purple Line Modernization Project | Chicago |  | Illinois |  | Heavy Rail | Improvement of existing service | 9.6 | Core Capacity | Project Development | 2014 | Not given | 4700 | 1500 |  | Annual report on funding recommendations | 2015 | Milestone: As of early 2014, CTA is considering undertaking the project in phases. FTA will work with CTA to establish a schedule for completing NEPA and advancing the project toward a Core Capacity Full Funding Grant Agreement
| Red and Purple Line Modernization Project – Phase One | Chicago |  | Illinois |  | Heavy Rail | Improvement of existing service | 9.6 | Core Capacity | Project Development | 2013 | Not given | 1700 |  |  | Annual report on funding recommendations | 2016 | In spring 2014, CTA announced its intention to undertake the project in phases.
| Red and Purple Line Modernization Project – Phase One | Chicago |  | Illinois |  |  |  |  | Core Capacity | Engineering | 2015 |  | 1,993 | 956 |  | Annual report on funding recommendations | 2017
| Red and Purple Modernization Phase One Project | Chicago |  | Illinois |  |  |  |  | Core Capacity | CGA | 2017 |  |  |  |  | Annual report on funding recommendations | 2018
| Red and Purple Modernization Phase One Project | Chicago |  | Illinois |  | Heavy Rail | Expansition of existing system | 5.6 | Core Capacity | Project Development | 2013 |  | 2,066.70 | 956.61 | 115.73 | Project Profile | 2020
| Red and Purple Modernization Phase One Project | Chicago |  | Illinois |  | Heavy Rail | Expansition of existing system | 5.6 | Core Capacity | Engineering | 2015 |  | 2,066.70 | 956.61 | 115.73 | Project Profile | 2020
| Red and Purple Modernization Phase One Project | Chicago |  | Illinois |  | Heavy Rail | Expansition of existing system | 5.6 | Core Capacity | FFGA Awarded | 2017 |  | 2,066.70 | 956.61 | 115.73 | Project Profile | 2020
| Douglas Branch Reconstrution | Chicago |  | Illinois |  | Heavy Rail | Improvement of existing service | 6.6 | New Starts | Preliminary Engineering | 1999 |  |  |  |  | Annual report on funding recommendations | 2007
| Douglas Branch Reconstrution | Chicago |  | Illinois |  | Heavy Rail | Improvement of existing service | 6.6 | New Starts |  |  |  | 450.80 | 320.10 | 28.80 | Annual report on funding recommendations | 2001
| Douglas Branch Reconstrution | Chicago |  | Illinois |  | Heavy Rail | Improvement of existing service | 6.6 | New Starts | Final Design | 2001 |  |  |  |  | Annual report on funding recommendations | 2007
| Douglas Branch Reconstrution | Chicago |  | Illinois |  | Heavy Rail | Improvement of existing service | 6.6 | New Starts | FFGA Awarded | 2001 | 2005 | 482.5 | 320.10 | 63.68 | Annual report on funding recommendations | 2004
| Douglas Branch Reconstrution | Chicago |  | Illinois |  | Heavy Rail | Improvement of existing service | 6.6 | New Starts | Project opening | 2005 |  | 482.68 | 320.10 |  | Annual report on funding recommendations | 2007
| Union-Pacific West Line Extension | Chicago |  | Illinois |  | Commuter Rail | Expansition of existing system | 8 | New Starts | Preliminary Engineering | 1998 |  | 142.08 | 87.44 |  | Annual report on funding recommendations | 2002
| Union-Pacific West Line Extension | Chicago |  | Illinois |  | Commuter Rail | Expansition of existing system | 8.5 | New Starts | Preliminary Engineering | 1998 |  |  |  |  | Annual report on funding recommendations | 2005
| Union-Pacific West Line Extension | Chicago |  | Illinois |  | Commuter Rail | Expansition of existing system | 8.5 | New Starts | Final Design | 2001 | 2006 | 134.56 | 80.76 | 12.90 | Annual report on funding recommendations | 2007
| Union-Pacific West Line Extension | Chicago |  | Illinois |  | Commuter Rail | Expansition of existing system | 8.5 | New Starts | FFGA Awarded | 2001 | 2006 | 134.56 | 80.76 | 12.90 | Annual report on funding recommendations | 2007
| Chicago, Illinois/Central Kane Corridor Commuter Rail | Chicago |  | Illinois |  | Commuter Rail | Expansition of existing system | 8 | New Starts | Preliminary Engineering | 1998 |  | 93 | 54.30 |  | Annual report on funding recommendations | 2001
2411 | Little Rock River Rail Project | Little Rock | _ | Arkansas | _ | Streetcar | Introduction of new mode | 1.9 | New Starts | Preliminary Engineering | 1999 |  | 8.28 | 6.62 |  | Annual report on funding recommendations | 2000
2411 | Little Rock River Rail Project | Little Rock | _ | Arkansas | _ | Streetcar | Introduction of new mode | 2.6 | New Starts | Final Design | 1999 |  | 15.1 | 8.6 | 3.9 | Annual report on funding recommendations | 2004
2411 | Little Rock River Rail Project | Little Rock | _ | Arkansas | _ | Streetcar | Introduction of new mode | 2.1 | New Starts | Preliminary Engineering | 1998 | 2002 | 13.2 | 8.6 | 2 | Annual report on funding recommendations | 2002
2411 | Little Rock River Rail Project | Little Rock | _ | Arkansas | _ | Streetcar | Introduction of new mode | 2.1 | New Starts | Final Design | 1999 | 2002 | 13.2 | 8.6 | 2 | Annual report on funding recommendations | 2002
2411 | Little Rock River Rail Project | Little Rock | _ | Arkansas | _ | Streetcar | Introduction of new mode | 2.5 | New Starts | Final Design | 1999 |  | 13.2 | 8.6 | 2 | Annual report on funding recommendations | 2001
| Central Phoenix/East Valley Light Rail | Pheonix | Tempe and Mesa | Arizona |  | Light Rail | Introduction of new mode | 20.3 | New Starts | Preliminary Engineering | 1998 |  | 1076 | 533.4 | 7.6 | Annual report on funding recommendations | 2002
| Central Phoenix/East Valley Light Rail | Pheonix | Tempe and Mesa | Arizona |  | Light Rail | Introduction of new mode | 25 | New Starts | Preliminary Engineering | 1998 |  | 1181 | 590.7 | 17.4 | Annual report on funding recommendations | 2003
| Central Phoenix/East Valley Light Rail | Pheonix | Tempe and Mesa | Arizona |  | Light Rail | Introduction of new mode | 20.3 | New Starts | Preliminary Engineering | 1998 |  | 1183.5 | 591.7 | 19.1 | Annual report on funding recommendations | 2004
| Central Phoenix/East Valley Light Rail | Pheonix | Tempe and Mesa | Arizona |  | Light Rail | Introduction of new mode | 20.3 | New Starts | Final Design | 2003 |  | 1376.8 | 587.20 | 19.2 | Annual report on funding recommendations | 2005
| Central Phoenix/East Valley Light Rail | Pheonix | Tempe and Mesa | Arizona |  | Light Rail | Introduction of new mode | 19.6 | New Starts | FFGA Awarded | 2005 |  | 1,412.12 | 587.20 | 59.75 | Annual report on funding recommendations | 2010
| Central Phoenix/East Valley Light Rail | Pheonix | Tempe and Mesa | Arizona |  | Light Rail | Introduction of new mode | 20.3 | New Starts | Preliminary Engineering | 1998 |  | 1.076 |  |  | Before and After Study | 2013
| Central Phoenix/East Valley Light Rail | Pheonix | Tempe and Mesa | Arizona |  | Light Rail | Introduction of new mode | 19.7 | New Starts | Final Design | 2003 |  | 1.181 |  |  | Before and After Study | 2013
| Central Phoenix/East Valley Light Rail | Pheonix | Tempe and Mesa | Arizona |  | Light Rail | Introduction of new mode | 19.7 | New Starts | FFGA Awarded | 2005 |  | 1.412 |  |  | Before and After Study | 2013
| Central Phoenix/East Valley Light Rail | Pheonix | Tempe and Mesa | Arizona |  | Light Rail | Introduction of new mode | 19.7 | New Starts | Project opening | 2008 |  |  |  |  | Before and After Study | 2013
| Central Phoenix Downtown Hub | Pheonix |  | Arizona |  | Light Rail | Expansition of existing system | 5.5 | New Starts | Project Development | 2015 | 2023 | 1,345.17 | 529.86 |  | Project Profile | 2019
| Central Phoenix Downtown Hub | Pheonix |  | Arizona |  | Light Rail | Expansition of existing system | 5.5 | New Starts | Engineering | 2019 | 2023 | 1,345.17 | 529.86 |  | Project Profile | 2019
| South Central LRT Extension | Pheonix |  | Arizona |  |  |  |  | New Starts | Project Development | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| Northwest Phase II LRT Extension | Pheonix |  | Arizona |  |  |  |  | New Starts | Project Development | 2017 |  | 318.7 | 156.1 |  | Annual report on funding recommendations | 2019
| Northwest Phase II LRT Extension | Pheonix |  | Arizona |  | Light Rail | expansition of existing system | 1.5 | New Starts | Project Development | 2017 |  | 401.33 | 198.26 |  | project Profile | 2019
| Modern Streetcar Project | Tucson |  | Arizona |  | Streetcar | Introduction of new mode | 3.9 | New Starts | Final Design | 2009 |  | 182.52 | 24.99 |  | Annual report on funding recommendations | 2011
| Modern Streetcar Project | Tucson |  | Arizona |  | Streetcar | Introduction of new mode | 3.9 | New Starts | Preliminary Engineering | 2008 |  | 182.52 | 24.99 |  | Annual report on funding recommendations | 2011
| Tempe Streetcar | Tempe |  | Arizona |  | Streetcar | Introduction of new mode | 2.7 | Small Starts | Project Development | 2013 | 2016 | 129.34 | 56 | FHWA Flexible Funds (Congestion Mitigation and Air Quality Funds): $32.10 mn | Annual report on funding recommendations | 2014
| Tempe Streetcar | Tempe |  | Arizona |  | Streetcar | Introduction of new mode | 2.7 | Small Starts | Project Development | 2013 | 2017 | 129.34 | 56 | FHWA Flexible Funds (Congestion Mitigation and Air Quality Funds): $32.10 mn | Annual report on funding recommendations | 2015
| Tempe Streetcar Project | Tempe |  | Arizona |  | Streetcar | Introduction of new mode | ~3 | Small Starts | Project Development | 2013 | 2017 | 129 | 56 |  | Annual report on funding recommendations | 2016
| Central Mesa Light Rail Transit Extension | Mesa | Phoenix | Arizona |  | Light Rail | Expansition of existing system | 3.1 | Small Starts | FFGA Awarded | 2012 | 2016 | 199.01 | 74.99 | FHWA Congestion Mitigation Air Quality (CMAQ): 52.84 mn | Annual report on funding recommendations | 2014
| Central Mesa Light Rail Transit Extension | Mesa | Phoenix | Arizona |  | Light Rail | Expansition of existing system | 3.1 | Small Starts | Project Development | 2010 |  | 198.5 |  |  | before and After Study | 2019 | The actual capital project cost was $196.7 million in year-of-expenditure (YOE)
| Central Mesa Light Rail Transit Extension | Mesa | Phoenix | Arizona |  | Light Rail | Expansition of existing system | 3.1 | Small Starts | PCGA | 2012 |  | 196.7 |  |  | before and After Study | 2019
| Central Mesa Light Rail Transit Extension | Mesa | Phoenix | Arizona |  | Light Rail | Expansition of existing system | 3.1 | Small Starts | Project opening | 2014 |  |  |  |  | before and After Study | 2019
| Transit Spine BRT | Flagstaff |  | Arizona |  | Bus Rapid Transit |  |  | Small Starts | Project Development | 2016 |  | 32.9 |  |  | Annual report on funding recommendations | 2018
| Transit Spine BRT | Flagstaff |  | Arizona |  | Bus Rapid Transit | Introduction of new mode | 13 | Small Starts | Project Development | 2016 | 2021 | 32.9 |  |  | Project Profile | 2018
| Mountain Link BRT Project | Flagstaff |  | Arizona |  | Bus Rapid Transit | Introduction of new mode | 4 | very Small Starts | Project Development | 2009 |  |  |  |  | before and After Study | 2014
| Mountain Link BRT Project | Flagstaff |  | Arizona |  | Bus Rapid Transit | Introduction of new mode | 4 | very Small Starts | SSGA | 2011 |  |  |  |  | before and After Study | 2014
| Mountain Link BRT Project | Flagstaff |  | Arizona |  | Bus Rapid Transit | Introduction of new mode | 4 | very Small Starts | Project opening | 2011 |  |  |  |  | before and After Study | 2014
| Northstar Corridor Rail | Minneapolis |  | Minnesota |  | Commuter Rail | Introduction of new mode | 80 | New Starts | Preliminary Engineering | 2000 |  | 223 | 112 |  | Annual report on funding recommendations | 2002
| Northstar Corridor Rail | Minneapolis |  | Minnesota |  | Commuter Rail | Introduction of new mode | 82 | New Starts | Preliminary Engineering | 2000 |  | 294 | 147 |  | Annual report on funding recommendations | 2003
| Northstar Corridor Rail | Minneapolis |  | Minnesota |  | Commuter Rail | Introduction of new mode | 82 | New Starts | Preliminary Engineering | 2000 |  | 301.9 | 150.9 |  | Annual report on funding recommendations | 2004
| Northstar Corridor Rail | Minneapolis |  | Minnesota |  | Commuter Rail | Introduction of new mode | 40.1 | New Starts | Preliminary Engineering | 2000 |  | 310 | 155 |  | Annual report on funding recommendations | 2005
| Northstar Corridor Rail | Minneapolis |  | Minnesota |  | Commuter Rail | Introduction of new mode | 40.1 | New Starts | FFGA Awarded | 2007 | 2010 | 317.38 | 156.81 | 5.18 | Annual report on funding recommendations | 2010
| Northstar Corridor Rail | Minneapolis |  | Minnesota |  | Commuter Rail | Introduction of new mode | 40 | New Starts | Preliminary Engineering | 2005 |  | 265.2 | 131 | 5.1 | Annual report on funding recommendations | 2007
| Northstar Corridor Rail | Minneapolis |  | Minnesota |  | Commuter Rail | Introduction of new mode | 40 | New Starts | Preliminary Engineering | 2005 |  | 265.1 |  |  | before and After Study | 2013
| Northstar Corridor Rail | Minneapolis |  | Minnesota |  | Commuter Rail | Introduction of new mode | 40 | New Starts | Final Design | 2006 |  | 307.2 |  |  | before and After Study | 2013
| Northstar Corridor Rail | Minneapolis |  | Minnesota |  | Commuter Rail | Introduction of new mode | 40 | New Starts | FFGA Awarded | 2007 |  | 303.3 |  |  | before and After Study | 2013
| Northstar Corridor Rail | Minneapolis |  | Minnesota |  | Commuter Rail | Introduction of new mode | 40 | New Starts | Project opening | 2009 |  |  |  |  | before and After Study | 2013
| Southwest Light Rail Transit | Minneapolis | Minnetonka, Hopkins, St. Louis Park | Minnesota |  | Light Rail | Introduction of new mode | 15.8 | New Starts | Preliminary Engineering | 2011 | 2017 | 1250.48 | 625.24 |  | Annual report on funding recommendations | 2014
| Southwest Light Rail Transit | Minneapolis | Minnetonka, Hopkins, St. Louis Park | Minnesota |  | Light Rail | Introduction of new mode | 15.8 | New Starts | Project Development | 2013 | 2018 | 1250.48 | 625.24 |  | Annual report on funding recommendations | 2015 | Anticipated completion of the Supplemental Draft EIS in mid-2014, completion of a Final EIS and receipt of a Record of Decision in mid-2015, receipt of a Full Funding Grant Agreement in late 2015.
| Southwest Light Rail Transit | Minneapolis | Minnetonka, Hopkins, St. Louis Park | Minnesota |  | Light Rail | Expansition of existing system | 15.7 | New Starts | Project Development | 2013 | 2020 | 1653.45 | 826.72 |  | Annual report on funding recommendations | 2016
| Southwest Light Rail Transit | Minneapolis |  | Minnesota |  | Light Rail |  |  | New Starts | Engineering | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Southwest Light Rail Transit | Minneapolis |  | Minnesota |  | Light Rail | Expansition of existing system | 14.5 | New Starts | Preliminary Engineering | 2011 | 2023 | 2,003.15 | 928.84 |  | Project Profile | 2019
| Southwest Light Rail Transit | Minneapolis |  | Minnesota |  | Light Rail | Expansition of existing system | 14.5 | New Starts | Engineering | 2016 | 2023 | 2,003.15 | 928.84 |  | Project Profile | 2019
| METRO Blue Line Extension | Minneapolis | Brooklyn Park | Minnesota |  | Light Rail | Expansition of existing system | 13 | New Starts | Project Development | 2014 | 2020 | 1002 | 510 |  | Annual report on funding recommendations | 2016
| METRO Blue Line Extension | Minneapolis |  | Minnesota |  |  | Expansition of existing system |  | New Starts | Engineering | 2016 |  | 1.536 | 752.7 |  | Annual report on funding recommendations | 2018
| METRO Blue Line Extension | Minneapolis |  | Minnesota |  | Light Rail | Expansition of existing system | 13.5 | New Starts | Engineering | 2017 | 2025 | 1,536.18 | 752.73 |  | Project Profile | 2019
| METRO Orange Line Bus Rapid Transit Project | Minneapolis |  | Minnesota |  | Bus Rapid Transit | Introduction of new mode | 17 | Small Starts | Project Development | 2014 | 2019 | 150.7 | 64.63 |  | Annual report on funding recommendations | 2016
| Hiawatha Corridor LRT | St. Paul | Minneapolis | Minnesota |  | Light Rail | Expansition of existing system | 11.6 | New Starts | Preliminary Engineering | 1999 |  |  |  |  | Annual report on funding recommendations | 2005
| Hiawatha Corridor LRT | St. Paul | Minneapolis | Minnesota |  | Light Rail | Expansition of existing system | 11.6 | New Starts | Final Design | 2000 |  |  |  |  | Annual report on funding recommendations | 2005
| Hiawatha Corridor LRT | St. Paul | Minneapolis | Minnesota |  | Light Rail | Expansition of existing system | 11.6 | New Starts | FFGA Awarded | 2001 | 2004 | 675.43 | 334.28 | 48.50 | Annual report on funding recommendations | 2006
| Hiawatha Corridor LRT | St. Paul | Minneapolis | Minnesota |  | Light Rail | Expansition of existing system | 11.6 | New Starts | FFGA Awarded | 2001 | 2004 | 675.43 | 334.28 | 49.50 | Annual report on funding recommendations | 2002
| Central Corridor LRT | St. Paul | Minneapolis | Minnesota |  | Light Rail | Expansition of existing system | 9.8 | New Starts | Preliminary Engineering | 2006 |  |  |  |  | Annual report on funding recommendations | 2013
| Central Corridor LRT | St. Paul | Minneapolis | Minnesota |  | Light Rail | Expansition of existing system | 9.8 | New Starts | FFGA Awarded | 2011 | 2014 (Dec) | 956.9 | 473.95 | FHWA Flexible Funds (CMAQ): 4.5 mn | Annual report on funding recommendations | 2014
| Central Corridor LRT | St. Paul | Minneapolis | Minnesota |  | Light Rail | Expansition of existing system | 9.8 | New Starts | FFGA Awarded | 2011 | 2014 (Jun) | 956.9 | 473.95 | FHWA Flexible Funds (CMAQ): 4.5 mn | Annual report on funding recommendations | 2015 | Section 20008 of the Moving Ahead for Progress in the 21st Century Act authorized FTA to award Federal major capital investment funds for final design and construction. Through FY 2014, Congress has appropriated a total of $364.80 million in Section 5309 New Starts funds.
| METRO Gold Line Bus Rapid Transit | St. Paul |  | Minnesota |  |  |  |  | New Starts | Project Development | 2017 |  | 420 | 189 |  | Annual report on funding recommendations | 2019
| METRO Gold Line Bus Rapid Transit | St. Paul |  | Minnesota |  | Bus Rapid Transit | Introduction of new mode | 10.3 | New Starts | Project Development | 2019 | 1905-07-16 | 460.90 | 207.41 | 4.40 | Project Profile | 2019
| Rochester Downtown Circulator Bus Rapid Transit | Rochester |  | Minnesota |  | Bus Rapid Transit | Introduction of new mode | 4 | Small Starts | Project Development |  | 1905-07-17 | 203 | 99.5 |  | Project Profile | 2020
| Wilmington to Newark Commuter Rail Improvements | Wilmington |  | Delaware |  | Commuter Rail | Improvement of existing service | 1.5 | New Starts | Preliminary Engineering | 2004 | 2009 | 54.9 | 24.9 | 9.9 | Annual report on funding recommendations | 2007
| Wilmington to Newark Commuter Rail Improvements | Wilmington |  | Delaware |  | Commuter Rail | Improvement of existing service | 1.5 | New Starts | Final Design | 2007 |  | 78.42 | 24.99 | 18.82 | Annual report on funding recommendations | 2011
| LYNX Blue Line Extension - Northeast Corridor | Charlotte |  | North Carolina |  | Light Rail | Introduction of new mode | 9.3 | New Starts | Preliminary Engineering | 2007 |  | 1,069.22 | 534.61 |  | Annual report on funding recommendations | 2013
| LYNX Blue Line Extension - Northeast Corridor | Charlotte |  | North Carolina |  | Light Rail | Introduction of new mode |  | New Starts | FFGA Awarded | 2012 | 2018 | 1160.08 | 580.04 |  | Annual report on funding recommendations | 2014
| LYNX Blue Line Extension - Northeast Corridor | Charlotte |  | North Carolina |  | Light Rail | Introduction of new mode |  | New Starts | FFGA Awarded | 2012 | 2018 | 1160.08 | 580.04 |  | Annual report on funding recommendations | 2015
| LYNX Blue Line Extension - Northeast Corridor | Charlotte |  | North Carolina |  | Light Rail | Introduction of new mode |  | New Starts | FFGA Awarded | 2012 | 2018 | 1160.08 | 580.04 |  | Annual report on funding recommendations | 2016
| CityLYNX Gold Line Phase 2 Streetcar | Charlotte |  | North Carolina |  | Streetcar | Expansition of existing system | 2.5 | Small Starts | Project Development | 2011 | 2018 | 126 | 63 |  | Annual report on funding recommendations | 2015 | completed the environmental review process with receipt of a Finding of No Significant Impact in June 2011. The Charlotte Regional Transportation Planning Organization is expected to adopt the LPA into the fiscally constrained long-range transportation plan in April 2014.
| CityLYNX Gold Line Phase 2 Streetcar | Charlotte |  | North Carolina |  | Streetcar | Expansition of existing system | 2.5 | Small Starts | Project Development | 2014 | 2019 | 150 | 74.99 |  | Annual report on funding recommendations | 2016 | completed the environmental review process with receipt of a Finding of No Significant Impact in June 2011. The Charlotte Regional Transportation Planning Organization is expected to adopt the LPA into the fiscally constrained long-range transportation plan in April 2014.
| CityLYNX Gold Line Phase 2 | Charlotte |  | North Carolina |  |  |  |  | Small Starts | CGA | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Blue Line Capacity Expansion | Charlotte |  | North Carolina |  |  |  |  | Core Capacity | Project Development | 2015 |  | 40.2 | 24.1 |  | Annual report on funding recommendations | 2017
| South Corridor Light Rail Project | Charlotte |  | North Carolina |  | Light Rail | Expansition of existing system | 11 | New Starts | Preliminary Engineering | 2000 |  | 331.1 | 166.8 |  | Annual report on funding recommendations | 2002
| South Corridor Light Rail Project | Charlotte |  | North Carolina |  | Light Rail | Expansition of existing system | 11.2 | New Starts | Preliminary Engineering | 2000 |  | 348.2 | 174.1 |  | Annual report on funding recommendations | 2003
| South Corridor Light Rail Project | Charlotte |  | North Carolina |  | Light Rail | Introduction of new mode | 9.6 | New Starts | Preliminary Engineering | 2000 |  | 370 | 185.4 |  | Annual report on funding recommendations | 2004
| South Corridor Light Rail Project | Charlotte |  | North Carolina |  | Light Rail | Introduction of new mode | 9.6 | New Starts | Final Design | 2003 |  | 385.9 | 193 |  | Annual report on funding recommendations | 2005
| South Corridor Light Rail Project | Charlotte |  | North Carolina |  | Light Rail | Introduction of new mode | 9.6 | New Starts | Final Design | 2003 |  | 426.85 | 192.94 | 6.41 | Annual report on funding recommendations | 2007
| South Corridor Light Rail Project | Charlotte |  | North Carolina |  | Light Rail | Introduction of new mode | 9.6 | New Starts | FFGA Awarded | 2005 | 2007 | 426.84 |  |  | Before and After Study | 2011
| South Corridor Light Rail Project | Charlotte |  | North Carolina |  | Light Rail | Introduction of new mode | 9.6 | New Starts | FFGA Awarded | 2007 | 2007 | 462.75 |  |  | Before and After Study | 2011 | Amended FFGA
| South Corridor Light Rail Project | Charlotte |  | North Carolina |  | Light Rail | Introduction of new mode | 9.6 | New Starts | Project opening | 2007 |  |  |  |  | Before and After Study | 2011
| Durham-Orange LRT | Durham |  | North Carolina |  | Light Rail |  |  | New Starts | Engineering | 2017 |  | $2,476.3 | 1,238.2 |  | Annual report on funding recommendations | 2019
| Durham-Orange Light Rail Transit | Durham |  | North Carolina |  | Light Rail | Introduction of new mode | 17.1 | New Starts | Project Development | 2014 | 2026 | 1800 | 910.3 |  | Annual report on funding recommendations | 2015
| Durham-Orange Light Rail Transit | Durham |  | North Carolina |  | Light Rail | Introduction of new mode | 17.1 | New Starts | Project Development | 2014 | 2026 | 1800 | 910.3 |  | Annual report on funding recommendations | 2016
| Regional rail system | Durham | Raleigh, Wake, Durham and Orange | North Carolina |  | Commuter Rail | Introduction of new mode | 34.7 | New Starts | Preliminary Engineering | 1998 |  | 754.7 | 377.3 | 14 | Annual report on funding recommendations | 2002
| Regional rail system | Durham | Raleigh, Wake, Durham and Orange | North Carolina |  | Commuter Rail | Introduction of new mode | 35.2 | New Starts | Preliminary Engineering | 1998 |  | 754.8 | 377.3 | 14 | Annual report on funding recommendations | 2003
| Regional rail system | Durham | Raleigh, Wake, Durham and Orange | North Carolina |  | Commuter Rail | Introduction of new mode | 35.1 | New Starts | Preliminary Engineering | 1998 |  | 832.2 | 447 | 14 | Annual report on funding recommendations | 2004
| Regional rail system | Durham | Raleigh, Wake, Durham and Orange | North Carolina |  | Commuter Rail | Introduction of new mode | 35.1 | New Starts | Final Design | 2003 |  | 843.8 | 413.5 | 5 | Annual report on funding recommendations | 2005
| Regional rail system | Durham | Raleigh, Wake, Durham and Orange | North Carolina |  | Commuter Rail | Introduction of new mode | 28.1 | New Starts | Preliminary Engineering | 1998 |  |  |  |  | Annual report on funding recommendations | 2007 | Diesel multiple unit rail
| Regional rail system | Durham | Raleigh, Wake, Durham and Orange | North Carolina |  | Commuter Rail | Introduction of new mode | 28.1 | New Starts | Final Design | 2004 |  | 809.9 | 485.4 | 12 | Annual report on funding recommendations | 2007 | Diesel multiple unit rail
| North-South BRT | Chapel Hill |  | North Carolina |  | Bus Rapid Transit |  |  | Small Starts | Project Development | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| North-South BRT | Chapel Hill |  | North Carolina |  | Bus Rapid Transit | Introduction of new mode | 8.2 | Small Starts | Project Development | 2016 | 2024 | 141.39 | 100 |  | Project Profile | 2019
| Wake Bus Rapid Transit: New Bern Avenue Project | Raleigh |  | North Carolina |  | Bus Rapid Transit | Introduction of new mode | 5 | Small Starts | Project Development | 2019 | 2023 | 71.45 | 35.05 |  | Project Profile | 2019
| Lowcountry Rapid Transit Project | Charleston |  | South Carolina |  | Bus Rapid Transit | Introduction of new mode | 26 | New Starts | Project Development |  | 2025 | 387.5 |  |  | Project Profile | 2019
| Purple Line BRT | Indianapolis |  | Indiana |  |  |  |  | Small Starts | Project Development | 2017 |  |  |  |  | Annual report on funding recommendations | 2019
| Red Line Rapid Transit | Indianapolis |  | Indiana |  |  |  |  | Small Starts | Project Development | 2015 |  |  |  |  | Annual report on funding recommendations | 2017
| IndyGo Blue Line Rapid Transit | Indianapolis |  | Indiana |  | Bus Rapid Transit | Introduction of new mode | 24 | Small Starts | Project Development |  | 2025 | 220 | 100 | 14.50 | Project Profile | 2019
| IndyGo Purple Line Rapid Transit | Indianapolis |  | Indiana |  | Bus Rapid Transit | Introduction of new mode | 14.8 | Small Starts | Project Development |  | 2023 | 155 | 77.50 | 21.93 | Project Profile | 2019
| West Lake Extension |  |  | Indiana |  |  |  |  | Small Starts | Project Development | 2016 |  | 543 |  |  | Annual report on funding recommendations | 2018
| West Lake Corridor | Lake County |  | Indiana |  | Commuter Rail | Expansition of existing system | 7.8 | New Starts | Project Development | 2016 | 2025 | 933.09 | 354.57 |  | Project Profile | 2019
| West Lake Corridor | Lake County |  | Indiana |  | Commuter Rail | Expansition of existing system | 7.8 | New Starts | Engineering | 2019 | 2025 | 933.09 | 354.57 |  | Project Profile | 2019
| South Shore Line Northwest Indiana Connectivity Plan | Gary | Michigan | Indiana |  |  |  |  | Core Capacity | Project Development | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Double Track Northwest Indiana | Gary | Michigan | Indiana |  | Commuter Rail | Expansition of existing system | 26.6 | Core Capacity | Project Development | 2016 | 2024 | 456.05 | 172.96 |  | Project Profile | 2019 | NICTD withdrew the project from Core Capacity Project Development in February 2019
| Double Track Northwest Indiana | Gary | Michigan | Indiana |  | Commuter Rail | Expansition of existing system | 26.6 | New Starts | Engineering | 2020 | 2024 | 456.05 | 172.96 |  | Project Profile | 2019 | NICTD withdrew the project from Core Capacity Project Development in February 2019
| New Britain – Hartford Busway | Hartford | New Britain | Connecticut |  | Bus Rapid Transit | Introduction of new mode | 9.6 | New Starts | Preliminary Engineering | 2000 |  | 80 | 51.60 | 12.4 | Annual report on funding recommendations | 2001
| New Britain – Hartford Busway | Hartford | New Britain | Connecticut |  | Bus Rapid Transit | Introduction of new mode | 9.6 | New Starts | Preliminary Engineering | 2000 |  | 82 | 51.6 | 14 | Annual report on funding recommendations | 2002
| New Britain – Hartford Busway | Hartford | New Britain | Connecticut |  | Bus Rapid Transit | Introduction of new mode | 9.6 | New Starts | Preliminary Engineering | 2000 | 2003 | 160 | 79.4 | 48.6 | Annual report on funding recommendations | 2003
| New Britain – Hartford Busway | Hartford | New Britain | Connecticut |  | Bus Rapid Transit | Introduction of new mode | 9.4 | New Starts | Preliminary Engineering | 2000 | 2007 | 175.2 | 87.5 | 51.7 | Annual report on funding recommendations | 2005
| New Britain – Hartford Busway | Hartford | New Britain | Connecticut |  | Bus Rapid Transit | Introduction of new mode | 9.4 | New Starts | Preliminary Engineering | 2000 | 2011 | 335.5 | 167.8 | 85 | Annual report on funding recommendations | 2007
| New Britain – Hartford Busway | Hartford | New Britain | Connecticut |  | Bus Rapid Transit | Introduction of new mode | 9.4 | New Starts | Final Design | 2006 |  | 572.69 | 275.30 | 179.53 | Annual report on funding recommendations | 2013
| New Britain – Hartford Busway | Hartford | New Britain | Connecticut |  | Bus Rapid Transit | Introduction of new mode | 9.4 | New Starts | FFGA Awarded | 2011 | 2015 | 572.69 | 275.3 | 184.67 | Annual report on funding recommendations | 2014
| New Britain – Hartford Busway | Hartford | New Britain | Connecticut |  | Bus Rapid Transit | Introduction of new mode | 9.4 | New Starts | Final Design | 2014 | 2015 | 567.05 | 275.3 | 179.54 | Annual report on funding recommendations | 2015
| Urban Transitway Phase II | Stamford |  | Connecticut |  | Transitway | Expansition of existing system | 0.6 | New Starts | Final Design | 2007 |  | 48.31 | 33.52 | 1.09 | Annual report on funding recommendations | 2010
| Urban Transitway Phase II | Stamford |  | Connecticut |  | Transitway | Expansition of existing system | 0.6 | New Starts | Preliminary Engineering | 2006 |  | 48.31 | 33.52 | 1.09 | Annual report on funding recommendations | 2011
| Urban Transitway | Stamford |  | Connecticut |  | Transitway | Expansition of existing system | 1 | New Starts | Preliminary Engineering | 2000 |  | 24 | 18 | 0.2 | Annual report on funding recommendations | 2003
| Brdigporte Inermodal Transporation center Phase 2B and 3 | Bridgeport |  | Connecticut |  | Commuter Rail | Expansition of existing system | 1 | New Starts | Preliminary Engineering | 2001 |  | 62.4 | 24.9 | 5 | Annual report on funding recommendations | 2004 | A combination of services, Bus rapid system, ferry, etc.
| High Capacity Transit Corridor Project | Honolulu |  | Hawaii |  | Transitway | Introduction of new mode | 20 | New Starts | Final Design | 2011 |  | 5,125.96 | 1,550.00 | 248 | Annual report on funding recommendations | 2013
| High Capacity Transit Corridor Project | Honolulu |  | Hawaii |  | Transitway | Introduction of new mode | 20 | New Starts | Preliminary Engineering | 2009 |  | 5,125.96 | 1,550.00 | 248 | Annual report on funding recommendations | 2013
| High Capacity Transit Corridor Project | Honolulu |  | Hawaii |  | Transitway | Introduction of new mode | 20 | New Starts | FFGA Awarded | 2012 | 2020 | 5121.69 | 1550 | 213.9 | Annual report on funding recommendations | 2014
| High Capacity Transit Corridor Project | Honolulu |  | Hawaii |  | Transitway | Introduction of new mode | 20 | New Starts | FFGA Awarded | 2012 | 2020 | 5121.69 | 1550 | 213.9 | Annual report on funding recommendations | 2015
| High Capacity Transit Corridor Project | Honolulu |  | Hawaii |  | Transitway | Improvement of existing service | 20 | New Starts | FFGA Awarded | 2012 | 2020 | 5121.69 | 1550 | 213.9 | Annual report on funding recommendations | 2016
| Primary Corridor Transportation Project | Honolulu |  | Hawaii |  | Bus Rapid Transit | Introduction of new mode | 32 | New Starts | Preliminary Engineering | 2001 |  | 683.4 | 231.6 | 186.6 | Annual report on funding recommendations | 2003
| Silver Line BRT | Grand Rapids | Kentwood, Wyoming | Michigan |  | Bus Rapid Transit | Introduction of new mode | 9.6 | Very Small Starts | Project Development | 2007 | 2014 | 35.29 | 28.22 |  | Annual report on funding recommendations | 2013
| Silver Line BRT | Grand Rapids | Kentwood, Wyoming | Michigan |  | Bus Rapid Transit | Introduction of new mode | 9.6 | Very Small Starts | FFGA Awarded | 2012 | 2014 | 39.86 | 18.99 | 12.89 | Annual report on funding recommendations | 2014
| Laker Line BRT | Grand Rapids |  | Michigan |  | Bus Rapid Transit |  |  | Small Starts | Project Development | 2015 | 71 | 56.8 |  |  | Annual report on funding recommendations | 2017
| Michigan/Grand River BRT | Lansing |  | Michigan |  | Bus Rapid Transit | Introduction of new mode | 8.5 | Small Starts | Project Development | 2013 | 2016 | 215.36 | 74.99 | 89.47 | Annual report on funding recommendations | 2014
| Michigan/Grand River BRT | Lansing |  | Michigan |  | Bus Rapid Transit | Introduction of new mode | 8.5 | Small Starts | Project Development | 2013 | 2016 | 215.36 | 74.99 | 89.47 | Annual report on funding recommendations | 2015
| Michigan/Grand River BRT | Lansing |  | Michigan |  | Bus Rapid Transit | Introduction of new mode | 8.5 | Small Starts | Project Development | 2013 | 2018 | 215.36 | 74.99 | 89.47 | Annual report on funding recommendations | 2016
| Capital Area Transportation Authority Bus Rapid TransitProject | Lansing |  | Michigan |  | Bus Rapid Transit |  | 8.5 | Small Starts | Project Development | 2013 |  | 141.85 | 97.82 | 15.37 | Project Profile | 2016
| Central Avenue Corridor BRT Project | Albuquerque |  | New Mexico |  | Bus Rapid Transit | Introduction of new mode | 17 | Small Starts | Project Development | 2015 | 2017 | Not given | Not given |  | Annual report on funding recommendations | 2016 | ABQ RIDE anticipates developing a locally preferred alternative (LPA) and adopting it into the region’s fiscally constrained long-range transportation plan by March 2015
| Central Avenue Corridor BRT Project | Albuquerque |  | New Mexico |  | Bus Rapid Transit | Introduction of new mode | 17 | Small Starts | Project Development | 2015 | 2017 | Not given | Not given |  | Annual report on funding recommendations | 2016
| 4th Street/Prater Way BRT Project | Reno | Sparks | Nevada |  | Bus Rapid Transit | Introduction of new mode | 3.2 | Small Starts | Project Development | 2013 | 2017 | 52.6 | 24.6 |  | Annual report on funding recommendations | 2015 | The revised design was designated as the Locally Preferred Alternative by RTC on November 15, 2013. FTA issued a Categorical Exclusion on February 7, 2014. RTC expects to receive a Small Starts Grant Agreement in August 2015
| 4th Street/Prater Way BRT Project | Reno |  | Nevada |  | Bus Rapid Transit |  |  | Small Starts | CGA | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Virginia Street BRT Extension Project | Reno |  | Nevada |  | Bus Rapid Transit | Expansition of existing system | 1.8 | Small Starts | Project Development | 2013 | 2018 | 27.3 |  |  | Annual report on funding recommendations | 2016
| Resort Corridor Fixed Guideway | Las Vegas |  | Nevada |  |  | Expansition of existing system | 4.7 | New Starts | Preliminary Engineering | 1998 |  | 597 | 210 |  | Annual report on funding recommendations | 2002
| Resort Corridor Fixed Guideway | Las Vegas |  | Nevada |  |  | Expansition of existing system | 3.1 | New Starts | Preliminary Engineering | 1998 |  | 440 | 130 | 165 | Annual report on funding recommendations | 2003
| Resort Corridor Fixed Guideway | Las Vegas |  | Nevada |  |  | Expansition of existing system | 2.3 | New Starts | Preliminary Engineering | 1998 |  | 453.9 | 159.7 | 160.8 | Annual report on funding recommendations | 2005 | Monorail
| Maryland Parkway High Capacity Transit Project | Las Vegas |  | Nevada |  | Bus Rapid Transit | Introduction of new mode | 8.7 |  | Project Development |  | 2024 |  |  |  | Project Profile | 2020
| East-West Connector BRT Project (The Amp) | Nashville |  | Tennessee |  | Bus Rapid Transit | Introduction of new mode | 7.1 | Small Starts | Project Development | 2014 | 2016 | 174 | 74.99 | FHWA Flexible Funds (Surface Transportation Program): 4mn | Annual report on funding recommendations | 2015
| East-West Connector BRT Project (The Amp) | Nashville |  | Tennessee |  | Bus Rapid Transit | Introduction of new mode | 7.1 | Small Starts | Project Development | 2014 | 2016 | 174 | 74.99 | FHWA Flexible Funds (Surface Transportation Program): 4mn | Annual report on funding recommendations | 2016 | MTA was conducting the environmental review process when local concerns over the project alignment arose. After establishing a citizens advisory committee and conducting additional public outreach during 2014, MTA announced in late January 2015 that it was ceasing work on the AMP project but continuing strategic planning efforts in the region to determine possible future transit solutions.
| East corridor commuter rail | Nashville |  | Tennessee |  | Commuter Rail | Introduction of new mode | 31.1 | New Starts | Preliminary Engineering | 1999 |  | 33.2 | 22.9 | 3.7 | Annual report on funding recommendations | 2002
| East corridor commuter rail | Nashville |  | Tennessee |  | Commuter Rail | Introduction of new mode | 32 | Small Starts | Final Design | 2001 |  | 33.2 | 22.9 | 3.7 | Annual report on funding recommendations | 2003
| East corridor commuter rail | Nashville |  | Tennessee |  | Commuter Rail | Introduction of new mode | 32 | Small Starts | Final Design | 2001 |  | 37.6 | 23 | 7.1 | Annual report on funding recommendations | 2004
| East corridor commuter rail | Nashville |  | Tennessee |  | Commuter Rail | Introduction of new mode | 32 | Small Starts | Preliminary Engineering | 1999 | 2006 |  |  |  | Annual report on funding recommendations | 2005
| East corridor commuter rail | Nashville |  | Tennessee |  | Commuter Rail | Introduction of new mode | 32 | Small Starts | Final Design | 2001 | 2006 | 41 | 24 | 8.4 | Annual report on funding recommendations | 2007
| Medical Center Extension | Memphis |  | Tennessee |  | Light Rail | Expansition of existing system | 2 | New Starts | Preliminary Engineering | 1998 | 2004 |  |  |  | Annual report on funding recommendations | 2005
| Medical Center Extension | Memphis |  | Tennessee |  | Light Rail | Expansition of existing system | 2 | New Starts | Final Design | 2000 | 2004 |  |  |  | Annual report on funding recommendations | 2005
| Medical Center Extension | Memphis |  | Tennessee |  | Light Rail | Expansition of existing system | 2 | New Starts | FFGA Awarded | 2000 | 2004 | 74.58 | 59.68 |  | Annual report on funding recommendations | 2005
| Memphis Innovation Corridor Project | Memphis |  | Tennessee |  | Bus Rapid Transit | Introduction of new mode | 8 | Small Starts | Project Development |  | 2026 |  |  |  | Project Profile | 2020
| Dulles Corridor Metrorail Project – Extension to Wiehle Avenue | Reston area (Fairfax County) | Tysons Corner | Northern Virginia | Washington DC | Bus Rapid Transit | Expansition of existing system | 11.7 | New Starts | FFGA Awarded | 2009 | 2014 (Dec) | 3142.47 | 900 | 75.00 | Annual report on funding recommendations | 2014 | Mode: Metrorail
| Dulles Corridor Metrorail Project – Extension to Wiehle Avenue | Reston area (Fairfax County) | Tysons Corner | Northern Virginia | Washington DC | Bus Rapid Transit | Expansition of existing system | 11.7 | New Starts | FFGA Awarded | 2009 | 2014 (Dec) | 3142.47 | 900 | 75.00 | Annual report on funding recommendations | 2015 | Mode: Metrorail
| Dulles Corridor Metrorail Project – Extension to Wiehle Avenue | Washington DC |  | Northern Virginia | Washington DC | Bus Rapid Transit | Expansition of existing system | 11.7 | New Starts | Final Design | 2008 | 2014 | 3,142.47 | 900.00 | 75.00 | Annual report on funding recommendations | 2011
| Dulles Corridor Metrorail Project – Extension to Wiehle Avenue | Washington DC |  | Northern Virginia | Washington DC | Bus Rapid Transit | Expansition of existing system | 11.6 | New Starts | Preliminary Engineering | 2005 | 2014 | 1,840.1 | 920 |  | Annual report on funding recommendations | 2007
| Dulles Corridor Metrorail Project – Extension to Wiehle Avenue | Washington DC |  | Northern Virginia | Washington DC | Bus Rapid Transit | Expansition of existing system | 23.5 | New Starts | Preliminary Engineering | 2000 |  | 357.1 | 214.3 |  | Annual report on funding recommendations | 2004
| Dulles Corridor Metrorail Project – Extension to Wiehle Avenue | Washington DC |  | Northern Virginia | Washington DC | Bus Rapid Transit | Expansition of existing system | 23.5 | New Starts | Preliminary Engineering | 2000 |  | 389.1 | 233.5 | 1 | Annual report on funding recommendations | 2003
| Dulles Corridor Metrorail Project – Extension to Wiehle Avenue | Washington DC |  | Northern Virginia | Washington DC | Bus Rapid Transit | Expansition of existing system | 23 | New Starts | Preliminary Engineering | 2000 |  | 287.3 |  | 1 | Annual report on funding recommendations | 2002
| East West Corridor BRT | Milwaukee |  | Wisconsin |  | Bus Rapid Transit | Introduction of new mode | 9.1 | Small Starts | Project Development | 2016 | 2021 | 54.79 | 40.93 | 2.27 | Project Profile | 2019
| East West Corridor BRT | Milwaukee |  | Wisconsin |  | Bus Rapid Transit |  | 9.1 | New Starts | Project Development | 2016 |  |  |  |  | Annual report on funding recommendations | 2018
| Madison East-West Bus Rapid Transit | Madison |  | Wisconsin |  | Bus Rapid Transit | Introduction of new mode | 15 | Small Starts |  |  |  | 120-130 |  |  | Project Profile | 2020
| Pawtucket/Central Falls Commuter Rail Station | Pawtucket |  | Rhode Island |  | Commuter Rail | Expansition of existing system |  | New Starts | Preliminary Engineering | 2010 | 2018 | 53.64 | 24.99 | 11 | Annual report on funding recommendations | 2013
| Rhode Island Commuter Rail Improvement | Pawtucket |  | Rhode Island |  | Commuter Rail | Improvement of existing service |  | New Starts | Final Design | 2001 | 2002/2003 | 18.5 | 10 | 4.7 | Annual report on funding recommendations | 2003
| Rhode Island Commuter Rail Improvement Program | Pawtucket |  | Rhode Island |  | Commuter Rail | Improvement of existing service |  | New Starts | Final Design | 2001 | 2004 | 18.5 | 10 |  | Annual report on funding recommendations | 2004
| South County Commuter Rail | Providence |  | Rhode Island |  | Commuter Rail | Introduction of new mode | 20 | New Starts | Preliminary Engineering |  |  | 43.7 | 24.9 | 9.9 | Annual report on funding recommendations | 2007
| Transportation Tomorrow South Central Corridor LRT | Louisville |  | Kentucky |  | Light Rail | Introduction of new mode | 17.5 | New Starts | Preliminary Engineering | 2001 |  | 748.1 | 372.5 | 37.6 | Annual report on funding recommendations | 2005
| Transportation Tomorrow South Central Corridor LRT | Louisville |  | Kentucky |  | Light Rail | Introduction of new mode | 15 | New Starts | Preliminary Engineering | 2001 |  | 671.2 | 380.2 | 49.8 | Annual report on funding recommendations | 2003
Note on A1: Voulgaris, Carole Turley: Assign a unique ID to the project. Some projects may change names over time, so this is to indicate that it's still the same project at each milestone.
Note on B1: Voulgaris, Carole Turley: The exact name of the project as it appears in the source document.
Note on C1: Voulgaris, Carole Turley: The primary city in which the project is located.
Note on D1: Voulgaris, Carole Turley: Additional cities that parts of the project are located in, if any.
Note on E1: Voulgaris, Carole Turley: The primary state in which the project is located.
Note on F1: Voulgaris, Carole Turley: Additional states parts of the project are located in, if any. (This is most likely to come up for projects in the DC area).
Note on I1: Voulgaris, Carole Turley: The length of the project, in miles.
Note on Q1: Voulgaris, Carole Turley: The document that all the data in this row came from. If data is from different sources, it should be in different rows. If the same data in in multiple documents (and doesn't conflict), list the most recent.

## Sheet1
Project Mode (column G) | Project Type (column H) | Grant Program (column J) | Project Milestone (column K) | Source Document (column Q)
Light Rail | New system | New Starts | Project Development | Annual Report of funding recommendations
Heavy Rail | Expansion of existing system | Small Starts | Engineering | Before and After Study
Commuter Rail | Improvement of existing service | Very Small Starts | Preliminary Engineering | ç
Transitway |  | Core Capacity | Final Design
People Mover |  |  | FFGA Awarded
Bus Rapid Transit |  |  | Project opening
Streetcar |  |  | Project Construction Grant Agreement
Construction Grant Agreement
SSGA