## Slide 1: Under-estimated or over budget? Evaluating cost estimate accuracy for federally-funded transit projects
Carole Voulgaris
Harvard Graduate School of Design

## Slide 2: Agenda
The Federal Transit Administration’s New Starts Program
Common explanations for optimism bias in demand and cost estimation
Differences between cost estimation and ridership forecasting
Relationships among forecasting/estimation errors

## Slide 3: The New Starts Program

## Slide 4: What is the New Starts program?
FTA’s primary grant program for capital investment in fixed-guideway public transit projects
  Urban rail
    Downtown people movers (monorail)
    Light rail
    Heavy rail/subway
    Commuter rail
  Bus rapid transit

## Slide 5: The role of forecasting and cost estimation
Cost effectiveness =
Cost
Benefits
Estimate of construction costs
Estimate of future ridership

## Slide 6
Changes to cost-effectiveness calculation
Addition of project evaluation criteria
Mobility improvement
  Value of travel time savings
  Number of low-income households within half mile
Environmental benefit
  Value of emissions reduction
  Change in energy consumption
  Compliance with EPA air quality standards
Operating efficiencies (Change in operating cost per passenger mile)
Cost effectiveness (Cost per new rider)
Transit-supportive existing land-use policies and future patterns: Low, medium, or high, based on
    Existing land use
    Containment of sprawl
    Transit-supportive policies
    Performance of land-use policies
Other factors
  The degree to which institutions are already in place as assumed in forecasts
  Project management capability
  Additional relevant factors
Added economic development and land use as criteria
2005 Dear Colleague letter: Cost effectiveness rating of medium or better required for funding
2007 NPRM: Cost effectiveness weighted at 50% of project evaluation score
2008 SAFETEA-LU technical corrections act: criteria must be comparably weighted

## Slide 7: Common explanations for optimism bias

## Slide 8: Explanations for bias
Technical/project specific
Flawed models
Unforeseeable events
Incorrect assumptions
Systemic
Psychological
  People really are optimistic
  People are bad at anticipating setbacks
Ethical
  Strategic misrepresentation
Defensible
Selection bias

## Slide 9: Differences between cost estimation and ridership forecasting

## Slide 10: Difference in incentives
Ridership forecasts
Predict ridership as high as possible/defensible.
Cost estimates
Estimates need to be low enough to make the project look attractive,
  But high enough that you get enough money to complete the project.

## Slide 11: Difference in expertise
Travel demand modeling
Models developed by transportation engineers
Models run by transportation engineers and planners
Basic model structure is a common part of a transportation planner’s/engineer’s education
For New Starts: Minimal oversight by Federal Transit Administration
Construction cost estimation
Cost estimates developed by cost estimators, construction managers, and construction engineers
Cost estimation techniques are not a standard part of a transportation planner’s/engineer’s education
For New Starts: Relatively high level of guidance and oversight

## Slide 12: Difference in perception of control
 | During project planning | During project construction | After project opening
Within the project sponsor’s control | Ridership forecasts | Observed cost | 
Beyond the project sponsor’s control | Cost estimates |  | Observed ridership

## Slide 13: Difference in temporal variation
Ridership forecasts
Prepared once near the beginning of project development and engineering
Compared to observed ridership that varies over time
Project opening
Cost estimates
Refined/revised over the course of project development and engineering
Compared to a single final cost estimate

## Slide 14: Accuracy compared to what?
Which observed ridership value?
FTA: Two years after project opening
Which cost estimate?
The earliest one?
The latest one?

## Slide 15: Cost escalation vs cost overrun
Cost escalation
Increases in project costs over the course of project development
May be viewed as a project management problem or an ethics problem
Cost overrun
Increase in project costs after construction begins
More likely to be viewed as a project management problem
Project opening

## Slide 16: Relationships among forecasting/estimation errors

## Slide 17: Relationship among errors
50 projects completed between 1989 and 2011 for which ridership forecasts are available in addition to initial and final cost estimates.

## Slide 18: Relationship among errors
r = (0.14, 0.60)
r = (-0.38, 0.15)
r = (-0.33, 0.13)
Error =
(Predicted – Observed)
(Predicted + Observed) / 2
50 projects completed between 1989 and 2011 for which ridership forecasts are available in addition to initial and final cost estimates.

## Slide 19: Change over time
r = (-0.59, -0.18)
r = (0.08, 0.53)
r = (-0.05, 0.44), median = 0.06%

## Slide 20: Relationship with project development duration
r = (-0.22, 0.28)
r = (-0.25, 0.25)
r = (-0.58, -0.14)
Of 59 projects with final cost estimates available:
44 began construction in the same year as the final cost estimate
51 had begun construction by the following year

## Slide 21: Relationship with construction duration
r = (0.16, 0.58)
r = (-0.58, -0.15)
r = (-0.43, 0.07)

## Slide 22: Relationship with project cost
r = (-0.23, 0.26)
r = (-0.64, -0.24)
r = (-0.57, -0.13)

## Slide 23: Relationship with project length
r = (-0.29, 0.20)
r = (-0.49, +0.0)
r = (-0.17, 0.34)

## Slide 24: Relationship with mode
People movers have ridership forecast errors 18 to 154 percentage points greater than light rail (95-percent confidence)
Cost estimates for light rail projects are 4 to 32 percentage points more accurate than those for heavy rail projects
No significant differences by mode

## Slide 25: Relationship with sequence/experience
No significant differences by sequence
r = (-0.25, 0.28)
r = (-0.50, 0.04)
r = (-0.39, 0.12)

## Slide 26: Summary of simple correlations
 | Forecast type |  | 
 | Cost estimate |  | Ridership forecast
 | Initial | Final | 
Time of forecast |  |  | 
Year | + | o | +
Governing legislation | o | o | o
Project characteristics |  |  | 
Elapsed time |  |  | 
Project development | o | — | o
Project construction | — | o | —
Financial characteristics |  |  | 
Total project cost | — | — | o
Physical characteristics |  |  | 
Project length | o | o | o
Project mode | o | ☐ | ☐
Local experience |  |  | 
Project sequence | o | o | o
Project share of new system miles | — | o | o
Relationship with accuracy, without controlling for other factors (95-percent confidence)
+ = Increase associated with improved accuracy
— = Increase associated with reduced accuracy
o = No significant relationship with accuracy
☐ = At least one pair of categories variables associated with a difference in accuracy

## Slide 27: Relationships with controls (linear regression)
 | Forecast type |  | 
 | Cost estimate |  | Ridership forecast
 | Initial | Final | 
Time of forecast |  |  | 
Year | o | o | +
Governing legislation | o | o | o
Project characteristics |  |  | 
Elapsed time |  |  | 
Project development | o | o | o
Project construction | o | o | —
Financial characteristics |  |  | 
Total project cost | — | — | o
Physical characteristics |  |  | 
Project length | o | o | o
Project mode | ☐ | ☐ | ☐
Local experience |  |  | 
Project sequence | o | o | o
Project share of new system miles | o | o | o
90-percent confidence
+ = Increase associated with improved accuracy
— = Increase associated with reduced accuracy
o = No significant relationship with accuracy
☐ = At least one pair of categories variables associated with a difference in accuracy
95-percent confidence
+ = Increase associated with improved accuracy
— = Increase associated with reduced accuracy
o = No significant relationship with accuracy
☐ = At least one pair of categories variables associated with a difference in accuracy

## Slide 28: Preliminary conclusions
Future
directions
Cost estimates –especially final cost estimates– have been more accurate than ridership forecasts.
Cost estimate error is not correlated with ridership forecast error.
Final cost estimate error is better than, but correlated with initial cost estimate error.
More costly projects experience higher cost estimation errors.
What external pressures, if any, create an incentive to misrepresent initial cost estimates?
To what degree are cost estimates self-fulfilling?
How do federal funding shares change with cost escalation?
What are the relationships between cost escalation and cost overrun?
Under what circumstances is a project abandoned?

## Slide 29: Thank you.
Carole Voulgaris
Harvard Graduate School of Design
cvoulgaris@gsd.harvard.edu