## in
ID | Name | Year | Milestone | Project length | Expected cost | Expected 5309 contribution | Expected other federal funds | Expected opening
100 | Downtown-Uptown-Oakland-East End BRT Project | 2017 | Project development | 15 | 249900000 | 99950000 | 10760000 | 2024
101 | Corridor one Rail MOS | 2002 | Preliminary Engineering | 40.5 | 87000000 | 24900000 | 10000000
102 | Schuylkill Valley Metro Rail | 2002 | preliminary engineering | 74 | 2588900000 | 2071100000
103 | South/North Corridor (MOS-1) | 1996 | preliminary engineering | 20 | 2400000000 | 1200000000
104 | Portland, Oregon/Westside-Hillsboro Corridor | 1992 | FFGA | 17.7 | 910180000 | 590070000 |  | 1998
104 | Portland, Oregon/Westside-Hillsboro Corridor | 1996 | FFGA Amended | 17.7 |  | 630060000 |  | 1998
104 | Portland, Oregon/Westside-Hillsboro Corridor | 1998 | Opened service | 17.7 | 963520000 | 630060000 |  | 1998
105 | Westside Light Rail to 185th | 1992 | Full Funding Grant Agreement |  | 688000000 | 516000000 |  | 1998
106 | South Corridor I-205 / Portland Mall LRT | 2004 | EIS | 8.3 | 557400000 | 334400000
106 | South Corridor I-205 / Portland Mall LRT | 2007 | Full Funding Grant Agreement | 8.3 | 575700000 | 345400000 | 88200000 | 2009
107 | Portland-Milwaukie Light Rail Project | 2002 | EIS | 7.3 | 1417760000 | 735860000 | 72500000 | 2009
107 | Portland-Milwaukie Light Rail Project | 2009 | Preliminary Engineering | 7.3 | 1417760000 | 735860000 | 72500000 | 2009
108 | Columbia River Crossing Project | 2009 | preliminary engineering | 2.9 | 3565020000 | 850000000 | 418570000 | 2019
108 | Columbia River Crossing Project | 2011 | Final EIS | 2.9 | 2796910000 | 850000000 | 122700000 | 2019
108 | Columbia River Crossing Project | 2013 | Legislation | 2.9 | 2711830000 | 850000000 | 84230000 | 2019
109 | Columbia River Crossing Project
110 | Powell-Division Transit and Development | 2015 | Small Starts Project Development | 14 |  | 75000000 |  | 2020
111 | TriMet Interstate MAX Light Rail | 1994 | Major Investment Study | 5.8
111 | TriMet Interstate MAX Light Rail | 1996 | Preliminary Engineering | 5.8
111 | TriMet Interstate MAX Light Rail | 1999 | FEIS | 5.8
111 | TriMet Interstate MAX Light Rail | 2000 | FFGA | 5.8 |  | 350000000 | 257500000 | 2004
111 | TriMet Interstate MAX Light Rail | 2004 | Opened service | 5.8
112 | MAX Red Line Extension and Reliability Improvements
113 | Westside Express Service Rail Project - Wilsonville - Beaverton | 1997 | Phase 1
113 | Westside Express Service Rail Project - Wilsonville - Beaverton | 1999 | Phase 2
113 | Westside Express Service Rail Project - Wilsonville - Beaverton | 2000 | Preliminary Engineering | 15.3 | 82800000 | 24900000
114 | Green Line Light Rail Project | 2004 | preliminary engineering | 14.5 | 505263157.89 |  |  | 2009
114 | Green Line Light Rail Project | 2005 | Final design | 14.5 | 559223300 |  |  | 2009
114 | Green Line Light Rail Project | 2007 | Full Funding Grant Agreement | 14.5 | 559223300 |  |  | 2009
114 | Green Line Light Rail Project | 2009 | Opened service | 14.5 | 576000000 |  |  | 2009
115 | Streetcar Loop Project | 2007 | Project development | 3.3 | 151900000 |  |  | 2012
115 | Streetcar Loop Project | 2009 | Small Starts Grant | 3.3 | 148800000 |  |  | 2012
115 | Streetcar Loop Project | 2012 | Opening | 3.3 | 148800000 |  |  | 2012
117 | Southwest Corridor Light Rail Transit Project | 2011 | Preliminary Engineering | 14.5 |  |  |  | 2024
117 | Southwest Corridor Light Rail Transit Project | 2016 | Final EIS | 14.5 |  |  |  | 2024
117 | Southwest Corridor Light Rail Transit Project | 2020 | Full Funding Grant Agreement | 14.5 | 2003150000 | 928840000 |  | 2024
118 | Pioneer Parkway EmX BRT | 2006 | Project development | 7.8
118 | Pioneer Parkway EmX BRT | 2008 | Project Construction Agreement | 7.8 | 41290000 | 32540000 | 490000 | 2010
118 | Pioneer Parkway EmX BRT | 2010 | Opening | 7.8
119 | West Eugene EmX Extension | 2011 | Locally Preferred Alternative | 8.9 | 95570000 | 74990000
119 | West Eugene EmX Extension | 2012 | Project development | 8.9 | 95570000 | 74990000 |  | 2017
119 | West Eugene EmX Extension | 2012 | Environmental Assessment | 9.2 | 96730000 | 74990000 | 1070000 | 2017
119 | West Eugene EmX Extension | 2017 | Small Grants Agreement
120 | Cleveland (Euclid Corridor) | 2000 | Preliminary Engineering | 9.8 | 228600000 | 135000000 |  | 2007
120 | Cleveland (Euclid Corridor) | 2005 | Final design | 9.4 | 168400000 | 82.2 |  | 2007
121 | Interstate 71 corridor (MOS-1) | 1998 | Preliminary Engineering | 19 | 874700000 | 431200000
121 | Interstate 71 corridor (MOS-1) | 2003 | Preliminary Engineering |  | 899900000 | 449900000
121 | Interstate 71 corridor (MOS-1) | 2004 | Draft Environmental Impact Statement | 19.5
121 | Interstate 71 corridor (MOS-1) | 2005 | No plans for referendum
122 | Northeast Corridor BRT Project | 2013 | Small Starts Project Development | 15.6 | 39430000 | 31540000 |  | 2016
122 | Northeast Corridor BRT Project | 2014 | Categorical Exclusion | 15.6 | 39430000 | 31540000 |  | 2017
123 | Northeast Corridor LRT | 2012 | Final design |  | 1160080000 | 580040000 |  | 2018
124 | Cleveland Avenue Bus Rapid Transit | 2013 | Small Starts Project Development | 15.6 | 39430000 | 31540000 |  | 2016
124 | Cleveland Avenue Bus Rapid Transit | 2014 | Categorical Exclusion | 15.6 | 39430000 | 31540000 |  | 2017
125 | Craig, Alaska (Alaska-Hollis Ketchikan Ferry)
126 | Alaska Rail Road - South Wasilla Track Realignment | 2005 | Preliminary Engineering |  | 25300000 | 23100000
127 | South Anchorage Double Track | 2003 | Final Design |  | 69600000 | 15000000
128 | Alaska Marine Highway System
129 | Norfolk -Virginia Beach Corridor (First phase)
130 | Norfolk LRT - The Tide Light Rail | 2002 | Preliminary Engineering | 7.3 | 194600000 |  |  | 2011
130 | Norfolk LRT - The Tide Light Rail | 2006 | Final design | 7.3 | 235600000 |  |  | 2011
130 | Norfolk LRT - The Tide Light Rail | 2007 | Full Funding Grant Agreement | 7.3 | 231600000 |  |  | 2011
130 | Norfolk LRT - The Tide Light Rail | 2011 | Opened service | 7.3 | 314600000 |  |  | 2011
131 | West End Transitway | 2016 | Small Starts Project Development | 5.3 | 119000000 - 140000000 |  |  | 2021
131 | West End Transitway | 2017 | Environmental Assessment | 5.3 | 119000000 - 140000000 |  |  | 2021
131 | West End Transitway | 2019 | Small Starts Grant | 5.3 | 119000000 - 140000000 |  |  | 2021
132 | Richmond Highway BRT Project | 2022 | Project development |  | 730000000 | 285000000
133 | Seattle-Tacoma Sounder Commuter Rail | 1998 | Preliminary Engineering | 40 |  |  |  | 1999
133 | Seattle-Tacoma Sounder Commuter Rail | 1998 | Final Design | 40 | 401000000 | 100000000 |  | 1999
134 | Central Link Initial Segment (Initial) | 1999 | Preliminary Engineering | 15.6 | 1858000000
134 | Central Link Initial Segment (Initial) | 2000 | Final Design | 15.6 | 2660320000
134 | Central Link Initial Segment (Initial) | 2003 | New Starts Funding | 15.6 | 2558000000 | 500000000 |  | 2009
135 | Roosevelt RapidRide BRT | 2019 | Project development |  | 77200000 | 38600000
135 | Roosevelt RapidRide BRT | 2020 | Project Development |  | 90200000 | 45000000
136 | University Link LRT Extension | 1999 | EIS
136 | University Link LRT Extension | 2001 | FFGA
136 | University Link LRT Extension | 2005 | Preliminary Engineering | 3.1 | 1720000000 | 700000000 |  | 2016
137 | Lynnwood Link Extension | 2013 | EIS | 8.5 | $1.2 billion $1.70 billion | $600 million - $850 million |  | 2023
137 | Lynnwood Link Extension | 2017 | New Starts Projects Not Yet Under Construction Grants |  | 2345925753 | 1172728284
138 | Center City Connector Streetcar | 2014 | Project development | 1.3 | 110000000 | 55 million - 75 million |  | 2018
138 | Center City Connector Streetcar | 2018 | Project development |  | 166000000 | 75000000
138 | Center City Connector Streetcar | 2019 | Project development |  | 177000000 | 75000000
138 | Center City Connector Streetcar | 2020 | Project development |  | 252200000 | 75000000
138 | Center City Connector Streetcar | 2021 | Project development |  | 285500000 | 75000000
139 | Sound Transit-Federal Way Link Extension | 2018 | Project development |  | 2165500000 | 500000000
139 | Sound Transit-Federal Way Link Extension | 2020 | Project development |  | 3160700000 | 790000000
140 | Madison Street Corridor BRT | 2019 | Project development |  | 121180000 | 59900000 | 9650000 | 2024
140 | Madison Street Corridor BRT | 2020 | Project development |  | 133380000 | 59900000 | 9650000 | 2024
141 | Link Extension and North Link | 2006 | EIS | 3.1 |  |  |  | 2017
141 | Link Extension and North Link | 2006 | Final Design | 3.1 |  |  |  | 2017
141 | Link Extension and North Link | 2009 | FFGA | 3.1 | 723330000 | 44000000 |  | 2017
142 | Airport Link | 2003 | EIS | 15.6 | 2558000000 | 500000000 |  | 2009
142 | Airport Link | 2008 | FFGA | 15.6 | 2558000000 | 500000000 |  | 2009
143 | North Link
144 | Everett to Seattle Commuter Rail | 1996 | Funding plan | 40 | 367000000 |  |  | 2006
144 | Everett to Seattle Commuter Rail | 1998 | Preliminary Engineering | 34.5 | 401000000 | 100000000 |  | 2008
144 | Everett to Seattle Commuter Rail | 1999 | Draft EIS | 35 | 104000000 | 24900000 |  | 2020
144 | Everett to Seattle Commuter Rail | 2000 | EIS | 35 | 104000000 | 24900000 |  | 2020
144 | Everett to Seattle Commuter Rail | 2006 | Final Design | 35 | 385000000 | 93000000 |  | 2020
145 | Federal Way Link Extension | 2018 | Project development |  | 1440000000
145 | Federal Way Link Extension | 2019 | Project development |  | 2165500000 | 500000000
145 | Federal Way Link Extension | 2020 | Project development |  | 3160700000 | 790000000
145 | Federal Way Link Extension | 2021 | FFGA |  | 3160704706 | 790000000
146 | Rapid Ride I | 2021 | Project development |  | 117000000 - 140000000
146 | Rapid Ride I | 2022 | Small Starts Project Development |  | 117634531 | 55628995
147 | Rapid Ride K | 2021 | Project development |  | 89800000
148 | Mill Plain Bus Rapid Transit | 2020 | Project development |  | 50000000 | 24900000
148 | Mill Plain Bus Rapid Transit | 2021 | Project development |  | 49900000 | 24900000
149 | Fourth Plain Bus Rapid Transit | 2015 | Project development | 6 | 53404002 | 38723202 | 4000000 | 2016
149 | Fourth Plain Bus Rapid Transit | 2016 | Project development | 5.9 | 53000000 | 38400000 | 4000000 | 2016
150 | Swift II | 2014 | Project development | 12 | 48000000 | 38000000 |  | 2018
150 | Swift II | 2016 | Project development |  | 66590000 | 43190000
150 | Swift II | 2017 | Project development |  | 73600000 | 47900000
150 | Swift II | 2018 | Project development |  | 73600000 | 43200000
151 | Tacoma Link Light Rail Expansion | 2016 | Project development | 2.4 | 166010000 | 74990000 | 11600000 | 2021
151 | Tacoma Link Light Rail Expansion | 2017 | Project development |  | 166000000 | 75000000
151 | Tacoma Link Light Rail Expansion | 2018 | Project development |  | 175600000 | 75000000
151 | Tacoma Link Light Rail Expansion | 2019 | Project development |  | 214600000 | 75000000
152 | Lakewood to Tacoma Commuter Rail | 1998 | Evironmental Assessment | 8.2
152 | Lakewood to Tacoma Commuter Rail | 1999 | Preliminary Engineering | 8 | 86000000 | 24900000 |  | 2001
152 | Lakewood to Tacoma Commuter Rail | 2003 | Final Design | 8 | 132000000 | 24900000
152 | Lakewood to Tacoma Commuter Rail | 2005 | Final Design | 8 | 205000000 | 41900000 |  | 2007
153 | Pacific Avenue/SR 7 Corridor | 2020 | Project development |  | 149900000 | 59700000
153 | Pacific Avenue/SR 7 Corridor | 2021 | Project development |  | 150000000 | 59900000
153 | Pacific Avenue/SR 7 Corridor | 2022 | Project development |  | 169997716 | 75202455
154 | Central City Line | 2017 | Project development |  | 72000000
154 | Central City Line | 2019 | Project development |  | 72000000 | 53400000
155 | Metra North Central Corridor | 2005 | FFGA | 16.3 | 225520000 | 75530000 |  | 2006
156 | Metra South West Corridor | 2004 | FFGA | 12 | 198120000 | 19680000 |  | 2006
157 | Central Area Circulator | 1995 -Terminated | FFGA |  | 775000000 | 116230000
158 | Ravenswood Line Extension | 2003 | Preliminary Engineering | 9.3 | 550000000 | 245600000 | 7890000
158 | Ravenswood Line Extension | 2004 | Preliminary Engineering | 9.3 | 529900000 | 245500000 | 7890000
158 | Ravenswood Line Extension | 2005 | Preliminary Engineering | 9.1 | 529900000 | 245520000
158 | Ravenswood Line Extension | 2007 | FFGA | 9.1 | 529910000 | 245520000 | 177570000 | 2009
158 | Ravenswood Line Extension | 2008 | FFGA | 9.1 | 529910000 | 245520000 | 177560000 | 2009
159 | Ashland Avenue BRT Phase I | 2013 | Environmental Assessment | 5.4 | 116900000 | 58300000
160 | Red and Purple Line Modernization Project | 2013 | Project development | 9.6 | 4700000000 | 1500000000
161 | Red and Purple Line Modernization Project Phase I | 2014 | Project development | 9.6 | 1700000000 |  |  | 2020-2021
161 | Red and Purple Line Modernization Project Phase I | 2015 | Project development |  | 1993250222 | 956607772
161 | Red and Purple Line Modernization Project Phase I | 2016 | Project development |  | 2066702783 | 956607772