## Table 1
Project Name |  | Project Sponsor | City/ Urbanized Area | State | Mode | Length | Number of Stations | Length of Exclusive BRT | Project Cost ($ millions) | CIG Funding Request ($ millions) | CIG Share | NEPA Completion | PD Entry Date | ENG Entry Date | LONP Request Date | LONP Decision Date | LONP Action | Project Rating Request Date* | Project Rating Date* | Overall Project Rating** | Non-CIG Matching Funds Status† | Estimated Grant Date‡
NS CC | Canarsie Line Power Improvements | NYMTA | New York | NY HR |  | 6 | 6 | N/A | 360.2 | 100 | 28% | 2016-08-24 | 2014-12-12 | 2017-06-02 | 2016-12-13 | 2017-01-19 | Approved | Aug 2016 | Nov 2016 | MH | Committed | Early 2024
| Green Line Transformation Program | MBTA | Boston | MA LRT |  | 23 | 66 | N/A | 2100 | TBD | TBD |  | 2022-05-12 | [7 empty] | In Progress | TBD
| FrontRunner Strategic Double Track Project | UDOT | Salt Lake City | UT CR |  | 83 | 16 | N/A | 1449.1 | TBD | TBD |  | 2022-11-02 |  |  |  |  | Aug 2022 | Nov 2022 | M | In Progress | TBD
| Inglewood Transit Connector Project | ITCJPA | Los Angeles | CA HR |  | 1.6 | 3 | N/A | 2018.8 | 1009.4 | 50% | 2023-03-16 | 2021-07-09 | 2023-12-28 |  |  |  | Aug 2023 | Oct 2023 | M | In Progress | Late 2024
| Red Line Extension | CTA | Chicago | IL HR |  | 5.6 | 4 | N/A | 3948 | 1974 | 50% | 2022-07-28 | 2020-12-15 | 2023-08-28 | 2023-02-08 | 2023-02-28 | Withdrawn | Mar 2023 | Jul 2023 | MH | In Progress | Late 2024
| METRO Blue Line Extension (Bottineau LRT) | Met Council | Minneapolis | MN LRT |  | 13.5 | 11 | N/A | 1536.2 | 752.7 | 49% | 2016-09-19 | 2014-08-22 | 2017-01-19 |  |  |  | Aug 2019 | Nov 2019 |  | In Progress | TBD
| NJ-NY Secaucus, Hudson Tunnels◊^ | GDC |  | NJ-NY CR |  | 6.5 | N/A | N/A | 14591 | 6880 | 43% | 2021-05-28 | 2016-07-14 | 2023-07-06 | 2023-07-07 | 2023-10-06 | Approved | Apr 2023 | Jun 2023 | MH | In Progress | Mid 2024
[15 empty] | 2023-07-10 | 2023-08-23 | Approved
| Lowcountry Rapid Transit | BCDCOG | Charleston | SC BRT |  | 21.3 | 20 | 11.7 | 625.1 | 375 | 60% | 2021-07-19 | 2019-09-27 | 2022-07-11 |  |  |  | May 2022 | July 2022 | MH | In Progress | Mid 2025
| Advanced Rapid Transit (ART) North-South Corridor | VIA | San Antonio | TX BRT |  | 10.3 | 26 | 7.9 | 446.3 | 267.8 | 60% | 2023-05-04 | 2021-08-23 | 2023-12-05 |  |  |  | Aug 2023 | Nov 2023 | MH | In Progress | Late 2024
| Capitol Extension Project | Valley Metro | Phoenix | AZ LRT |  | TBD | TBD | N/A | TBD | TBD | TBD |  | 2023-04-20 | [7 empty] | In Progress | TBD
| Valley Link Rail Project Phase 1 | TVSJVRRA | Livermore | CA CR |  | 26 | 4 | N/A | 1800 | 450 | 25% |  | 2022-05-26 | [7 empty] | In Progress | TBD
| West Santa Ana Branch Transit Corridor | LACMTA | Los Angeles | CA LRT |  | 14.8 | 9 | N/A | $4,900 - $5,100 | TBD | TBD |  | 2022-02-23 | [7 empty] | In Progress | TBD
| Transbay Downtown Rail Extension | Transbay JPA | San Francisco | CA CR |  | 2.2 | 2 | N/A | 8254.7 | 4077.9 | 49% | 2019-07-22 | 2021-12-06 | [7 empty] | In Progress | TBD
| BART Silicon Valley Phase II | VTA | San Jose | CA HR |  | 6 | 4 | N/A | 12237 | 6045.1 | 49% | 2021-03-08 | 2022-12-01 |  | 2022-10-18 | 2022-12-01 | Approved | Aug 2022 | Nov 2022 | MH | In Progress | TBD
| Northeast Corridor Rapid Transit Project | DTPW | Miami | FL CR |  | 13.5 | 7 | N/A | 538.1 | 263.7 | 49% | 2023-11-28 | 2021-10-26 |  |  |  |  | Aug 2023 |  |  | In Progress | TBD
| METRO Purple Line BRT | Met Council | St. Paul | MN BRT |  | 15 | 21 | 11 | 445 | 218 | 49% | 2021-10-05 | 2021-12-10 | [7 empty] | In Progress | TBD
| University Corridor Bus Rapid Transit Project | METRO | Houston | TX BRT |  | 25.3 | 41 | 23.9 | 2226 | 1335.6 | 60% | 2023-11-22 | 2021-09-29 |  |  |  |  | Aug 2022 | Nov 2022 | M | In Progress | TBD
| Richmond Highway BRT | Fairfax County | Fairfax County | VA BRT |  | 7.4 | 9 | 6.7 | 730 | 285 | 39% | 2022-01-07 | 2020-03-13 | [7 empty] | In Progress | TBD
| Ballard Link Extension | Sound Transit | Seattle | WA LRT |  | 7.1 | 9 | N/A | 9000 | TBD | TBD |  | 2022-07-13 | [7 empty] | In Progress | TBD
| West Seattle Link Extension | Sound Transit | Seattle | WA LRT |  | 4.7 | 3 | N/A | 3200 | TBD | TBD |  | 2022-07-13 | [7 empty] | In Progress | TBD
| Interstate Bridge Replacement Program | WSDOT | Vancouver/Portland | WA-ORLRT+ |  | 1.9 | 3 | 1.9 | 1800 | TBD | TBD |  | 2023-09-06 | [7 empty] | In Progress | TBD
SS | University-Medical BRT | City of Huntsville | Huntsville | AL BRT |  | 9 | TBD | N/A | 49 | TBD | TBD |  | 2023-05-26 | N/A | [6 empty] | In Progress | TBD
| Tucson High-Capacity Transit Project | City of Tucson | Tucson | AZ BRT |  | 4.7 | TBD | TBD | $117-$137 | TBD | TBD |  | 2023-09-14 | N/A | [6 empty] | In Progress | Early 2026
| Downtown Streetcar | LADOT | Los Angeles | CA SC |  | 3.4 | 23 | N/A | 296.4 | 100 | 34% | 2019-04-18 | 2014-02-28 | N/A |  |  |  | Sep 2018 | Nov 2018 | ML | In Progress | TBD
| SURF! Busway and Bus Rapid Transit Project | MST | Monterey Bay | CA BRT |  | 19.5 | 29 | 6 | 66 | 22.2 | 34% | 2023-01-25 | 2020-04-20 | N/A | 2023-09-20 |  |  | Aug 2022 | Nov 2022 | MH | In Progress | Fall 2024
| Downtown Riverfront Streetcar | SacRT | Sacramento | CA SC |  | 1.5 | 3 | N/A | 117 | 58.5 | 50% |  | 2014-05-01 | N/A | [6 empty] | In Progress | TBD
| East Colfax Avenue BRT | RTD | Denver | CO BRT |  | 8.5 | 28 | 5.5 | 255.3 | 126.9 | 50% |  | 2021-11-03 | N/A |  |  |  | Aug 2022 | Nov 2022 | H | In Progress | Mid 2024
| Federal Boulevard BRT Project | CDOT | Denver | CO BRT |  | 21 | TBD | TBD | 300 | TBD | TBD |  | 2023-10-26 | N/A | [6 empty] | In Progress | Late 2027
| West Elizabeth BRT Corridor Project | City of Fort Collins | Fort Collins | CO BRT |  | 3.6 | 10 | N/A | 110.6 | 71.9 | 65% | 2022-11-28 | 2021-07-20 | N/A |  |  |  | Aug 2023 |  |  | In Progress | Early 2025
| Broward Commuter Rail South | Broward County | Broward County | FL CR |  | 11.5 | 3 | N/A | 316.9 | 150 | 47% |  | 2022-12-02 | N/A | [6 empty] | In Progress | 2025
| East-West Corridor Rapid Transit Phase I Project | DTPW | Miami | FL BRT |  | 13.5 | 3 | TBD | 281 | 92.7 | 33% |  | 2021-10-26 | N/A | [6 empty] | In Progress | TBD
| SunRail Connector to the Orlando International Airport | FDOT | Orlando | FL CR |  | 5.5 | TBD | N/A | $175 - $225 | TBD | TBD | 2015-12-23 | 2015-10-26 | N/A | [6 empty] | In Progress | TBD
| Tampa Streetcar Extension and Modernization | City of Tampa | Tampa | FL SC |  | 4 | 17 | N/A | 234.5 | 99.9 | 43% |  | 2018-06-20 | N/A | [6 empty] | In Progress | TBD
| Campbellton Community Investment Corridor BRT | MARTA | Atlanta | GA BRT |  | 6 | 9 | 5.5 | 274.7 | TBD | TBD | 1905-07-17 | 2022-11-21 | N/A | [6 empty] | In Progress | TBD
| Clayton Southlake BRT | MARTA | Atlanta | GA BRT |  | 15.5 | 13 | TBD | 338.1 | 150 | 44% |  | 2022-02-24 | N/A | [6 empty] | In Progress | TBD
| IndyGo Blue Line Rapid Transit | IndyGo | Indianapolis | IN BRT |  | 24 | 30 | 13.4 | 371.9 | 149.9 | 40% |  | 2018-04-11 | N/A | 2021-11-30 | 2021-12-20 | Denied | Aug 2023 | Nov 2019 | MH | In Progress | Fall 2024
| East-West Bank BRT Corridor | RTA | New Orleans | LA BRT |  | 15.1 | 25 | 10.6 | 326 | TBD | TBD |  | 2023-08-08 | N/A | [6 empty] | In Progress | Early 2026
| Veirs Mill Road BRT | MCDOT | Montgomery County | MD BRT |  | 7.6 | 12 | TBD | 102 | TBD | TBD |  | 2022-09-09 | N/A | [6 empty] | In Progress | 2025
| METRO F Line Bus Rapid Transit | Met Council | Minneapolis | MN BRT |  | 13 | 32 | 6 | 98 | 53.4 | 54% |  | 2022-04-28 | N/A |  |  |  | Aug 2022 | Nov 2022 | M | In Progress | 2025
| Link Rapid Transit Project | City of Rochester | Rochester | MN BRT |  | 2.9 | 7 | 1.8 | 143.4 | 84.9 | 59% | 2023-12-04 | 2020-02-11 | N/A |  |  |  | Aug 2022 | Nov 2022 | MH | Committed | Late 2024
| North-South BRT | Chapel Hill Transit | Chapel Hill | NC BRT |  | 8.2 | 17 | 5.7 | 183 | 146.4 | 80% | 2023-03-08 | 2016-11-21 | N/A |  |  |  | Aug 2023 | Nov 2019 | M | In Progress | 2026
Project Name |  | Project Sponsor | City/ Urbanized Area | State | Mode | Length | Number of Stations | Length of Exclusive BRT | Project Cost ($ millions) | CIG Funding Request ($ millions) | CIG Share | NEPA Completion | PD Entry Date | ENG Entry Date | LONP Request Date | LONP Decision Date | LONP Action | Project Rating Request Date* | Project Rating Date* | Overall Project Rating** | Non-CIG Matching Funds Status† | Estimated Grant Date‡
SS | Wake Bus Rapid Transit: Southern Corridor Project | City of Raleigh | Raleigh | NC | BRT | 5.1 | 9 | 3.8 | 173.9 | 85.9 | 49% |  | 2021-07-14 | N/A |  |  |  | Aug 2022 | Nov 2022 | MH | In Progress | 2025
| Wake Bus Rapid Transit: Western Corridor | City of Raleigh | Raleigh | NC | BRT | 12 | 19 | TBD | 180 | TBD | TBD |  | 2020-12-23 | N/A | [6 empty] | In Progress | 2027
| Maryland Parkway Bus Rapid Transit Project | RTC | Las Vegas | NV | BRT | 12.5 | 29 | 7.3 | 378.1 | 150 | 40% | 2019-12-16 | 2020-01-30 | N/A |  |  |  | Nov 2023 | Dec 2023 | MH | Committed | March 2024
| Woodhaven Select Bus Service | NYDOT | New York | NY | BRT | 6.1 | 11 | 5.2 | 258.8 | 97.2 | 38% | 2015-07-13 | 2015-03-20 | N/A |  |  |  | Aug 2019 | Nov 2019 | MH | In Progress | TBD
| Hamilton Avenue Corridor BRT | SORTA | Cincinnati | OH | BRT | 9 | 12 | 7.4 | 138.6 | 110.9 | 80% |  | 2023-06-30 | N/A | [6 empty] | In Progress | 2025
| Reading Road Corridor BRT | SORTA | Cincinnati | OH | BRT | 10 | 15 | 7 | 156.7 | 109.7 | 70% |  | 2023-06-30 | N/A |  |  |  | Aug 2023 |  |  | In Progress | 2025
| MetroHealth Line BRT | GCRTA | Cleveland | OH | BRT | 4 | TBD | TBD | 50 | 20 | 40% |  | 2022-03-03 | N/A | [6 empty] | In Progress | Late 2024
| East Main Street BRT | COTA | Columbus | OH | BRT | 13 | 18 | TBD | $220 - $230 | TBD | TBD |  | 2021-10-22 | N/A | [6 empty] | In Progress | TBD
| West Broad Street BRT | COTA | Columbus | OH | BRT | 9.3 | 17 | 5.2 | 339.5 | 149.9 | 44% |  | 2021-10-22 | N/A |  |  |  | Aug 2023 |  |  | In Progress | 2027
| Memphis Innovation Corridor | MATA | Memphis | TN | BRT | 8 | 16 | 1 | 111.7 | 74.3 | 67% | 2021-02-11 | 2020-04-21 | N/A |  |  |  | Aug 2021 | Nov 2021 | M | In Progress | Early 2024
| METRORapid Gulfton Corridor Project | METRO | Houston | TX | BRT | 4.1 | 8 | TBD | 220 | TBD | TBD |  | 2023-06-30 | N/A | [6 empty] | In Progress | Late 2024
| Advanced Rapid Transit (ART) East-West Corridor | VIA | San Antonio | TX | BRT | 7.3 | 18 | 5.1 | 289.2 | 142.9 | 49% |  | 2022-10-28 | N/A |  |  |  | Aug 2023 |  |  | In Progress | 2026
| Midvalley Connector | UTA | Salt Lake County | UT | BRT | 7 | 15 | 1.4 | 103.4 | 62.8 | 61% | 2022-09-23 | 2021-04-23 | N/A |  |  |  | Jun 2022 | Oct 2022 | MH | In Progress | June 2024
| West End Transitway | City of Alexandria | Alexandria | VA | BRT | 5.3 | 15 | 2.7 | $119 - $140 | TBD | TBD | 2017-04-21 | 2016-07-06 | N/A | [6 empty] | In Progress | TBD
| Center City Connector | SDOT | Seattle | WA | SC | 1.3 | 4 | N/A | 285.5 | 75 | 26% | 2017-02-16 | 2014-07-21 | N/A | 2017-12-22 | 2018-02-16 | Approved | Aug 2019 | Nov 2019 | H | In Progress | TBD
| RapidRide I Line | King County Metro | Seattle | WA | BRT | 17 | 41 | 2 | 168.5 | 79.7 | 47% | 2021-06-10 | 2019-05-28 | N/A |  |  |  | Aug 2021 | Nov 2021 | MH | In Progress | Late 2024
| RapidRide J Line | SDOT | Seattle | WA | BRT | 5.2 | 11 | 2.3 | 128.5 | 64.2 | 50% | 2022-04-26 | 2017-09-08 | N/A |  |  |  | Aug 2021 | Nov 2021 | H | Committed | January 2024
| RapidRide K Line | King County Metro | Seattle | WA | BRT | 15.7 | 36 | TBD | 89.8 | TBD | TBD |  | 2019-12-20 | N/A | [6 empty] | In Progress | TBD
| Division Street Bus Rapid Transit Project | Spokane Transit A | City of Spokane | WA | BRT | 10 | 23 | TBD | 202 | TBD | TBD |  | 2023-09-19 | N/A | [6 empty] | In Progress | Late 2026
| Madison North-South BRT | City of Madison | Madison | WI | BRT | 11.5 | 24 | 5.2 | 150.7 | 118.1 | 78% |  | 2023-07-06 | N/A |  |  |  | Aug 2023 |  |  | In Progress | Mid 2025
| Milwaukee North-South BRT Corridor | Milwaukee County | Milwaukee | WI | BRT | 18 | 33 | 14.2 | 148.2 | TBD | TBD |  | 2023-02-01 | N/A | [6 empty] | In Progress | 2025
Guide to abbreviations:
Project Type: NS = New Starts, SS = Small Starts, CC = Core Capacity
Mode: BRT = Bus Rapid Transit, CR = Commuter Rail, HR = Heavy Rail, LRT = Light Rail Transit, SC = Streetcar
Rating: H = High, MH = Medium-High, M = Medium, ML = Medium-Low, L = Low
Other: CIG = Capital Investment Grant, NEPA = National Environmental Policy Act, PD = Project Development, Eng = Engineering, LONP = Letter of No Prejudice, TBD = To Be Determined, N/A = Not Applicable
* Ratings are point-in-time evaluations by FTA and may change as the projects proceed through planning and design. Project ratings are typically prepared for the Annual Report to Congress and for project advancement decisions such as Engineering approvals or construction grant awards.
** FY 2024 Annual Report to Congress or latest ratings
† 'Committed' means project sponsor has obtained all non-CIG matching funds; 'In Progress' means project sponsor is still working to obtain commitments of all non-CIG matching funds
‡ Estimated Grant Dates are based on projects meeting all of the readiness requirements to receive a construction grant, and are subject to change if these items are not completed by project sponsors in a timely manner.
◊ Joint Intercity-Public Transit project; CIG share reported as a percentage of the total overall project cost
^ USDOT TIFIA, RRIF, or RAISE funding also assumed
This CIG Dashboard is posted consistent with the requirements of 49 U.S.C. § 5309(r).