## year-data-srcs
temp_id | Project_ID | Name | Year | Milestone | Project length | Expected cost | Expected 5309 contribution | Expected other federal funds | Expected opening | Source
354 | 350 | TRAX Light Rail System- Medical Center Extension | AR-2005 | FFGA Awarded | AR-2005 | AR-2005 | AR-2005 |  | AR-2005 | AR-2005
355 | 350 | TRAX Light Rail System- Medical Center Extension | AR-2003 | Final Design | AR-2003 | AR-2003 | AR-2003 |  |  | AR-2003
356 | 350 | TRAX Light Rail System- Medical Center Extension | AR-2005 | Preliminary Engineering | AR-2005 | BA |  |  |  | AR-2005
357 | 350 | TRAX Light Rail System- Medical Center Extension | BA | Project Opening | BA |  |  |  |  | BA
355 | 350 | TRAX Light Rail System- Medical Center Extension | BA | Final Design | BA | BA | BA |  |  | BA
356 | 350 | TRAX Light Rail System- Medical Center Extension | BA | Preliminary Engineering | AR-2005 |  |  |  |  | AR-2005
354 | 350 | TRAX Light Rail System- Medical Center Extension | BA | FFGA Awarded | AR-2005 | AR-2005 | AR-2005 |  | AR-2005 | AR-2005
361 | #N/A | TRAX Light Rail System | BA | Final Design | [5 empty] | BA
362 | #N/A | TRAX Light Rail System | BA | Preliminary Engineering | [5 empty] | BA
363 | 307 | Draper Transit Corridor | AR-2013 | Preliminary Engineering |  | AR-2013 | AR-2013 |  |  | AR-2013
364 | 307 | Draper Transit Corridor | AR-2013 | FFGA Awarded |  | AR-2013 | AR-2013 |  |  | AR-2013
365 | 311 | FrontRunner North Rail Project | BA | Preliminary Engineering | BA | BA |  |  |  | BA
366 | 311 | FrontRunner North Rail Project | BA | Final Design | BA | BA |  |  |  | BA
367 | 311 | FrontRunner North Rail Project | BA | FFGA Awarded | BA | BA |  |  |  | BA
368 | 311 | FrontRunner North Rail Project | BA | Project Opening | BA |  |  |  |  | BA
369 | 302 | CBD to university LRT | AR-2005 | Preliminary Engineering | AR-2005 |  |  |  |  | AR-2005
370 | 302 | CBD to university LRT | AR-2005 | Final Design | AR-2005 |  |  |  |  | AR-2005
372 | 302 | CBD to university LRT | AR-2005 | Project Opening | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005
373 | 302 | CBD to university LRT | AR-2002 | FFGA Awarded | AR-2003 | AR-2003 | AR-2003 | AR-2003 | AR-2003 | AR-2003
374 | 332 | Provo-Orem Bus Rapid Transit | AR-2014 | Project Development | AR-2014 | AR-2014 | AR-2014 |  | AR-2014 | AR-2014
377 | 332 | Provo-Orem Bus Rapid Transit | AR-2018 | CGA | [5 empty] | AR-2018
378 | 325 | Ogden/Weber State University BRT | PP | Project Development | PP |  |  |  | PP | PP
379 | 320 | Minillas Extension | AR-2002 |  |  | AR-2002 | AR-2002 |  |  | AR-2002
379 | 320 | Minillas Extension | AR-2000 |  |  | AR-2002 | AR-2002 |  |  | AR-2002
381 | 351 | Tren Urbano | AR-2004 |  | AR-2004 | AR-2004 | AR-2004 |  |  | AR-2004
382 | 351 | Tren Urbano | AR-1997 | FFGA Awarded | AR-1997 | AR-1997 | AR-1997 | AR-1997 | AR-2005 | AR-1997
388 | 351 | Tren Urbano | AR-2007 | Project Opening | AR-2007 | AR-2007 | AR-2007 | AR-2007 |  | AR-2007
391 | #N/A | St. Clair County, Illinois Corridor | AR-1997 | FFGA Awarded | AR-1997 | AR-1997 | AR-1997 |  | AR-1997 | AR-1997
391 | #N/A | St. Clair County, Illinois Corridor | AR-1998 | FFGA Awarded | AR-1997 | AR-1997 | AR-1997 |  | AR-1997 | AR-1997
391 | #N/A | St. Clair County, Illinois Corridor | AR-2003 | FFGA Awarded | AR-1997 | AR-1997 | AR-1997 |  | AR-1997 | AR-1997
394 | 340 | St. Clair County, Illinois Corridor (IOS-1) | AR-1999 | FFGA Awarded | AR-1999 | AR-1999 | AR-1999 |  |  | AR-1999
395 | #N/A | St. Clair County, Illinois Corridor | AR-2005 | Preliminary Engineering | AR-2005 | AR-2005 | AR-2005 |  |  | AR-2005
396 | #N/A | St. Clair County, Illinois Corridor | AR-2005 | Final Design | AR-2005 | AR-2005 | AR-2005 |  | AR-2005 | AR-2005
391 | #N/A | St. Clair County, Illinois Corridor | AR-2005 | FFGA Awarded | AR-1997 | AR-1997 | AR-1997 |  | AR-1997 | AR-1997
398 | #N/A | St. Clair County, Illinois Corridor | AR-2005 | Project Opening | AR-2005 | AR-2005 | AR-2005 |  |  | AR-2005
399 | 338 | Southtown Corridor | AR-1997 | Preliminary Engineering | AR-1997 | AR-1997 | AR-1997 |  |  | AR-1997
400 | #N/A | Southtown Corridor (Segment) | AR-2000 | Preliminary Engineering | AR-2000 | AR-2000 | AR-2000 |  |  | AR-2000
402 | 343 | Streetcar Expansion | PP | Project Development | PP | PP | PP |  | PP | PP
403 | 337 | Southtown BRT | AR-2005 | Preliminary Engineering | AR-2005 | AR-2005 | AR-2005 |  |  | AR-2005
404 | 337 | Southtown BRT | N.R. | Final Design | N.R. | N.R. | N.R. |  |  | OTHER
405 | 331 | Prospect MAX Bus Rapid Transit | AR-2017 | Project Development | [5 empty] | AR-2017
407 | 314 | I-35 Commuter Rail | AR-2002 | Preliminary Engineering | AR-2002 | AR-2002 | AR-2002 |  |  | AR-2002
408 | 352a | Tri-County Commuter Rail | AR-1997 |  | AR-1997 | AR-1997 | AR-1997 | AR-1997 | AR-1997 | AR-1997
408 | 352a | Tri-County Commuter Rail | AR-1998 |  | AR-1997 | AR-1997 | AR-1997 | AR-1997 | AR-1997 | AR-1997
408 | 352a | Tri-County Commuter Rail | AR-2000 |  | AR-1997 | AR-1997 | AR-1997 | AR-1997 | AR-1997 | AR-1997
411 | 352b | Tri-County Commuter Rail / Segment 5 | AR-2001 | Final Design | AR-2001 | AR-2001 | AR-2001 | AR-2001 | AR-2001 | AR-2001
412 | 352b | Tri-County Commuter Rail / Segment 5 | AR-2002 |  |  | AR-2002 | AR-2002 | AR-2002 | AR-2002 | AR-2002
415 | 353 | Tri-Rail Double-track Corridor Improvement | BA | Preliminary Engineering | BA | BA | BA | BA | BA | BA
416 | 353 | Tri-Rail Double-track Corridor Improvement | BA | FFGA Awarded | BA | BA | AR-2003 | AR-2003 | BA | BA
418 | 353 | Tri-Rail Double-track Corridor Improvement | BA | Project Opening | BA |  |  |  |  | BA
419 | 309 | East-West Corridor/Miami Intermodal Center | AR-1997 |  | AR-1997 | AR-1997 | AR-1997 |  |  | AR-1997
420 | 309 | East-West Corridor/Miami Intermodal Center | AR-1998 | Preliminary Engineering | [5 empty] | AR-1998
421 | #N/A | East-West Corridor/Miami Intermodal Center (MOS) | AR-1998 | Preliminary Engineering | AR-1998 | AR-1998 | AR-1998 |  |  | AR-1998
421 | #N/A | East-West Corridor/Miami Intermodal Center (MOS) | AR-2000 | Preliminary Engineering | AR-1998 | AR-1998 | AR-1998 |  |  | AR-1998
423 | 319 | Miami (North 27th Avenue Corridor) | AR-1997 |  | AR-1997 | AR-1997 | AR-1997 |  |  | AR-1997
424 | 322 | North 27th Avenue Corridor | AR-2002 | Preliminary Engineering | AR-2002 | AR-2002 | AR-2002 |  |  | AR-2002
425 | 323 | North Corrido Metro Rail Extension | AR-2005 | Preliminary Engineering | AR-2005 | AR-2005 | AR-2005 | AR-2005 |  | AR-2005
426 | 334 | South Corridor Rapid Transit Project | PP | Project Development | PP | PP | PP |  | PP | PP
427 | 336 | South Miami-Dade Bustway Extension | AR-2002 | Preliminary Engineering | AR-2002 | AR-2002 | AR-2002 | AR-2002 |  | AR-2002
428 | 336 | South Miami-Dade Bustway Extension | AR-2002 | Final Design | AR-2002 | AR-2002 | AR-2002 | AR-2002 |  | AR-2002
429 | 304 | Central Broward Transit Study, Phase I | AR-2017 | Project Development | [5 empty] | AR-2017
430 | #N/A | Central Florida Light Rail System- Initial Operating Segment | AR-2013 | FFGA Awarded | AR-2013 | AR-2013 | AR-2013 |  | AR-2013 | AR-2013
431 | #N/A | Central Florida Light Rail System- Initial Operating Segment | AR-2013 | Final Design | AR-2013 | AR-2013 | AR-2013 |  | AR-2013 | AR-2013
432 | #N/A | Central Florida Light Rail System- Initial Operating Segment | AR-2013 | Preliminary Engineering | AR-2013 | AR-2013 | AR-2013 |  | AR-2013 | AR-2013
433 | 328 | Orlando (I-4 Central Florida Light Rail System) (MOS) | AR-1998 |  | AR-1998 | AR-1998 | AR-1998 |  | AR-1998 | AR-1998
433 | 328 | Orlando (I-4 Central Florida Light Rail System) (MOS) | AR-2000 |  | AR-1998 | AR-1998 | AR-1998 |  | AR-1998 | AR-1998
435 | 345 | SunRail Phase II North | AR-2015 | FFGA Awarded | AR-2015 | AR-2015 | AR-2015 |  | AR-2015 | AR-2015
436 | 345 | SunRail Phase II North | PP | Project Development | PP | PP | PP |  | PP | PP
438 | 346 | SunRail Phase II South | AR-2014 | Engineering | AR-2014 | AR-2014 | AR-2014 |  | AR-2014 | AR-2014
441 | 346 | SunRail Phase II South | AR-2017 | CGA |  | AR-2017 | AR-2017 |  |  | AR-2017
443 | 344 | SunRail Connector to Orlando Airport | AR-2017 | Project Development | AR-2017 |  |  |  |  | AR-2017
445 | 305 | Central Florida Commuter Rail Transit – Initial Operating Segment | AR-2013 | Preliminary Engineering | AR-2013 | AR-2013 | AR-2013 |  |  | AR-2013
447 | 305 | Central Florida Commuter Rail Transit – Initial Operating Segment | AR-2013 | Final Design | AR-2013 | AR-2013 | AR-2013 |  | AR-2014 | AR-2013
448 | 305 | Central Florida Commuter Rail Transit – Initial Operating Segment | AR-2013 | FFGA Awarded | AR-2013 | AR-2013 | AR-2013 |  |  | AR-2013
449 | 305 | Central Florida Commuter Rail Transit – Initial Operating Segment | BA | Project Opening | BA |  |  |  |  | BA
450 | 310 | Flagler to duPont Place | AR-1997 | FFGA Awarded | AR-1997 | AR-1997 | AR-1997 |  |  | AR-1997
451 | 310 | Flagler to duPont Place | AR-1998 | FFGA Awarded |  | AR-1998 | AR-1998 |  |  | AR-1998
452 | 335 | South Extension of the Automated Skyway Express (ASE) | AR-1995 | FFGA Awarded | AR-1995 | AR-1995 | AR-1995 |  |  | AR-1995
453 | #N/A | JTA Bus Rapid Transit North Corridor | AR-2013 | Project Development | AR-2013 | AR-2013 | AR-2013 |  |  | AR-2013
454 | #N/A | BRT North Corridor | AR-2017 | CGA | [5 empty] | AR-2017
455 | 308 | East Corridor | AR-2017 | Project Development |  | AR-2017 | AR-2017 |  |  | AR-2017
456 | #N/A | JTA Bus Rapid Transit Southeast Corridor | AR- | Project Development | AR- | AR- | AR- |  |  | AR-
457 | 339 | Southwest Corridor | AR-2017 | Project Development |  | AR-2017 | AR-2017 |  |  | AR-2017
458 | 354 | Wave Streetcar | AR-2014 | Project Development | AR-2014 | AR-2014 | AR-2014 | AR-2014 | AR-2014 | AR-2014
461 | 354 | Wave Streetcar | AR-2019 | CGA | AR-2019 |  |  |  |  | AR-2019
462 | 316 | JTA BRT Southeast Corridor | AR-2014 | Project Development | AR-2014 | AR-2014 | AR-2014 |  | AR-2014 | AR-2014
465 | 315 | JTA BRT North Corridor | AR-2014 | Project Development | AR-2014 | AR-2014 | AR-2014 |  | AR-2014 | AR-2014
468 | 303 | Central Avenue Bus Rapid Transit Project | PP | Project Development | PP | PP | PP |  | PP | PP
469 | 347 | Tampa Bay Regional Rail | AR-2005 | Preliminary Engineering | AR-2005 | AR-2005 | AR-2005 |  |  | AR-2005
470 | 348 | Tampa Streetcar Extension Project | OTHER | Project Development | OTHER |  | OTHER |  | OTHER | OTHER
471 | #N/A | Largo Corridor | AR-1997 | Preliminary Engineering | AR-1997 | AR-1997 | AR-1997 |  |  | AR-1997
471 | #N/A | Largo Corridor | AR-1998 | Preliminary Engineering | AR-1997 | AR-1997 | AR-1997 |  |  | AR-1997
473 | #N/A | Largo Corridor | AR-2000 |  | AR-2000 | AR-2000 | AR-2000 |  | AR-2000 | AR-2000
474 | #N/A | Largo Corridor | AR-2002 | FFGA Awarded | AR-2002 | AR-2002 | AR-2002 |  | AR-2002 | AR-2002
475 | 317 | Largo Metrorail Extension | AR-2005 | Final Design | AR-2005 | AR-2005 | AR-2005 |  | AR-2005 | AR-2005
476 | 317 | Largo Metrorail Extension | AR-2005 | FFGA Awarded | AR-2005 | AR-2005 | AR-2005 |  | AR-2005 | AR-2005
477 | 301 | Canal Streetcar Spine | AR-1997 | Preliminary Engineering | AR-1997 | AR-1997 | AR-1997 |  |  | AR-1997
479 | 301 | Canal Streetcar Spine | AR-2000 | Final Design | AR-2000 | AR-2000 | AR-2000 |  | AR-2001 | AR-2000
482 | 301 | Canal Streetcar Spine | AR-2005 | FFGA Awarded | AR-2005 | AR-2005 | AR-2005 |  | AR-2005 | AR-2005
483 | 306 | Desire Streetcar Line | AR-2002 | Preliminary Engineering | AR-2002 | AR-2002 | AR-2002 |  |  | AR-2002
486 | 341 | St. Claude and Elysian Fields Streetcar Extensions | PP | Project Development | PP |  |  |  | PP | PP
487 | #N/A | TramLinkBR Streetcar | AR-2018 | Project Development | [5 empty] | AR-2018
488 | 349 | TramLinkBR | PP | Project Development | PP | PP | PP |  | PP | PP
489 | #N/A | Hudson-Bergen Waterfront Light Rail Transit System | AR-1997 | Preliminary Engineering | AR-1997 | AR-1997 | AR-1997 |  |  | AR-1997
490 | #N/A | Hudson-Bergen Waterfront Light Rail Transit System | AR-1999 |  | AR-1999 | AR-1999 |  |  |  | AR-1999
490 | #N/A | Hudson-Bergen Waterfront Light Rail Transit System | AR-2000 |  | AR-1999 | AR-1999 |  |  |  | AR-1999
492 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | AR-1997 | Preliminary Engineering | AR-1997 |  |  |  |  | AR-1997
493 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | AR-1998 | FFGA Awarded | AR-1998 | AR-1998 | AR-1998 | AR-1998 | AR-1998 | AR-1998
493 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | AR-2000 | FFGA Awarded | AR-1998 | AR-1998 | AR-1998 | AR-1998 | AR-1998 | AR-1998
493 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | AR-2005 | FFGA Awarded | AR-1998 | AR-1998 | AR-1998 | AR-1998 | AR-1998 | AR-1998
493 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | AR-2003 | FFGA Awarded | AR-1998 | AR-1998 | AR-1998 | AR-1998 | AR-1998 | AR-1998
497 | 313a | Hudson-Bergen Waterfront Light Rail Transit System (MOS-1) | AR-2005 | Project Opening | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005
498 | 313b | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) | AR-2010 | FFGA Awarded | AR-2010 | AR-2010 | AR-2010 | AR-2010 |  | AR-2010
498 | 313b | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) | AR-2007 | FFGA Awarded | AR-2010 | AR-2010 | AR-2010 | AR-2010 |  | AR-2010
500 | 313b | Hudson-Bergen Waterfront Light Rail Transit System (MOS-2) | AR-2001 |  | AR-2001 | AR-2001 | AR-2001 | AR-2001 |  | AR-2001
501 | 321a | Newark-Elizabeth Rail Link | AR-1997 |  | AR-1997 | AR-1997 |  |  |  | AR-1997
502 | 321b | Newark-Elizabeth Rail Link (MOS I) | AR-2000 |  | AR-2000 | AR-2000 | AR-2000 | AR-2000 |  | AR-2000
502 | 321b | Newark-Elizabeth Rail Link (MOS I) | AR-2001 |  | AR-2000 | AR-2000 | AR-2000 | AR-2000 |  | AR-2000
504 | 321b | Newark-Elizabeth Rail Link (MOS I) | AR-2005 | FFGA Awarded | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005
505 | 333 | Secaucus Transfer Station | AR-1997 | FFGA Awarded | AR-1997 | AR-1997 | AR-1997 |  | AR-1997 | AR-1997
506 | 312 | Hudson Tunnel | AR-2018 | Project Development | [5 empty] | AR-2018
507 | 330 | Portal North Bridge Replacement | AR-2018 | Project Development | [5 empty] | AR-2018
507 | 330 | Portal North Bridge Replacement | PP | Project Development | [5 empty] | AR-2018
509 | 327 | Oklahoma city (Map Links) Park Avenue Rail Loop | AR-1997 |  | AR-1997 | AR-1997 | AR-1997 | AR-1997 |  | AR-1997
510 | 326 | Oklahoma city (Map Links) | AR-1998 |  | AR-1998 | AR-1998 | AR-1998 | AR-1998 |  | AR-1998
511 | 329 | Phase I Airport Busway/Wabash HOV Facility | AR-1996 | FFGA Awarded | AR-1996 | AR-1996 | AR-1996 | AR-1996 |  | AR-1996
511 | 329 | Phase I Airport Busway/Wabash HOV Facility | AR-1997 | FFGA Awarded | AR-1996 | AR-1996 | AR-1996 | AR-1996 |  | AR-1996
511 | 329 | Phase I Airport Busway/Wabash HOV Facility | AR-1998 | FFGA Awarded | AR-1996 | AR-1996 | AR-1996 | AR-1996 |  | AR-1996
511 | 329 | Phase I Airport Busway/Wabash HOV Facility | AR-1999 | FFGA Awarded | AR-1996 | AR-1996 | AR-1996 | AR-1996 |  | AR-1996
515 | 318 | Martin Luther King, Jr. East Busway Extension | AR-2000 |  | AR-2000 | AR-2000 | AR-2000 | AR-2000 |  | AR-2000
516 | 342 | Stage II Light Rail Transit Reconstruction Project | AR-1997 | Preliminary Engineering | AR-1997 | AR-1997 | AR-1997 | AR-1997 |  | AR-1997
517 | 342 | Stage II Light Rail Transit Reconstruction Project | AR-2000 | Final Design | AR-2000 | AR-2000 | AR-2000 | AR-2000 |  | AR-2000
516 | 342 | Stage II Light Rail Transit Reconstruction Project | AR-2001 | Preliminary Engineering | AR-1997 | AR-1997 | AR-1997 | AR-1997 |  | AR-1997
519 | 342 | Stage II Light Rail Transit Reconstruction Project | AR-2005 | FFGA Awarded | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005
520 | 324 | North Shore LRT Connector | AR-2002 | Preliminary Engineering | AR-2002 | AR-2002 | AR-2002 |  |  | AR-2002
520 | 324 | North Shore LRT Connector | AR-2003 | Preliminary Engineering | AR-2002 | AR-2002 | AR-2002 |  |  | AR-2002
520 | 324 | North Shore LRT Connector | AR-2004 | Preliminary Engineering | AR-2002 | AR-2002 | AR-2002 |  |  | AR-2002
523 | 324 | North Shore LRT Connector | AR-2005 | Final Design | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005
524 | 324 | North Shore LRT Connector | AR-2010 | FFGA Awarded | AR-2010 | AR-2010 | AR-2010 | AR-2010 |  | AR-2010
520 | 324 | North Shore LRT Connector | BA | Preliminary Engineering | AR-2002 | AR-2002 | AR-2002 |  |  | AR-2002
523 | 324 | North Shore LRT Connector | BA | Final Design | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005 | AR-2005
524 | 324 | North Shore LRT Connector | BA | FFGA Awarded | AR-2010 | AR-2010 | AR-2010 | AR-2010 |  | AR-2010
528 | 324 | North Shore LRT Connector | BA | Recovery Plan | BA | BA |  |  |  | BA
529 | 324 | North Shore LRT Connector | BA | Project opening | BA |  |  |  |  | BA